|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2020/20/Up Keeping Date: 06.05.2022

**M/s D N Virkar Engineers and Contractor,**

**204, Usha Garden Society,**

**Rambaug No.4**

**Kalyan 421301**

**(Amendment No.1 to Gem Contract No. GEM-511687782760106 dated 06.05.2022)**

Sub:- Maintenance & Up-Keeping of Electric Loco Shed Kalyan including SMM/ELS/KYN and Trip Sheds at CSMT, VVH, LNL & IGP for a period of two years

Ref : i) This office Gem Contract No. GEM-511687782760106 dated 06-05-2022.

ii) Your offer against GeM Bid No. GEM/2022/B/2050019 dated 17.03.2022

--\*\*--

Vide above mentioned GeM Contract an order has been awarded to you against GeM Bid GEM/2022/B/2050019 dated 17.03.2022 on **Rs.1,90,16,620.86 inclusive of all**. However, asthe amount mentioned by you in price break up against the item no.5. “Maintenance and Up-keeping of all offices” is incorrect (Rates quoted by you is Rs.0.94 from which amount works out to Rs.36,27,669.94 instead of Rs.36,66,262.17) your order has been accepted by the competent authority at **Rs.1,89,78,028.64 (Rupees One Crore Eighty- Nine Lakh Seventy- Eight Thousand Twenty Eight and Sixty- Eight Paisa only) as per Annexure-A** inclusive of all taxes, duties, GST, transportation, labour charges (based on minimum wages rate as per Minimum Wages Act, 1948), consumable materials, machinery/ tool & tackles, statutory charges etc. for subject service from 13.05.2022 to 12.05.2024.

The contract start date as per the contract is 13.05.2022 and end date is 12.05.2024. However, the existing contract of this office is expiring on 07.05.2022 hence for the uninterrupted service this office intended to start this work immediately. Therefore you are requested to start this contract at the earliest i.e from 08.05.2022 and accordingly contract end date will be 07.05.2024.

Other terms and conditions will be remain unaltered as per Contract No. GEM-511687782760106 dated 06.05.2022.

You are requested to acknowledge the receipt of this amendment to this office at the earliest.

(Niraj Kumar Garg)

Sr.Divisional Electrical Engineer

(Traction Rolling Stock)

Central Railway, Kalyan

Copy: Sr. DFM, CSTM

Budget supervisor

SSE/General Section. For information. He will co-ordinate & supervise the work.