|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No.ELSKYN/WKS/2020/16/Tap Changer Date: 19-07-2025

**Sr.DEE (TRS) BSL**

|  |  |
| --- | --- |
| Sub: | Extension of time for the work against, LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/ 00967350038710 dated 21-07-2021 for Repair, Rehabilitation, Reconditioning, Testing and Supply of Tap Changer of Electric Locomotives based at Electric Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.” |
| Ref: | 1. This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/ 00967350038710 dated 21-07-2021. 2. This office letter of even no. dated 10-09-2024. |

--\*\*--

The contract for the subject work was awarded to M/s River Engineering Pvt Ltd, 54-55, Toy City, Ecotech-III, Greater Noida, Noida – 201206, vide LOA under reference (1). This contract is for 70 Nos. tap changers for three different sheds i.e. Ajni, Bhusawal and ELS Kalyan.

As on date, the work pertaining to the schedule quantity for ELS/KYN and ELS/AQ has been completed. However, work related to 3 tap changers is still pending execution by the firm.

The original completion period for this contract was up to **20.07.2024**, which was subsequently extended up to **20.07.2025** vide this office letter under reference (2). But the entire quantity has not been completed within the extended period.

In view of the above, you are requested to kindly intimate this office whether an extension is required to complete the remaining quantity. If so, please furnish a proper justification for the delay in execution of the balance quantity. You are also requested to confirm whether levy of penalty is applicable in this case, and if yes, the same may be conveyed accordingly.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 18.07.2025**

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1.) LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2.) Your office letter no. ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

3). HQ Letter No.L.253.AC.118.Vol-VI dated 24.01.2023

4.) HQ Letter No.L.253.AC.118.Vol-VI dated 20.06.2023

5.) RB letter no.2023/Elect(TRS)/440/3 dated 16.11.2023

6.) HQ Letter No.L.253.AC.118.Vol-VII dated 13.06.2024

7.) ELS/AQ/DRG/WCQ/21-22/10 dtd. 17.04.2025

--\*\*--

With reference to your office LOA a contract for the subject has been awarded to M/s AAL Noida for ELS/KYN, ELS/BSL & ELS/AQ. The schedule quantity of ELS/KYN is 9855 loco days for 09 locos.

Due to transfer of locos from ELS/AQ to ELS/KYN vide HQ & RB letters under Ref. 3, 4 & 6 holding of ELS/KYN for AAL SIV is increased from 09 Nos. to 25 Nos. Further, 09 locos transferred from ELS/KYN to ELS/BSL vide HQ letter under Ref.6. Hence the total number of loco days will be executing till 12th quarter are 17,232 Nos.

Vide letter at ref. (7), extension period of subject work was extended up to 31.07.2025

The new tender for above work opened on dtd. 02/05/2025 and is under TC and it will take 2-3 months in finalization. Hence there is need to carry out quantity variation for 3 months up to 31/10/2025 in current contract

The details of loco days required for quantity variation are as under:

|  |  |  |
| --- | --- | --- |
| Sr. No. | Period | Total required loco days. |
| 1. | 22.04.2022 to 21.04.2025 | 17232 |
| 2. | 22.04.2025 to 31.07.2025 | 1616 |
| 3. | 01.08.2025 to 31.10.2025 | 1472 |
|  | Total No. of days required for ELS/KYN | 20,320 |

**(ASHISH GUPTA)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No: ELSKYN/WKS/2023/10/FDCS-Medha Date: 18.07.2025

**Sr.DEE (TRS) BSL**

Sub :- Annual Maintenance Contract of M/s Medha Make Microprocessor Based Control & Fault Diagnostic System (MPCS) Ver 2 of AC Conventional Locomotives as per RDSO’s SMI No. RDSO/2016/EL/SMI/0288 (Rev) for a period of 3 years at Electric Loco Shed, Kalyan, Qty- 07 Nos.

Ref :- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER-

2023-13 / 00987030096072 dated 24.01.2024

2. Your office letter no. BSL/TRS/Tender/2023/13 dated 15.03.2024

--\*\*--

With reference to your office letter at Ref.1 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 15.03.2024. Vide Joint Note No. ELS/KYN/I&E/Medha/MPCS dated 14.03.2024 & 15.03.2024

AMC work of Medha make FDCS (V-2 & V-3) for 5th Qtr. i.e. from 15.03.2025 to 14.06.2025 has been carried out by firm as per LOA and scope of work satisfactorily. The Joint Note, down time calculation & penalty calculation statement of 5th Qtr. duly signed by DEE (TRS) KYN are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills

.

**(ASHISH GUPTA)**

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**ELSKYN/WKS/2020/17/AMC SIV Siemens DATE:- 24.06.2025**

**Sr. DEE/TRS**

**BHUSAWAL**

**Subject:** Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan

**Ref:** 1. **Contract Agreement** No. BSL/TRS/Tender/2017/06 dated 08.03.2018

2. Your office letter no. BSL/TRS/Tender/2017/06 dated 08.05.2025

--\*\*--

In view of your letter under ref-2 for the subject work, it is stated that the work is successfully completed in all respects at ELS/KYN.

This is for your information & necessary action please.

|  |
| --- |
| (**Ashish Gupta**) DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

**No: ELSKYN/WKS/Misc. Date: 17.06.2025**

CWM/ELW/BSL

Sub: - Warranty obligation and attending the defect of BA Panel components

of Loco No. 21899, 21943, 21951.

Ref: (i) ELW BSL Letter no. ELW/BSL/Tender/Warranty failure dated

06.06.2025

(ii) ELSKYN.ACE.FR.ELWBSL/08 dated 17.06.2025

--\*\*--

ELW BSL vide letter under reference (i) has requested to convey the expenditure occurred

in attending defects on loco no. 21899, 21943, and 21951 by the railways so that same can be recovered from the firm.

Further the cost of warranty failure attended, as asked vide your letter at ref (i),

works out to be Rs 30,590.10 as detailed in Note No. ELSKYN.ACE.FR.ELWBSL/08 dated 17.06.2025 (Copy enclosed). However other losses on account of said failure may please be confirmed from other respective department.

This is for your information and further action at your end.

(**Ashish Gupta**)

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2025/IPAS Date. 31.05.2025

**AEDPM (T)**

**CSMT**

Sub: Creation of IPAS user ID

--\*\*\*--

Kindly create IPAS user for following Supervisor of ELS Kalyan, the details are as under:

|  |  |  |
| --- | --- | --- |
| Sr. No. | Particulars | Details |
| 1 | Name | Sanjeev Kumar |
| 2 | Designation | SSE/Drg |
| 3 | Mobile No. | 7021519393 |
| 4 | Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| 5 | PF No. | 00211030859 |

(**Ashish Gupta**)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No: ELSKYN/WKS/2023/10/FDCS-Medha Date: 17.04.2025

**Sr.DEE (TRS) BSL**

Sub :- Annual Maintenance Contract of M/s Medha Make Microprocessor Based Control & Fault Diagnostic System (MPCS) Ver 2 of AC Conventional Locomotives as per RDSO’s SMI No. RDSO/2016/EL/SMI/0288 (Rev) for a period of 3 years at Electric Loco Shed, Kalyan, Qty- 07 Nos.

Ref :- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER-

2023-13 / 00987030096072 dated 24.01.2024

2. Your office letter no. BSL/TRS/Tender/2023/13 dated 15.03.2024

--\*\*--

With reference to your office letter at Ref.1 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 15.03.2024. Vide Joint Note No. ELS/KYN/I&E/Medha/MPCS dated 14.03.2024 & 15.03.2024

AMC work of Medha make FDCS (V-2 & V-3) for 3rd Qtr. i.e. from 15.09.2024 to 14.12.2024 and 4th Qtr i.e from 15.12.2024 to 14.03.2025 has been carried out by firm as per LOA and scope of work satisfactorily. The Joint Note, down time calculation & penalty calculation statement of 3rd Qtr and 4th Qtr duly signed by DEE (TRS) KYN are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills

.

**(ASHISH GUPTA)**

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2024/38/ MISC ABB Propulsion Date: 16.04.2025**

**Sr.DEE (TRS) AQ**

Sub:- CAMC of M/s ABB make Propulsion System for a period of 03 years at ELS/KYN

Ref:- LOA No. ELS/AQ/DRG/WCQ/24-25-01 dated 03.05.2024.

--\*\*--

With reference to above referred contract a Joint note of **1st Qtr** i.e from 04.05.2024 to 03.08.2024, **2nd Qtr** i.e from 04.08.2024 to 03.11.2024, and **3rd Qtr** i.e from 04.11.2024 to 03.02.2025 duly signed by concerned officer in-charge is sent to your office for passing payment. The CAMC work of ABB make Propulsion for has been carried out by firm as per LOA and scope of work satisfactorily.

The certificate for measurement of 1st to 3rd Quarter of above-mentioned contract is as under: -

1. It is certified that, 20% work check done by me.
2. It is certified that; this work is completed for ELS/AQ contract under ref. on 03.02.2025.

Joint notes of these quarters (1st to 3rd Qtr) duly signed are sent herewith for further necessary for processing payment.

**(Shri. Ashish Gupta)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No. ELSKYN/WKS/2022-27-EOT-AMT-B Date: 12.04.2025**

**DEE (TRS) GKP**

**ELS/Gorakhpur/NCR**

Sub:- Regarding Verification of Performance Letter Submitted by firm.

Ref:- 1. LOA no. ELSKYNWKS22-27-EOT-AMT-B / 00224660084174 dtd 10.08.2023

2. Your office letter no.ELS/GKP/CAMC/CRANE/24-25 dated 07.04.2025

--\*\*--

With reference to your office letter under Ref.2, it is certified that Appreciation/ Performance letter No.ELS.KYN.Misc dated 09.07.2024 is authentic and issued by this office for work done against LOA under Ref.2. 100% payment for the same has been made to the firm as per payment terms of LOA.

**(BHUPESH YADAV)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 23.08.2024**

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no. ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to above referred contract a Joint note and penalty statement upto 7th Qtr. i.e 22.04.2022 to 21.01.2024 duly signed by concerned officer in-charge was sent to your office for passing payment as stated in your office letter mentioned at Ref.2.

Now CAMC work of AAL make SIV for 8th Qtr i.e from 22.01.2024 to 21.04.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

The certificate for measurement of 8th Quarter of above-mentioned contract is as under: -

1. It is certified that, 20% work is check done by me.
2. It is certified that; this work is under process.

Joint notes and penalty statements of these quarters (8th Qtr) duly signed by DEE/TRS/Kalyan are sent herewith for further necessary action at your end.

**(Shri. Ashish Gupta)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 28.03.2025**

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no. ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

3. HQ Letter No.L.253.AC.118.Vol-VI dated 24.01.2023

4. HQ Letter No.L.253.AC.118.Vol-VI dated 20.06.2023

5. RB letter no.2023/Elect(TRS)/440/3 dated 16.11.2023

6. HQ Letter No.L.253.AC.118.Vol-VII dated 13.06.2024

--\*\*--

With reference to your office LOA a contract for the subject has been awarded to M/s AAL Noida for ELS/KYN, ELS/BSL & ELS/AQ. The schedule quantity of ELS/KYN is 9855 loco days for 09 locos.

Due to transfer of locos from ELS/AQ to ELS/KYN vide HQ & RB letters under Ref. 3, 4 & 6 holding of ELS/KYN for AAL SIV is increased from 09 Nos. to 25 Nos. Further, 09 locos transferred from ELS/KYN to ELS/BSL vide HQ letter under Ref.6. Hence the total number of loco days will be executing till 12th quarter are 17,232 Nos.

Also processing of new tender will take approximately 2-3 months in finalization. Hence you are requested to extend the contract by 31.07.2025 by operating variation for 16 locos of ELS/KYN.

The details of loco days required for quantity variation are as under:

|  |  |  |
| --- | --- | --- |
| Sr. No. | Period | Total required loco days. |
| 1. | 22.04.2022 to 21.04.2025 | 17232 |
| 2. | 22.04.2025 to 31.07.2025 | 1616 |
|  | Total No. of days required for ELS/KYN | 18,848 |

**(ASHISH GUPTA)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

The schedule quantity of ELS/KYN is 9855 loco days for 09 locos. During 4th quarter (22.01.2023 to 21.04.2023) 02 loco was transferred from ELS/AQ to ELS/BSL vide HQ letter No.L.253.AC.118.Vol-VI dated 24.01.2023. During 5th quarter (22.04.2023 to 21.07.2023) 08 locos are transferred from ELS AQ to ELS KYN vide HQ Letter No.L.253.AC.118.Vol-VI dated 20.06.2023. Again, during 7th quarter (22.10.2023 to 21.01.2024) 06 locos transferred from ELS/AQ to ELS/KYN vide RB letter no.2023/Elect(TRS)/440/3 dated 16.11.2023. During 9th quarter under Ref.2 a Joint note and penalty statement upto 9th Qtr. i.e up to 21.07.2024 duly signed by concerned officer in-charge was sent to your office for passing payment against subject contract vide this office letter of even no. dated 23.11.2024.

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELS KYN/WKS/2023/10/FDCS-Medha Date: 25.03.2025

**Sr.DEE (TRS) BSL**

Sub:- Inclusion of Ver.3 Fault Diagnostic System (MPCS) into the work of “Comprehensive Annual Maintenance Contract (AMC) of M/s Medha Make (MPCS) (FDCS) at Electric Loco Shed, Bhusawal, Kalyan”

Ref: 1. Your office LOA No.BSL/TRS/Tender/2023/13/00987030096072 dtd 24.01.2024

2. This office letter of even no. dated 16.10.2023

3. This office letter of even no. dated 12.03.2024

--\*\*--

Vide your office LOA mentioned under ref.1, ELS/Kalyan’s 07 Nos. Medha make Ver.2 MPCS are covered under CAMC. Vide this office letter under Ref.3 ELS/KYN’s 10 locos of Medha make MPCS Ver.3 is under CAMC for 01 year.

However, this office proposal for Ver.3 is under process which will take more time. During this period three more locos are going out of warranty, hence you are requested to make the payment of 11 locos during 5th Qtr & 13 locos during 6th Qtr till the finalization of tender for ver.3. The number of loco days executed in last one year and required loco days for another 02 quarters are as under:

|  |  |  |  |
| --- | --- | --- | --- |
| Qtr. No. | CAMC Period | No. of Locos | No. Loco Days. |
| 1. | 15.03.2024 to 14.06.2024 i.e. 92 Days | 04 | 363 |
| 2. | 15.06.2024 to 14.09.2024 i.e. 92 Days | 04 | 368 |
| 3. | 15.09.2023 to 14.12.2024, i.e. 91 days | 06 | 468 |
| 4. | 15.12.2024 to 14.03.2025, i.e. 91 days | 09 | 648 |
| **Total No. of Loco day executed** | | | 1847 |
| 5. | 15.03.2025 to 14.06.2025, i.e. 92 days | 11 | 990 |
| 6. | 15.06.2025 to 14.09.2025, i.e. 92 days | 13 | 1119 |
| **Total No. of Loco day required additionally** | | | 2109 |

It is requested to include ELS/KYN’s additional 02 quarters quantity 2109 locos days of Ver.3 MPCS in the LOA issued by your office under ref.1.

**(ASHISH GUPTA)**

**DEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **SN** | **Loco No.** | **DOC** | **Warranty Period Upto** | **15.03.2025 to 14.06.2025 i.e 92 days** | **15.06.2025 to 14.09.2025 i.e 92 days** |
| 1 | 27118 | 03-05-16 | 02-05-21 | 92 | 92 |
| 2 | 27356 | 31-10-18 | 30-10-23 | 92 | 92 |
| 3 | 28557 | 23-01-19 | 22-01-24 | 92 | 92 |
| 4 | 27109 | 20-03-19 | 19-03-24 | 92 | 92 |
| 5 | 27260 | 26-09-19 | 25-09-24 | 92 | 92 |
| 6 | 27374 | 25-11-19 | 24-11-24 | 92 | 92 |
| 7 | 27367 | 31-Dec-19 | 30-12-24 | 92 | 92 |
| 8 | 27375 | 22-02-20 | 21-02-25 | 92 | 92 |
| 9 | 27112 | 02-03-20 | 01-03-25 | 92 | 92 |
| 10 | 27408 | MFG 02/15 | 01-02-22 | 92 | 92 |
| 11 | 27105 | 06-04-20 | 05-04-25 | 70 | 92 |
| 12 | 27126 | 09-07-20 | 08-07-25 |  | 68 |
| 13 | 27111 | 07-08-20 | 06-08-25 |  | 39 |
|  |  |  |  | **990** | **1119** |

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No.ELSKYN/WKS/2024/35/AAL SIV Date: 24.03.2025**

**Sr.DEE (TRS) BSL**

Sub:- Submission of sanctioned estimate for “Comprehensive Annual Maintenance contract of M/s AAL make 180 KVA SIV of Electric locomotives for the period of three years at Electric Loco Shed Kalyan, (16 Locos)”

Ref: ELS/AQ’s LOA No. ELS-AJNI-ELECTRICAL/ELS-AQ-DRG-WCQ-21-22-10/00015970051944 dated 30.03.2022

--\*\*--

A subject contract for a period of 3 years for ELS/BSL, ELS/AQ and ELS/KYN based locomotives was awarded to M/s AAL vide ELS/AQ’s LOA under ref. This contract is expiring on 21.04.2025.

A fresh proposal for 16 Nos. AAL SIV locos at total cost of Rs. of Rs.1,08,10,786 /- (Including 18% GST) through Single Tender from OEM M/s AAL, has been sanctioned by ADRM/BB vide e-office Note No.#17 dated 18.03.2025. Detailed estimate No.ELSKYN/WKS/2024/41/AAL SIV dated 27.12.2024 got sanctioned by Sr.DEE(TRS)KYN vide e-office Note No.#21 dated 19.03.2025.

HQ has nominated ELS/BSL for processing the AMC of AAL make SIV for further tenders, vide letter no.L.253 AC/AMC dated 27.12.2024 ( CP-11 ). Therefore you are requested to include ELS/KYN’s quantity in your tender. The details of locos to be covered are as under:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Loco No.** | **SIV Sr. No.** | **Sr. No.** | **Loco No.** | **SIV Sr. No.** |
| 1. | 27108 | OB180 - 1102063 | 9. | 27356 | OB180 - 1102054 |
| 2. | 27205 | OB180 - 0905013 | 10. | 27399 | OB180 - 1102063 |
| 3. | 27240 | OB180 - 0905010 | 11. | 27410 | OB180 - 1102060 |
| 4. | 27258 | OB180 - 1102045 | 12. | 27431 | OB180 - 0609019 |
| 5. | 27259 | OB180 – 0701041 | 13. | 27485 | OB180 - 1102043 |
| 6. | 27284 | OB180 - 1102046 | 14. | 28558 | OB180 - 1212 033 |
| 7. | 27290 | OB180 - 1102059 | 15. | 28559 | OB180 - 1212 032 |
| 8. | 27316 | OB180 - 0701042 | 16. | 28560 | OB180 - 1206 019 |

Following documents are attached herewith for further action:

1. Sr.DFM/CSMT’s letter No.BB/AC/FX-III/10108058 dated 28-02-2025, e office Note # 11 dated 28.02.2025

2. ADRM/BB’s sanction for AMC on single tender basis with OEM M/s AAL vide this office note of even no. dated 30.12.2024. (E-office Note # 17 dtd.17.03.2025)

3. Sanctioned Detailed Estimate No.ELSKYN/WKS/2024/41/AAL SIV dated 27.12.2024 vide office e-office Note #21 dated 19.03.2025.

4. Technical Specification

You are requested to include above 16 Nos. SIVs of ELS/ Kalyan in new AMC in your tender.

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2024/20/BHEL Propulsion Date: 27.02.2025**

**CEE (Loco)**

**PLW**

**Patiala**

Sub:- CAMC of BHEL make Propulsion locos fitted in WAP7 locomotives of ELS/KYN

for a period of 3 years through OEM M/s BHEL.

Ref:- 1. This office LOA No.ELSKYN/WKS/2024/20/BHEL Propulsion dtd 18.10.2024.

2. Your office PO No. 20/18/6019/1/771076 dtd 19.05.2018,

3. Your office PO No. 20/20/6014/1/771835 dtd. 22.12.2018

--\*\*--

In reference to your office POs mentioned above, this office has issued a LOA for the CAMC work at predefined rates of the respective POs. This office has calculated the CAMC starting date based on the commissioning done at various sheds and issued LOA for CAMC work accordingly.

Now, there is disagreement with the commissioning date of the following three locos by the firm. In this regard, this office is requesting you to kindly provide the commissioning date of the locos covered under POs mentioned above.

|  |  |  |  |
| --- | --- | --- | --- |
| **Sr. No.** | **Loco No.** | **PO No.** | **PO date** |
| 1 | 39046 | 20/18/6019/1/771076 | 19.05.2018 |
| 2 | 39070 | 20/18/6019/1/771076 | 19.05.2018 |
| 3 | 39076 | 20/20/6014/1/771835 | 22.12.2018 |

Kindly provide the date of commissioning of the above locos at the earliest so that CAMC work can be initiated accordingly.

**(NIRAJ KUMAR GARG)**

**Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  **वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय**  **विद्युत लोको शेड, कल्याण – ४२१ ३०१-**  **फोन / फैक्स:- 0251- 2361293 & 2363563** | **New Bitmap Image.bmp** | **Central Railway**  **Office of Sr. DEE (TRS),**  **Electric Loco Shed, Kalyan - 421 301.**  **Email :- 1.** [srdeetrskyncrly@bb.railnet.gov.in](mailto:srdeetrskyncrly@bb.railnet.gov.in)  2. srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/2020/16/Tap Changer Date: 27.02.2025

**CWM/ELW/BSL**

Sub:- Rehabilitation of Tap changer from ELS/Kalyan( balance qty of ELS/AQ).

Ref: 1.This office's LOA No. ELS-KYN-ELECTRICAL/ ELSKYN-WKS-2020-16-TC- A/00967350038710 dated 21.07.2021. and LOA Amendment No. ELSKYN/WKS/2020/16/TC-A dated 27.07.2021.

2. Your office letter No. ELW/BSL/Tender/Tap Changer dtd. 13.01.2024

3. Amendment to LOA dtd. 27.02.2025

--\*\*--

In reference to your office letter under Ref.2 you have requested to permit the rehabilitation work of 01 nos. of Tap changers in the exiting contract issued by this office. It is hereby informed that this office is in a position to permit 01 Nos. Tap changer from balance quantity of ELS/AQ. The same has been conveyed to firm vide amendment to LOA under reference dated 27.02.2025.

This office contract is for repair, rehabilitation & reconditioning of Tap changers having life more than 18 years. Kindly ensure the same before handing it over to firm for repair- rehab.

This is for your information.

(Niraj Kumar Garg)

Sr. DEE/TRS/KYN

Electric Loco Shed/KYN/CR

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2024/20/BHEL Propulsion Date: 26.02.2025**

**CEE (Inspection)**

**BLW**

**Varanasi**

Sub:- CAMC of BHEL make Propulsion locos fitted in WAP7 locomotives of ELS/KYN

for a period of 3 years through OEM M/s BHEL.

Ref:- 1. This office LOA No.ELSKYN/WKS/2024/20/BHEL Propulsion dtd 18.10.2024.

2. Your office PO No. 61713161/18138910 dtd 06.04.2018,

3. Your office PO No. 061813030/19152447 dtd. 04.01.2019

--\*\*--

In reference to your office POs mentioned above, this office has issued a LOA for the CAMC work at predefined rates of the respective POs. This office has calculated the CAMC starting date based on the commissioning done at various sheds and issued LOA for CAMC work accordingly.

Now, there is disagreement with the commissioning date of following six locos by the firm. In this regard, this office is requesting you to kindly provide the commissioning date of the locos covered under POs mentioned above.

|  |  |  |  |
| --- | --- | --- | --- |
| **Sr. No.** | **Loco No.** | **PO No.** | **PO date** |
| 1 | 37055 | 061713161.18138910 | 06.04.2018 |
| 2 | 37078 | 061713161/18138910 | 06.04.2018 |
| 3 | 37079 | 061713161.18138910 | 06.04.2018 |
| 4 | 37262 | 061813030.19152447 | 04.01.2019 |
| 5 | 37333 | 061813030/19152447 | 04.01.2019 |
| 6 | 37335 | 061813030/19152447 | 04.01.2019 |

Kindly provide the date of commissioning of the above locos at the earliest so that CAMC work can be initiated accordingly.

**(NIRAJ KUMAR GARG)**

**Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 24.02.2025**

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no. ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to your office letter under Ref.2 a Joint note and penalty statement upto 9th Qtr. i.e up to 21.07.2024 duly signed by concerned officer in-charge was sent to your office for passing payment against subject contract vide this office letter of even no. dated 23.11.2024.

Now CAMC work of AAL make SIV for 10th & 11th Qtr i.e from 22.07.2024 to 21.01.2025 has been carried out by firm as per LOA and scope of work satisfactorily.

Joint notes and penalty statements for these quarters (10th & 11th Qtr) duly signed by DEE/TRS/Kalyan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills

**(ASHISH GUPTA)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | A red and white logo  Description automatically generated | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No. ELS KYN/WKS/2023/12/Siemens HLC Date: 27.01.2025**

**Sr.DEE (TRS) AQ**

Sub:- CAMC of SIEMENS make IGBT based 2X500 KVA Hotel Load Converters fitted in WAP7 locomotives of ELS/KYN for a period of 3 years through OEM M/s SIEMENS.

Ref:- 1. This office LOA No.ELS KYN/WKS/2023/12/Siemens HLC ELS/AQ/ DRG/ WCQ-24-25/01 dated 15.01.2024

2. HQ’s Letter No.L.253.AC.118.Vol.VII dated 13.06.2024

3. Your office letter No.ELS/AQ/DRG/WCQ-24-25/Siemense HLS dated 18.12.2024

--\*\*--

As requested by your office vide letter under Ref.3, it is hereby conveyed that the payment for Loco No.37270 & 37267 will be passed by this office till finalization of your tender for these locos.

**(ASHISH GUPTA)**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  **वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय**  **विद्युत लोको शेड, कल्याण – ४२१ ३०१-**  **फोन / फैक्स:- 0251- 2361293 & 2363563** | **New Bitmap Image.bmp** | **Central Railway**  **Office of Sr. DEE (TRS),**  **Electric Loco Shed, Kalyan - 421 301.**  **Email :- 1.** [srdeetrskyncrly@bb.railnet.gov.in](mailto:srdeetrskyncrly@bb.railnet.gov.in)  2. srdeetrskyncrly@gmail.com |

**No**. **ELSKYN/WKS/2020/16/Tap Changer** Date: 24.01.2025

**CWM/ELW/BSL**

Sub:- Rehabilitation of Tap changer from ELS/Kalyan( balance qty of ELS/AQ).

Ref: 1.This office's LOA No. ELS-KYN-ELECTRICAL/ ELSKYN-WKS-2020-16-TC- A/00967350038710 dated 21.07.2021. and LOA Amendment No. ELSKYN/WKS/2020/16/TC-A dated 27.07.2021.

2. Your office letter No. ELW/BSL/Tender/Tap Changer dtd. 13.01.2024

3. Amendment to LOA dtd. 24.01.2025

--\*\*--

In reference to your office letter under Ref.2 you have requested to permit the rehabilitation work of 02 nos. of Tap changers in the exiting contract issued by this office. It is hereby informed that this office is in a position to permit 02 Nos. Tap changer from balance quantity of ELS/AQ. The same has been conveyed to firm vide amendment to LOA under reference dated 24.01.2025.

This office contract is for repair, rehabilitation & reconditioning of Tap changers having life more than 18 years. Kindly ensure the same before handing it over to firm for repair- rehab.

This is for your information.

(Niraj Kumar Garg)

Sr. DEE/TRS/KYN

Electric Loco Shed/KYN/CR

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com)  :- [srdeetrskyncrly@bb.railnet.gov.in](mailto:srdeetrskyncrly@bb.railnet.gov.in) |

No. ELSKYN/WKS/2024/15 Hiring SUV Date: 21.01.2025

**Director,**

GeM.

**Sub: -**Rectification in technical evaluation of GEM/2024/B/5576330 dated 07.11.2024

**Ref: -** 1. GEM/2024/B/5576330 dated 07.11.2024

--\*\*--

With reference GeM Bid under ref, this office has erroneously qualified L9 M/s. Rangiramani Infrastructure Private Limited and later confirmed and notified the bidder. Due to which we are unable to change the status of L-9 and further technical evaluate offers i.e **L-10 to L-12**.

As discussed, we have mailed to rest of the participants i.e **L-9 to L-12** the decision of Tender committee on 14.01.2025 and advised them to submit technical representation, if any before 16.01.2025 16.00 hrs. (48 hrs. as per GeM)

Post-closing of window for representation, the decision of Tender committee accepted by competent authority on 17.01.2025 is stated below:-

|  |  |  |  |
| --- | --- | --- | --- |
| SN | Firm name | Decision | Remarks |
| 1 | L-9 M/s Rangiramani Infra Pvt. Ltd | Qualified | Clarification for already submitted document i.e Annexure D has been furnished by the firm.  In view of above offer of M/s. Rangiramani Infra Private Limited is qualified.  Hence, status of decision to be maintained as “**Qualified”** |
| 2 | L-10 M/s. Padmavati Tours And Travels | Disqualified | Firm failed to submit documents as per checklist enclosed with bid. Further during representation the Firm accepted the TC decision.  Hence, status of decision to be made as “**Disqualified”** |
| 3 | L-11 M/s. Rohideshwar Goods Transport Services Private Limited | Disqualified | Firm failed to submit documents as per checklist enclosed with bid. Further No representation received  Hence, status of decision to be made as “**Disqualified”** |
| 4 | L-12 M/s. Swapnarekha Tours & Travels | Disqualified | Firm failed to submit documents as per checklist enclosed with bid. Further No representation received  Hence, status of decision to be made as “**Disqualified”** |

It is requested to make changes in the technical evaluation status as per decision of tender committee for the bidders L-9 to L-12 as mentioned above.

Please do the needful.

**(ASHISH GUPTA)**

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

**DA:** Letter to Firms for representation, if any

Representation received from firms on official mail.

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com)  :- [srdeetrskyncrly@bb.railnet.gov.in](mailto:srdeetrskyncrly@bb.railnet.gov.in) |

No: ELSKYN/WKS/2023/10/FDCS-Medha Date: 08.01.2025

**Sr.DEE (TRS) BSL**

Sub:- Annual Maintenance Contract of M/s Medha Make Microprocessor Based Control & Fault Diagnostic System (MPCS) Ver 2 of AC Conventional Locomotives as per RDSO’s SMI No. RDSO/2016/EL/SMI/0288 (Rev) for a period of 3 years at Electric Loco Shed, Kalyan, Qty- 07 Nos.

Ref:- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER- 2023-13 / 00987030096072 dated 24.01.2024

2. Your office letter no. BSL/TRS/Tender/2023/13 dated 15.03.2024

--\*\*--

With reference to your office letter at Ref.1 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 15.03.2024. Vide Joint Note No.ELS/KYN/I&E/Medha/MPCS dated 14.03.2024 & 15.03.2024

AMC work of Medha make FDCS (V-2 & V-3) for 2nd qtr. i.e. from 15.06.2024 to 14.09.2024 has been carried out by firm as per LOA and scope of work satisfactorily. Joint Note, Down time calculation & penalty calculation statement of 2nd quarter duly signed by DEE (TRS) KYN are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills

.

(ASHISH GUPTA)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELSKYN/WKS/2020/16/Tap Changer Date: 01.01.2025

**Sr.DEE (TRS) BSL**

Sub: - Repair, Rehabilitation, Reconditioning, Testing and Supply of Tap Changer of Electric Locomotives based at Electric Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.

Ref: 1. This office is LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-

TC-A/ 00967350038710 dated 21-07-2021

2. ELS/Ajni letter no. HQ-KYN-146 dtd 02.09.2024

3. ELW/BSL letter no. ELW/BSL/Tender/Tap Changer dated 19.12.2024

--\*\*--

The contract for the subject work was awarded to M/s River Engineering Pvt. Ltd, 54-55, Toy City, Ecotech-III, Greater Noida, Noida – 201206, vide LOA under reference. This contract is for 70 Nos. tap changers for three different sheds i.e. ELS/Ajni, ELS/Bhusawal and ELS/Kalyan with completion period up to three years extended upto 20.07.2025.

ELS/AQ vide letter under reference 2, has informed that as all WAG-7 locos have been transferred henceforth they have no requirement of their balance quantity, which is 05 nos.

ELW/BSL vide letter under reference 3, requested to permit the rehabilitation of tap changers, Qty- 02 nos. under this office LOA. You are requested to convey to this office whether you have additional requirement of quantity over your existing balance qty. If not the balance Qty of ELS/AQ will be utilized by ELW/BSL as per their requirement.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2020/21/ MEDHA/AMC-SIV Date: 11.12.2024

**Sr.DEE (TRS) BSL**

Sub:- Contract Agreement No. ELSKYN/WKS/2020/21/MEDHA/AMC-SIV dated 05.08.2021 for the work of “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) for a period of three years as per RDSO’s SMI No.RDSO/2016/EL/SMI/0291 (Rev.0) at Electric Loco Shed Kalyan, Bhusawal and Ajni, Qty- 70 Nos.”

Ref:- 1. LOA No. ELS-KYN-ELECTRICAL/ ELSKYN-WKS-2020-21-AMC-

SIV/00987030036441 dated 04.06.2021

--\*\*--

A contract for the subject work covering quantity of 34 Nos. SIV (ELS/ KYN- 08 Locos, ELS/Bhusawal- 17 locos & ELS/AQ- 09 Locos) was awarded by this office vide LOA no. mentioned under reference. This contract finally expired on 07.10.2024 with variation for ELS/ KYN & ELS/BSL.

Now the subject contract has been completed and a fresh contract has also been awarded, as the above contract was awarded by this shed, final payment is to be released by this office.

It is therefore requested to kindly confirm whether final payment of your quantity has been passed from your end and give the figures of final payment amount released & security deposit deducted from the bills against subject mentioned contract.

(**ASHISH GUPTA**)

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed,  Kalyan – 421 301.  Email:srdeetrskyncrly@gmail.com |

No: ELS KYN/WKS/2022/10/Electrifi-A Date: 09.12.2024

**DFM-I/BB**

Sub:- Introduction of NS item and variation in the existing work of “Electrification work for newly shifted Auxiliary Section and Body Section at Electric Loco Shed, Kalyan.”

Ref :- LOA no. ELS-KYN-ELECTRICAL / ELSKYNWKS22-10Electrifi-A

/01374300076008 dated 28.04.2023

---\*\*---

With reference to above-mentioned LOA, it is proposed for variation in some quantity and addition of NS items. Accordingly, variation statement has been prepared and forward for vetting to account office.

It is further stated that as in the reference LOA against which the subject variation is proposed there was only participant. Hence, there is **no vitiation.**

(**Bhupesh Yadav)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 09.12.2024**

**Sr.DEE (TRS) AQ**

Sub:- Inclusion of ABB make propulsion locomotives in ELS/KYN AMC

Ref:- Your office letter no. ELS/AQ/DRG/WCQ-24-25/01 dated 03.12.2024

--\*\*--

With reference to your office letter, it is conveyed that this office is initiating an AMC for ABB make propulsion system. Processing of proposal will take considerable time.

Therefore, as discussed you are requested to make payments for a further 02 Qtrs. by the time this office will award AMC. Necessary debit will be accepted against the passing of bills.

**(Niraj Kumar Garg)**

**Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/Tap Changer Date. 07.12.2024

**Sr.DEE(TRS) AQ**

Sub: Warranty obligation against work of “Repair, Reconditioning, Rehabilitation, Testing and Supply of Tap Changers”.

Ref: 1. Your office LOA No.ELS/AQ/DRG/WCQ/19-20/01/00967350004367 dated

02.08.2019.

2. Your office letter No.ELS/AQ/DRG/WCQ/19-20/01 dated 11-11-2024

--\*\*\*--

With reference to your letter under Ref – 2, it is hereby conveyed that there is no warranty obligation pending with firm against subject work. The details of the date of commissioning with loco no. is given below.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr. No. | Tap Changer Sr. No. | New Sr. No. | Date of commissioning | Loco No. |
| 1 | 40A991450 | TCR2108241-01 | 18.12.2021 | 21938 |
| 2 | 41A95814 | TCR2108241-02 | 18.11.2021 | 21871 |
| 3 | 40D981425 | TCR2108241-03 | 27.10.2021 | 27367 |

This is for your information and necessary action.

(**Ashish Gupta**)

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2022/IPAS Date. 28.11.2024

**AEDPM (T)**

**CSMT**

Sub: Creation of IPAS user ID

--\*\*\*--

Kindly create IPAS user for following Supervisoir of ELS Kalyan, the details are as under:

|  |  |  |
| --- | --- | --- |
| Sr. No. | Particulars | Details |
| 1 | Name | Mohan Goyal |
| 2 | Designation | SSE/M&P |
| 3 | Mobile No. | 7021519393 |
| 4 | Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| 5 | PF No. | 00211030859 |

(**Ashish Gupta**)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 23.11.2024**

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no. ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to your office letter under Ref.2 a Joint note and penalty statement upto 7th Qtr. i.e 22.07.2024 to 21.01.2024 duly signed by concerned officer in-charge was sent to your office for passing payment against subject contract vide this office letter of even no. dated 05.04.2024.

Now CAMC work of AAL make SIV for 8th & 9th Qtr i.e from 22.01.2024 to 21.07.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

Joint notes and penalty statements of these quarters (8th & 9th Qtr) duly signed by DEE/TRS/Kalyan are sent herewith for further necessary action at your end.

The total no. of loco days already executed at ELS/Kalyan upto Qtr 10 are 14,288 loco days. Number of loco days for Qtr 11 & Qtr 12 are 2912, thus total loco days required for ELS/Kalyan is **17,200 Nos.** up to end of quarter 12 i.e upto 21.04.2025.

**(Bhupesh Yadav)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No. ELSKYN/WKS/20/17/AMC SIV Siemens Date: 17.10.2024**

**Sr.DEE (TRS) BSL**

Sub:- Extension of work against, LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021 for “Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan”

Ref: 1. Your office LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS –

TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

2. This office letter of even no. dated 23.08.2024

2. This office letter of even no. dated 24.08.2024.

--\*\*--

The contract for the subject work was awarded to M/s Siemens Ltd. Navi Mumbai, vide LOA under reference with a completion period of three years i.e. up to 07.06.2024.

Vide this office letter of even no dated 24.08.2024, this office has sent joint note and penalty statement upto 11 Qtrs. i.e upto 07.03.2024. Now, Joint note and Penalty statement of 12th Qtr from the period 08.03.2024 to 07.06.2024 duly signed by DEE/TRS/Kalyan is sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

As desired, it is informed that a total of **22,463 Nos. loco days** are required by ELS/KYN upto 31.12.2024.

In view of the above, it is requested to increase the ELS/KYNs quantity of the existing contract for 18 locos of ELS/Kalyan so that the healthiness of SIV can be ensured without interruption.

**(ASHISH GUPTA)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/2019/16/HIRECT SIV Date: 15.10.2024

**Sr.DEE (TRS) BSL**

Sub:- CA No.CR/BSL /Elect. /2021/0011 dated 20-07-2021 for “Renewal of Annual Maintenance Contract (AMC) of HIRECT make SIV for the period of three years at Electric Loco Shed, Bhusawal / Kalyan.”

Ref: (i) Your office LOA No. BHUSAWAL DIVISION- ELECTRICAL/ BSL-TRS-TENDER-2021-01/ 01029820032724 dtd. 27-02-2021

(ii) Your office letter no. BHUSA/TRS/TENDER/2021/01 dated 11.10.2024

--\*\*--

In reference to your letter under Ref.2, as desired, it is hereby informed that the 3894 Nos. of loco days has been executed (Joint Note prepared) and 3288 loco days bill has been passed till date at ELS/Kalyan against above contract.

**(ASHISH GUPTA)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2024/IPAS Date. 10.10.2024

**AEDPM (T)**

**CSMT**

Sub: Replacing of user details of created IPAS ID.

--\*\*\*--

DEE (TRS) KALYAN, Shri Nitish Kumar Shukla has been transferred from ELS/Kalyan. It is requested to replace old user with the new user details as given below.

|  |  |  |
| --- | --- | --- |
|  | (Old user) | (New user details) |
|  |  |  |
| Particulars | CR02EXE1051 | -- |
| Name | Shri Nitish Kumar Shukla | ASHISH GUPTA |
| Designation | DEE (TRS)KALYAN | DEE(TRS)KALYAN |
| Mobile No. | 8828119321 |  |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| PF No. | 00729800412 | 00729800383 |

You are requested to replace user of existing officers ID’s at the earliest.

(ASHISH GUPTA)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| Gazetted officer’s Name | Already Created ID on AIMS.(Old user)/ designation | To be Replaced (New user details) |
| Shri Nitish Kumar Shukla | CR02EXE1051 (ADEE-1/TRS/KYN | Shri Ashish Gupta  Designation:- DEE-II(TRS)KALYAN  Mobile No. 8828119362  Office Address: Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301  PF No. 00729800383 |
|  | |
|
|
|
|

Kindly change user details of IPAS user for following officer at ELS Kalyan,

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2022/IPAS Date. 22.11.2023

**AEDPM (T)**

**CSMT**

Sub: Creation of IPAS user ID

--\*\*\*--

Kindly create IPAS user for following officers of ELS Kalyan, the details are as under:

|  |  |  |  |
| --- | --- | --- | --- |
| Sr. No. | Particulars | DEE-I | DEE-II |
| 1 | Name | SHIKHAR SRIVASTAVA | ASHISH GUPTA |
| 2 | Designation | DEE-I(TRS)KALYAN | DEE-II(TRS)KALYAN |
| 3 | Mobile No. | 8828119321 | 8828119362 |
| 4 | Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| 5 | PF No. | 00729800412 | 00729800383 |

(BHUPESH YADAV)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**No. ELSKYN/WKS/2024/IR\_WCMS User Date. 05.09.2024**

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing IR-WCMS user details and Mapping with HRMS

--\*\*\*--

Currently ADEE-2 (TRS) Kalyan of ELS KYN Shri. Bhupesh Yadav is promoted to the posted of DEE-1 (TRS) KYN. Therefore, it is requested to replace old IR-WCMS user with the new user details as given below.

|  |  |  |
| --- | --- | --- |
| **Particulars** | **Old user details** | **New user details** |
| Name (in full) | BHUPESH YADAV | BHUPESH YADAV |
| Designation | ADEE (TRS) KALYAN | DEE-1 (TRS) KALYAN |
| IR-WCMS Id | adeeelskyn2 | deeelskyn |
| IR-WCMS Password | Adeeelskyn2@123 | Deeelskyn@1234 |
| HRMS Id | WZMGUW | WZMGUW |
| HRMS Password | Bhupesh@71 | Bhupesh@71 |
| IREPS user ID | adee2trs.elskyn@gmail.com | deetrs.elskyn@gmail.com |

You are requested to replace the details with new one and map the ID with HRMS.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELSKYN/WKS/2024/WFL-CAMC Date: 30.09.2024

**Sr.DEE (TRS),**

EMU Carshed, Sanpanda

**Sub:** CAMC of WFL System fitted in Locomotives of ELS Kalyan

**Ref:** Your office LOA No. EMULS-SNPD-ELECTRICAL / SNPD-RS-WKS-23-

05 / 01449630090982 dtd 11.11.2023

--\*\*--

ELS/KYN has 62 nos. WFL system installed in 31 locos. The warranty of these WFL system has been expired and there is no AMC contract for maintaining the same.

The contract for the subject work is running in your shed vide LOA under reference, therefore, it is proposed to add 62 Nos WFL system installed in 31 locos of ELS/KYN in your existing contract. The detailed scope of work along with list of spares part and consumable required is enclosed along with this letter.

Necessary debit will be accepted after completion of work.

Kindly confirm about the acceptance of above.

**(Niraj Kumar Garg)**

**Sr. DEE (TRS) Kalyan**

DA: - Encl. as above

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2016/25/AMC-SIV Date: 14.09.2024

**Sr.DEE (TRS) BSL &**

**Sr.DEE (TRS) AQ**

Sub: Refund of Security deposit deducted against C.A. No. ELSKYN.WKS.2016.25.AMC-SIV dated 05-10-2018 for “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) fitted in conventional locomotives as per RDSO's SMI No.RDSO/2016/EL/SMI/0291 (Rev 0) for a period of 3 years at Electric Loco Shed, Kalyan, Ajni and Bhusaval”

Ref : (i) LOA no. ELSKYN/WKS/2016/25/ AMC-SIV dated 21.03.2018

--\*\*--

The subject contract was awarded to M/s Medha Servo Drives Pvt. Ltd., P-4/5 B, Industrial Park, Nacharam, Hydrabad-500 076 at a total cost of Rs.1,32,75,000 /- with completion period up to 20.03.2021 and extended up to 09.06.2021.

The firm vide their letters Ref SIV:AMC:CR:KYN:SSC:L21032018:1134.24 dated 30.07.2024 has requested to release SD, EMD & PBG.

The subject work has been completed by the firm and the final bill passed by this shed. Sr.DEE(TRS) Kalyan vide this office note no. ELSKYN/WKS/2016/25/AMC-SIV dated 10.08.2024 has accorded approval for refund of SD, EMD & PBG.

Therefore, it is advised to return the security deposit deducted from your bills against the subject contract to the firm.

**(Shri Ashish Gupta)**

**DEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**No. ELSKYN/WKS/2024/IR\_WCMS User Date. 05.09.2024**

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing IR-WCMS user details and Mapping with HRMS

--\*\*\*--

Currently ADEE-2 (TRS) Kalyan of ELS KYN Shri. Bhupesh Yadav is promoted to the posted of DEE-1 (TRS) KYN. Therefore, it is requested to replace old IR-WCMS user with the new user details as given below.

|  |  |  |
| --- | --- | --- |
| **Particulars** | **Old user details** | **New user details** |
| Name (in full) | BHUPESH YADAV | BHUPESH YADAV |
| Designation | ADEE (TRS) KALYAN | DEE-1 (TRS) KALYAN |
| IR-WCMS Id | adeeelskyn2 | deeelskyn |
| IR-WCMS Password | Adeeelskyn2@123 | Deeelskyn@1234 |
| HRMS Id | WZMGUW | WZMGUW |
| HRMS Password | Bhupesh@71 | Bhupesh@71 |
| IREPS user ID | adee2trs.elskyn@gmail.com | deetrs.elskyn@gmail.com |

You are requested to replace the details with new one and map the ID with HRMS.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.coxm](mailto:srdeetrskyncrly@gmail.coxm) |

No: ELSKYN/WKS/2024/06/Medha SIV Date: 02.09.2024

**Sr.DEE (TRS) BSL**

Sub: - Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter

(SIV) for a period of two years at Electric loco shed, Kalyan & Bhusawal.

Ref: - Deviation Statement against Tender No.ELSKYNWKS-24-06-Medha-SIV Due

on 24.08.2024

--\*\*--

With reference to tender floated against the subject work, the firm M/s Medha Servo Drives Pvt. Ltd. has offered following deviation against tender condition. The same is stated below:

|  |  |  |  |
| --- | --- | --- | --- |
| **SN** | **Railway’s Conditions** | **Firm Deviation** | **Firm comment** |
| 1 | **Chapter-II**  2.13- Conditions of contracts 2.15 warranty  **(i.)Warranty against the manufacturing defects of the spares supplied and replaced shall be for a periods of One Year (12 Months) from the date of fitment.** | Warranty against the manufacturing defects of the spares supplied and replaced shall be for a periods of 06 Months from the date of fitment. | Warranty clause is not applicable for AMC and is not as per RDSO SMI No. RDSO/2016/EL/SMI/0291 (REV. '0') Dated 21.06.2016. However, firm requests to consider 6 months ( from the date of fitment) towards warranty instead of 12 months |
| 2 | TECHNICAL SPECIFICATION &  SCOPE OF WORK Scope of  Work: 3.11 Schedule A-11  **Checking of functioning of churning fan by pressing the push button switch provided at**  **power panel side.** | Checking of functioning of churning fan, provided  as per OEM design, by pressing the push button  switch provided at power panel side. | As per OEM design, Churning fan is not provided in M/s Medha make static converter |
| 3 | TECHNICAL SPECIFICATION &  SCOPE OF WORK A.  Technical Specification for CAMC of  180KVA Medha make SIV 3.11  Schedule A-12  **ALL OFC coupler connections to be checked** | All OFC coupler, provided as per OEM design, connections to be checked. | As per OEM design, OFC couplers are not provided in M/s Medha make static converter. |
| 4 | TECHNICAL SPECIFICATION &  SCOPE OF WORK B. Technical  Specification for CAMC of 2 X  130KVA Medha make SIV 1.8  Schedule Maintenance SL. No. 24  **Blower fan overhauling (new blower will be provide after 2 times overhauling)** | Blower fan, during overhauling schedules, shall be replaced if the performance is not as per requirement. | Blower fan shall be replaced if the performance is not as per requirement i.e. on condition basis not periodically. |

You are requested to offer your comment against deviation submitted by firm

(Shri. Niraj Kumar Garg)

Sr. DEE (TRS) Kalyan

DA: Deviation statement

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2024/IR\_WCMS User Date. 24.08.2024

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing IR-WCMS user details and Mapping with HRMS

--\*\*\*--

Currently ADEE-2 (TRS) Kalyan post is vacant. However, as some contract agreement which were initially forwarded by ADEE- 2 (TRS) Kalyan is currently pending with the same post i.e ADEE-2 (TRS) Kalyan. This Contract Agreements need to be send to Contractor for signing and finalization. Therefore, it is requested to replace old IR-WCMS user with the new user details as given below.

|  |  |  |
| --- | --- | --- |
| **Particulars** | **Old user details** | **New user details** |
| Name (in full) | BHUPESH YADAV | BHUPESH YADAV |
| Designation | ADEE (TRS) Kalyan | ADEE (TRS) KALYAN |
| IR-WCMS Id | adeeelskyn1 | adeeelskyn2 |
| IR-WCMS Password | Adeeelskyn1@1 | Adeeelskyn2@123 |
| HRMS Id | -- | WZMGUW |
| HRMS Password | -- | Bhupesh@71 |
| IREPS user ID | adee1trs.elskyn@gmail.com | adee2trs.elskyn@gmail.com |

You are requested to replace the details with new one and map the ID with HRMS.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.coxm](mailto:srdeetrskyncrly@gmail.coxm)  : srdeetrskyncrly |

No: ELSKYN/WKS/2023/10/FDCS-Medha Date: 24.08.2024

**Sr.DEE (TRS) BSL**

Sub:- Annual Maintenance Contract of M/s Medha Make Microprocessor Based Control & Fault Diagnostic System (MPCS) Ver 2 of AC Conventional Locomotives as per RDSO’s SMI No. RDSO/2016/EL/SMI/0288 (Rev) for a period of 3 years at Electric Loco Shed, Kalyan, Qty- 07 Nos.

Ref:- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER- 2023-13 / 00987030096072 dated 24.01.2024

2. Your office letter no. BSL/TRS/Tender/2023/13 dated 15.03.2024

--\*\*--

With reference to your office letter at Ref.1 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 15.03.2024. Vide Joint Note No.ELS/KYN/I&E/Medha/MPCS dated 14.03.2024&115.03.2024

AMC work of Medha make FDCS (V-2 & V-3) for 1st qtr. i.e. from 15.03.2024 to 14.06.2024 has been carried out by firm as per LOA and scope of work satisfactorily. Joint Note, Down time calculation & penalty calculation statement of 1st quarter duly signed by ADEE (TRS) KYN are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills

.

(ASHISH GUPTA)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No. ELS KYN/WKS/2023/12/Siemens HLC Date: 24.08.2024**

**M/s SIEMENS LTD-NAVI MUMBAI.**

Kalwa Works, Thane Belapur Road

Navi Mumbai.- 400708

Maharashtra, India.

**Reminder-I**

Sub: - CAMC of SIEMENS make IGBT based 2X500 KVA Hotel Load Converters fitted

in WAP 7 Locomotives of ELS/KYN for a period of 3 years through OEM M/s

SIEMENS.

Ref: LOA no. ELS KYN/WKS/2023/12/Siemens HLC Date: 15.01.2024

The subject work of “ CAMC of SIEMENS make IGBT based 2X500 KVA Hotel Load Converters fitted in WAP7 Locomotives of ELS/KYN for a period of 3 years through OEM M/s SIEMENS” was awarded to you vide LOA under ref. at the total cost of Rs. 1,49,30,736.06 (all inclusive.

You were advised to sign contract agreement since last 02 months vide telephonic and WhatsApp communication but till date you have not turned up.

In view of above, you are again advised to sign the contract agreement at the earliest so that agreement can be finalized.

**(Shri. ASHISH GUPTA)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.coxm](mailto:srdeetrskyncrly@gmail.coxm)  : srdeetrskyncrly |

No: ELSKYN/WKS/2023/10/FDCS-Medha Date: 23.08.2024

**Sr.DEE (TRS) BSL**

Sub:- Annual Maintenance Contract of M/s Medha Make Microprocessor Based Control & Fault Diagnostic System (MPCS) Ver 2 of AC Conventional Locomotives as per RDSO’s SMI No.RDSO/2016/EL/SMI/0288 (Rev) for a period of 3 years at Electric Loco Shed, Kalyan, Qty- 07 Nos.

Ref:- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER- 2023-13 / 00987030096072 dated 24.01.2024

--\*\*--

With reference to your office letter at Ref.1 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 15.03.2024. Vide Joint Note No.ELS/KYN/I&E/Medha/MPCS dated 14.03.2024.

Payment for AMC work of Medha make FDCS for 11 Qtrs. i.e. from 09.09.2020 to 08.06.2023 has been already passed

Further, AMC work carried out by firm during the period 09.06.2023 to 12.03.2024 i.e. 3 Qtrs. is as under:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Qtr. No. | AMC Period | No. of Locos | Date of Joint Note | No. Loco Days. | Downtime in Hrs. |
| 1. | 09.06.2023 to 08.09.2023 i.e. 92 Days | 07 | 14.10.2023 | 644 | 00 Hrs. |
| 2. | 09.09.2023 to 08.12.2023 i.e. 91 Days | 07 | 02.01.2024 | 637 | 00 Hrs. |
| 3. | 09.12.2023 to 12.03.2024, i.e. 95 days | 07 | 14.03.2024 | 665 | 00 Hrs. |
|  |  | **Total No. of Loco days** | | **1,946** |  |

AMC work of Medha make FDCS for 3 Qtrs. i.e. from 09.06.2023 to 12.03.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

As stated in your office letter mentioned at Ref.3, Joint note and downtime calculation sheet of each quarter (3 Qtrs.) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

(ASHISH GUPTA)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**No. ELSKYN/WKS/2020/17/AMC SIV Siemens DATE:- 23.08.2024**

**Sr. DEE/TRS/BSL**

**Subject:** Annual Maintenance Contract of Siemens make SIV for the period of three

year at Electric Loco Shed, Bhusawal/Ajni/Kalyan

**Ref:** 1.LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

2. Your office letter no. BSL/TRS/Tender/2021/02 dated 11.07.2023

--\*\*--

The AMC of 14 Nos. Siemens make SIV at Electric Loco Shed, Kalyan for a period of 3 years has been started from 08.06.2021 vide Joint Note No.ELSKYN/PEX/JN/SIEMENS/SIV/CAMC/21-22/1 dated 08.06.2021. Further vide Joint No.ELSKYN/PEX/JN/SIEMENS/SIV/HO/AMC/22-23/1 dated 30.01.2021, 10 locos are handed over to firm for AMC (03 Nos. w.e.f 13.01.2023 , 01 No. w.e.f. 24.01.2023, 01 No. w.e.f. 20.06.2023 and 05 Nos. w.e.f. 17.11.2023 ).

As stated in your office letter mentioned at Ref.2, Joint note and Penalty statement of each quarter from the period 08.12.2023 to 07.03.2024 (i.e.11th Qtrs) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

|  |
| --- |
| (Shri. Ashish Gupta)  DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 23.08.2024**

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no. ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to above referred contract a Joint note and penalty statement upto 7th Qtr. i.e 22.04.2022 to 21.01.2024 duly signed by concerned officer in-charge was sent to your office for passing payment as stated in your office letter mentioned at Ref.2.

Now CAMC work of AAL make SIV for 8th Qtr i.e from 22.01.2024 to 21.04.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

The certificate for measurement of 8th Quarter of above-mentioned contract is as under: -

1. It is certified that, 20% work is check done by me.
2. It is certified that; this work is under process.

Joint notes and penalty statements of these quarters (8th Qtr) duly signed by DEE/TRS/Kalyan are sent herewith for further necessary action at your end.

**(Shri. Ashish Gupta)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No. ELSKYN/WKS/20/17/AMC SIV Siemens Date: 23.08.2024**

**Sr.DEE (TRS) BSL**

Sub:- Extension of work against, LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021 for “Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan”

Ref: Your office LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS –

TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

--\*\*--

The contract for the subject work was awarded to M/s Siemens Ltd. Navi Mumbai, vide LOA under reference with a completion period of three years i.e. up to 07.06.2024.

The new proposal for the subject work is currently under tender stage, opening due 16.09.2024. The same will take considerable amount of time for finalization. In addition, it is for your information that 01 Loco No. 27110, SIV Sr. No, STBDN1058 is running out of warranty since 07.08.2024.

In view of above, it is requested for extension of Quantity in the existing contract for 17 locos of ELS/Kalyan and an additional 01 locos, which is out of warranty since 07.08.2024 so that the healthiness of SIV can be ensured without interruption.

**(Shri. Ashish Gupta)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**ELSKYN/WKS/2020/17/AMC SIV Siemens DATE:- 23.08.2024**

**Sr. DEE/TRS/BSL**

**Subject:** Annual Maintenance Contract of Siemens make SIV for the period of three

year at Electric Loco Shed, Bhusawal/Ajni/Kalyan

**Ref:** 1.LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

2. Your office letter no. BSL/TRS/Tender/2021/02 dated 11.07.2023

--\*\*--

The AMC of 14 Nos. Siemens make SIV at Electric Loco Shed, Kalyan for a period of 3 years has been started from 08.06.2021 vide Joint Note No.ELSKYN/PEX/JN/SIEMENS/SIV/CAMC/21-22/1 dated 08.06.2021. Further vide Joint No.ELSKYN/PEX/JN/SIEMENS/SIV/HO/AMC/22-23/1 dated 30.01.2021, 04 locos are handed over to firm for AMC (03 Nos. w.e.f 13.01.2023 and 01 No. w.e.f 24.01.2023).

As stated in your office letter mentioned at Ref.2, Joint note and Penalty statement of each quarter from the period 08.06.2023 to 07.12.2023 (i.e 9th & 10th Qtrs) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

|  |
| --- |
| (SHIKHAR SRIVASTAVA) DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 23.08.2024**

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no.ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to above referred contract a Joint note and penalty statement upto 7th Qtr i.e. 22.04.2022 to 21.01.2024 duly signed by concerned officer in-charge was sent to your office for passing payment as stated in your office letter mentioned at Ref.2.

Now CAMC work of AAL make SIV for 8th Qtr i.e from 22.01.2024 to 21.04.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

The certificate for measurement of 8th Quarter of above-mentioned contract is as under: -

1. It is certified that, 20% record check done by me.
2. It is certified that; this work is under process.

Joint notes and penalty statements of these quarters (8th Qtr.) duly signed by DEE/TRS/Kalyan are sent herewith for further necessary action at your end.

**(Shri. Ashish Gupta)**

**DEE/TRS/KALYAN**

**For Sr. DEE/TRS/KALYAN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No. ELSKYN/WKS/20/17/AMC SIV Siemens Date: 23.08.2024**

**Sr.DEE (TRS) BSL**

Sub:- Extension of work against, LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021 for “Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan”

Ref: Your office LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS –

TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

--\*\*--

The contract for the subject work was awarded to M/s Siemens Ltd. Navi Mumbai, vide LOA under reference with a completion period of three years i.e. up to 07.06.2024.

The new proposal for the subject work is currently under tender stage, opening due 16.09.2024. The same will take considerable amount of time for finalization. In addition, it is for your information that 01 Loco No. 27110, SIV Sr. No, STBDN1058 is running out of warranty since 07.08.2024.

In view of above, it is requested for extension of Quantity in the existing contract for 17 locos of ELS/Kalyan and an additional 01 locos, which is out of warranty since 07.08.2024 so that the healthiness of SIV can be ensured without interruption.

**(Shri. Ashish Gupta)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.coxm](mailto:srdeetrskyncrly@gmail.coxm)  : srdeetrskyncrly |

No: ELSKYN/WKS/2023/10/FDCS-Medha Date: 23.08.2024

**Sr.DEE (TRS) BSL**

Sub:- Annual Maintenance contract (AMC) of M/s. Medha make MPCS (FDCS) at Electric loco shed, Bhusawal, Kalyan.

Ref:- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER- 2020-06 / 00987030024273 dated 20.08.2020

2. Your office letter no.BSL/TRS/Tender/2016/08 dated 15.06.2021.

3. Your office letter No.BSL/TRS/Tender/2020/06 dated 24.07.2023

4. Your office letter No. BSL/TRS/Tender/2020/06 /00987030024273 dtd 17.08.2023

5. Your office letter No. CR/BSL/Elect./2020/0025/CD-0002

6. Your office letter No. CR/BSL/Elect./2020/0025/CD-0003

--\*\*--

With reference to your office letter at Ref.2 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 09.09.2020. Vide Joint Note No.ELS/KYN/I&E/Medha/MPCS dated 16.06.2021 date of handover of 06 locos was revised and 06 locos are handed over to M/s Medha for subject mentioned work. Vide Joint No.ELS/KYN/I&E/MEDHA/FDCS/02/10 dated 29.10.2021 one more loco added in the subject AMC from dated 29.10.2021.

Payment for AMC work of Medha make FDCS for 11 Qtrs. i.e. from 09.09.2020 to 08.06.2023 has been already passed

Further, AMC work carried out by firm during the period 09.06.2023 to 12.03.2024 i.e. 3 Qtrs. is as under:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Qtr. No. | AMC Period | No. of Locos | Date of Joint Note | No. Loco Days. | Downtime in Hrs. |
| 1. | 09.06.2023 to 08.09.2023 i.e. 92 Days | 07 | 14.10.2023 | 644 | 00 Hrs. |
| 2. | 09.09.2023 to 08.12.2023 i.e. 91 Days | 07 | 02.01.2024 | 637 | 00 Hrs. |
| 3. | 09.12.2023 to 12.03.2024, i.e. 95 days | 07 | 14.03.2024 | 665 | 00 Hrs. |
|  |  | **Total No. of Loco days** | | **1,946** |  |

AMC work of Medha make FDCS for 3 Qtrs. i.e. from 09.06.2023 to 12.03.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

As stated in your office letter mentioned at Ref.3, Joint note and downtime calculation sheet of each quarter (3 Qtrs.) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

(ASHISH GUPTA)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

**No. ELSKYN/WKS/20/17/AMC SIV Siemens Date: 23.08.2024**

**Sr.DEE (TRS) BSL**

Sub:- Extension of work against, LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021 for “Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan”

Ref: Your office LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS –

TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

--\*\*--

The contract for the subject work was awarded to M/s Siemens Ltd. Navi Mumbai, vide LOA under reference with a completion period of three years i.e. up to 07.06.2024.

The new proposal for the subject work is currently under tendering stage. The same will take considerable amount of time for finalization. In addition, it is for your information that 01 loco is running out of warranty since 07.08.2024, therefore it is requested for extension of Quantity in the existing contract for 24 locos of ELS/Kalyan and additional 01 locos which is out of warranty since 07.08.2024 so that the healthiness of SIV can be ensured without interruption.

**(Shri. Ashish Gupta)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

**SUMMARY OF INSPECTION NOTE**

Contract Labour (R & A) Act,1970 & Central Rules,1971

|  |  |  |
| --- | --- | --- |
| **SN** | **Irregularities Noticed** | **Remarks** |
| **1** | **The notices showing the following were not displayed/amended [Breach of Rule 81(1)(i).]** |  |
| a | The Rates of Wages in English/Hindi/ local language |  |
| b | The Hours of Work in English/Hindi/ local language |  |
| c | The date of Payment in English/Hindi/ local language |  |
| d | The Wage period in English/Hindi/ local language |  |
| e | Date of payment of un-paid wages in English/Hindi/local language |  |
| **2** | **Notice Of Commencement/Completion** |  |
| a | Intimation about the Commencement /Completion of contract work has not been submitted to the Inspector in Form - VII annexed to the Rationalisation of Forms and Reports under Certain Labour Laws Rules, 2017 within 15 days. [Breach of Rule 25 (2) (viii)] |  |
| 3 | **Display Of Abstract Of Act** |  |
| a | An abstract of Act & Rules in the Form approved by the CLC[C] has not been displayed in English/Hindi and in the local language. [Breach of Rule, 79.] |  |
| 4 | **PERTAINING TO REGISTER AND RECORDS** |  |
| 4.1 | Following Registers have not been maintained at all/correctly |  |
| a | Employee Register in Form- A specified in the Schedule to the Ease of Compliance to Maintain Registers under various Labour Laws,20l7 has not  been maintained at all.[Breach of Rule 75 read with Rule 80 (1)] |  |
| b | Wage Register in Form B specified in the Schedule to the Ease of Compliance to Maintain Registers under various Labour Laws, 2017 has not been maintained correctly. [Breach of Rule 78 (1) (a) (i) & 78 (1) (a) (iii)] |  |
| c | Register of Loan / Recoveries in Form C specified in the Schedule to the Ease of Compliance to Maintain Registers under various Labour Laws, 2017 has not been maintained correctly. [Breach of Rule 78 (1) (a) (ii)] |  |
| d | Attendance Register in Form D specified in the Schedule to the Ease of Compliance to Maintain Registers under various Labour Laws, 2017 has not  been maintained Correctly. [Breach of Rule 78 (1) (a) (i)] |  |
| e | Wage slips in Form XIX is not being issued to the workmen at least a day prior to the disbursement of wages although wage period is more than a  week,[Breach of Rule, 78(1)(b).] |  |

**Minimum Wages Act, 1948 & Central Rules, 1950**

|  |  |  |
| --- | --- | --- |
| SN | Irregularities detected | Remarks |
| 1 | The following notices were not displayed at the main entrance of the establishment and at its office:- [Breach of Rule 22] |  |
| a | Notice containing Minimum Rates of Wages in English & language understood by the majority of the workers. |  |
| 2 | **DISPLAY OF ABSTRACT OF ACT** |  |
| a | The abstract of the Act and Rules made there under in English/Hindi was not displayed at the main entrance of the establishment and in its office.[ Breach of Rule 22] |  |
| b | N:B:  Where the delay in payment is over one month full particulars of employees, viz., name designation, address, amount due and the wage period, etc., should be noted on a separate sheet which will form an enclosure to the claim application to be filed immediately after the expiry of the notice period given to the employer |  |
| c | No. of Persons getting Overtime Benefit |  |
| d | Total Overtime Benefit Amount |  |
| 3 | PERTAINING TO REGISTER AND RECORDS |  |
| a | 1(b) Wage Register in Form - B specified in the Schedule to the Ease of Compliance to Maintain Registers under various Labour Laws, 2017 has not  been maintained correctly and kept at the work spot. [Breach of Rule 25 (2) & 26 (1)] |  |
| b | 2.(b) Register of Loan/Recoveries in Form - C specified in the Schedule to the Ease of Compliance to Maintain Registers under various Labour Laws, 2017 has not been maintained correctly and kept at the work spot. [Breach of Rule 21 (4)] |  |
| c | 3.(b)Attendance Register in Form - D specified in the Schedule to the Ease of Compliance to Maintain Registers under various Labour Laws, 2017 has not  been maintained correctly and kept at the work spot. [Breach of Rule 21 (4)] |  |
| 4 | WAGE SLIP/WAGE BOOK |  |
| a | Wage slips in form XI are not issued by the employer at least a day Prior Disbursement of wages. [Breach of Rule 26(2).] |  |

**Payment of Wages (Railway) & Rules, 1938**

|  |  |  |
| --- | --- | --- |
| SN | Irregularities detected | Remarks |
| 1 | Notice showing the wage period for which wages payable is not displayed as per rule 8(1)(i) in English and Hindi or in the Language [if that be not Hindi] of  the majority of persons employed. [Breach of Rules 8 (1)(i)] |  |
| 2 | Notice showing the days or dates on which wages are to be paid not displayed. [Breach of Rule 8(1) (ii)] |  |
| a | In English |  |
| b | In Hindi or in the language [if that be not Hindi] of the majority of the persons employed which is 27 |  |
| 3 | Notice showing the days or dates on which unpaid wages are to be paid is not displayed.  [Breach of Rule 8(1) (iii)] |  |
| a | In English. |  |
| b | In Hindi or in the language (if that be not Hindi) of the majority of the persons  employed which is 27 |  |
| 4 | DISPLAY OF ABSTRACT OF ACT |  |
| a | The Abstract of the Act and the rules made thereunder in Form IV in Hindi or in the language understood by majority of the employed persons was not displayed [Breach of Rule 21 read with section 25 of payment of wages Act 1936] |  |
| 5 | PERTAINING TO REGISTER AND RECORDS |  |
| a | Wage Register does not include requisite particulars prescribed under Rule 5. [Breach of Rule 5] |  |
| b | Wage Register & Register of Loan / Recoveries Form C have not been preserved. [Beach of Rule 6] |  |

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELSKYN/WKS/2022/20/BTIL TC Date: 06.08.2024

**Sr.DEE (TRS) AQ**

Sub:- ComprehensiveAnnual Maintenance Contract (CAMC) of BTILmake IGBT based Traction Converters fitted in 3phase locomotives of ELS/KYN for a period of 03Years through OEM M/s BTIL.

Ref: 1. This office's LOA No. ELS-KYN-ELECTRICAL /ELSKYNWKS-2022-

20-BTIL-TC /00623660096189 dated 25.01.2024.

2. Railway Board Letter No.L.253.AC.118.Vol. VII dated 13.06.2024

3. Your office letter ELS/AQ/DRG-23-24/21 dated 16.07.2024

--\*\*--

The contract for 06 Nos. BTIL make IGBT based TC CAMC was awarded to M/s ALSTOM TRANSPORT INDIA LIMITED, 65/2, Block C, Level 03, Bagmane Embassy Building Bagmane Tech Park, CV Raman Nagar Bengaluru- 560093, vide LOA under Ref.1.

Vide your letter at Ref.2. it is stated that ”09 Nos. [30263, 30265, 30267, 30296, 30301, 30303, 30310, 30514, 30518) BT (MICAS) make propulsion locomotives has been transferred from ELS/KYN to ELS/AQ, if these locos are covered in AMC contract of ELS/KYN with BT/ Bangalore and transfer AMC of these locos to ELS/AQ.”

In this connection, it is to inform you that out of above mentioned 09 locos, only 06 locos (30265, 30267, 30301, 30310, 30514 & 30518) are covered in ELS/KYN LOA and 02 locos 30263 & 30296 are under warranty and Loco No.30303 is already covered under AMC at your end. Also, it is learnt that AMC of M/s Alstom make traction converter is already running in your shed.

Therefore, you are requested to include the above-mentioned 06 locos in AMC contract running in your shed through quantity variation and accordingly kindly convey this office in this regard.

**Sr.DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No.ELSKYN/WKS/2020/16/Tap Changer Date: 06.08.2024

**Sr.DEE (TRS) AQ**

Sub:- Extension of work against, LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/ 00967350038710 dated 21-07-2021 for Repair, Rehabilitation, Reconditioning, Testing and Supply of Tap Changer of Electric Locomotives based at Electric Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.”

Ref: This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/ 00967350038710 dated 21-07-2021

--\*\*--

The contract for the subject work was awarded to M/s River Engineering Pvt Ltd, 54-55, Toy City, Ecotech-III, Greater Noida, Noida – 201206, vide LOA under reference. This contract is for 70 Nos. tap changers for three different sheds i.e. Ajni, Bhusawal and ELS Kalyan with completion period up to three years.

The completion period of this contract has been expired on 20.07.2024.

As on date, Out of 41 nos. tap changer of ELS/KYN, 38 nos. Tap changers have been repaired and 3 nos. tap changers are balance for which extension will be processed by this office.

You are requested to convey to this office if any extension will be required for your office to execute the subject contract along with proper justification for balance quantity. Also kindly convey the levy of penalty if any.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/16/Tap Changer Date: 27.12.2021

**Sr.DEE (TRS) BSL**

Sub:-This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/

00967350038710 dated 21-07-2021 for Repair, Rehabilitation, Reconditioning,

Testing and Supply of Tap Changer of Electric Locomotives based at Electric

Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.

Ref : (i) This office letter of even No. dated 11-08-2021

(ii) This office letter of even No. dated 24-09-2021

--\*\*--

LOA including Specification and Scope of work was sent to you vide this office letter referred at Sr. No. (i) above. Further PBG, Indemnity Bonds were sent vide this office letter referred at Sr. (ii)

Now agreement No.ELSKYN/WKS/2020/16/TC dated 04-10-2020 has been signed. This agreement contains Power of Attorney and its legal vetting from LAW Section, 3 Indemnity Bonds and their legal vetting from LAW Section, Bank Guarantee Bond towards PG along with its confirmation from Bank and legal vetting from LAW Section.

One copy of agreement duly verified by WAO(ELW) Bhusawal vide letter No. AC/W/BSL/FX/AGREEMENT/33 dated 06-12-2021 is sent herewith for your reference and records. One original agreement copy is available at WAO (ELW) Bhusawal office.

Further original Indemnity Bond dated 31-07-2021 for Rs 1,90,00,000/- pertaining to your office is sent herewith for your records and reference.

As stated earlier Law vetting charges of Rs 200/- each for documents verified by LAW Section shall be deducted from this end.

Please acknowledge the receipt.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2024/IR\_WCMS User Date. 05.08.2024

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing IR-WCMS user details and Mapping with HRMS

--\*\*\*--

ADEE-I (TRS) KALYAN, Shri Nitish Kumar Shukla has been transferred from ELS/Kalyan. A vetted Contract agreement was forwarded to contractor through his user on IR-WCAMS this CA is to be pulled back and resend to correct user id of contractor and same can be send to Sr.DEE/TRS/Kalyan for signing. For this purpose you are requested to replace the old IR-WCMS user with the new user details as given below.

|  |  |  |
| --- | --- | --- |
| Particulars | Old user details | New user details |
| Name (in full) | NITISH KUMAR SHUKLA | BHUPESH YADAV |
| Designation | ADEE (TRS) Kalyan | ADEE (TRS) KALYAN |
| IR-WCMS Id | adeeelskyn1 | adeeelskyn1 |
| IR-WCMS Password | Adeeelskyn1@1 | Adeeelskyn1@123 |
| HRMS Id | -- | WZMGUW |
| HRMS Password | -- | Bhupesh@71 |
| IREPS user ID | adee1trs.elskyn@gmail.com | adee1trs.elskyn@gmail.com |

You are requested to replace the details with new one and map the ID with HRMS.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2024/IR\_WCMS User Date. 02.08.2024

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing IR-WCMS user details and Mapping with HRMS

--\*\*\*--

Below old IR-WCMS user DEE-I (TRS) KALYAN, Shri Shikhar Srivastva’s user has been transferred to Shri Bhupesh Yadav DEE-I (TRS) KALYAN of same shed. Hence you are requested to replace the old IR-WCMS user with the new user details. Also map the user with HRMS

|  |  |  |
| --- | --- | --- |
| Particulars | Old user details | New user details |
| Name (in full) | SHIKHAR SRIVASTAVA | BHUPESH YADAV |
| Designation | DEE-I (TRS) KALYAN | DEE-I (TRS) KALYAN |
| IR-WCMS Id | Deeelskyn1 | Deeelskyn1 |
| IR-WCMS Password | deeelskyn!1234 | deeelskyn!1234 |
| HRMS Id | JEGKZL | WZMGUW |
| HRMS Password | Smeetu25@ | Bhupesh@71 |
| IREPS user ID | deetrs.elskyn@gmail.com | deetrs.elskyn@gmail.com |

You are requested to replace the details with new one and map the ID with HRMS.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/2019/16/HIRECT SIV Date: 24.07.2024

**Sr.DEE (TRS) BSL**

Sub:- Quantity extension along with time Extension of CA No.CR/BSL /Elect. /2021/0011 dated 20-07-2021 for “Renewal of Annual Maintenance Contract (AMC) of HIRECT make SIV for the period of three years at Electric Loco Shed, Bhusawal / Kalyan.”

Ref: (i) Your office LOA No. BHUSAWAL DIVISION- ELECTRICAL/ BSL-TRS-TENDER-2021-01/ 01029820032724 dtd. 27-02-2021

(ii) Your office letter no. BHUSA/TRS/TENDER/2021/01 dated 27.02.2024

(iii) Your office letter no. BHUSA/TRS/TENDER/2021/01 dated 20.06.2024

--\*\*--

A contract for the subject work was awarded to M/s Hind Rectifiers Limited- Mumbai, Lake Road, Bhandup West, Mumbai - 400 078 at a total cost of Rs.19,49,319/- vide LOA No. BHUSAWAL DIVISION- ELECTRICAL/ BSL-TRS-TENDER-2021-01/ 01029820032724 dtd. 27-02-2021 with a completion period of three years i.e. up to 27.02.2024 and extended upto 17.06.2024 & 17.07.2024 vide your office letter mentioned under Ref.2 and Ref. 3

Vide letter under ref 2, it is learnt that there is no Hirect make SIV under AMC at ELS/BSL. Therefore, this balance quantity of ELS/BSL will be utilized by ELS/KYN. Hence, it is requested for time extension in the existing contract upto 18.08.2024 to utilize the balance quantity of the original contract i.e. upto 100%.

In addition, the quantity expected to carry in one quarter is 450 loco days therefore, the firm may be requested to extend the original contract quantity upto 25% so that the healthiness of the SIV can be ensured.

**Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/IR\_WCMS User Date. 18.07.2024

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing of LOA Admin in IR-WCMS portal.

--\*\*\*--

In this office there were two DEEs posted in the past, LOA was signed by these two DEEs. As on date there is only one DEE available at ELS Kalyan. Thus, this office is facing problems assigning activities of LOAs signed by earlier DEE. Following is the list of LOAs whose LOA admin is required to be replaced.

|  |  |
| --- | --- |
| Sr. No. | LOA No. & Date |
| 1 | ELS-KYN-ELECTRICAL/ELSKYNWKS-2021-38-RW-AM/00958190052427  dated 07.04.2022 |
| 2. | ELS-KYN-ELECTRICAL/ELSKYNWKS2021-14-PUCONV-A/01136250061230 dated 05.09.2022 |
| 3. | ELS-KYN-ELECTRICAL/ELSKYNWKS22-3Waterchanne/01043400066222 dated 21.11.2022 |
| 4. | ELS-KYN-ELECTRICAL/ELSKYN-WKS-22-34-7775-TFP/ 00028970085714  dated 30.08.2023 |
| 5. | ELS-KYN-ELECTRICAL/ELSKYNWKS-22-39-AC-Out-A/10040010087299  dated 20.09.2023 |
| 6. | ELS-KYN-ELECTRICAL/ELSKYNWKS22-29-TMStator-A/00064860090663 dated 08.11.2023 |

You are requested to replaced LOA admin of these LOAs and make new LOA admin to existing DEE user ID- dee2trskyn (HRMS ID- RGJOJK).

Please do the needful.

**ADEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/IR\_WCMS User Date. 15.07.2024

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing IR-WCMS user details and Mapping with HRMS

--\*\*\*--

Below old IR-WCMS user SSE(MW) Shri Manohar Tekade’s user has been transferred to Shri Kartik Jayesh Bhatty SSE(MW) of same section. Hence you are requested to replace the old IR-WCMS user with the new user details. Also map the user with HRMS

|  |  |  |
| --- | --- | --- |
| Particulars | Old user details | New user details |
| Name (in full) | MANOHAR TEKADE | KARTIK JAYESH BHATTY |
| Designation | SSE (MW) ELS KYN | SSE (MW) ELS KYN |
| IR-WCMS Id | ssemwelskyn |  |
| IR-WCMS Password | Ssemwelskyn@123 |  |
| HRMS Id | XJJMDN | JCNGIZ |
| HRMS Password | D12m05@1995 | Aumi@1105 |
| IREPS user ID | ssemw.elskyn@gmail.com | ssemw.elskyn@gmail.com |

You are requested to replace the details with new one and map the ID with HRMS.

**ADEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  व.रि.मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय, विद्युतलोकोशेड, कल्याण–४२१३०१  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301. Email: srdeetrskyncrly@bb.railnet.gov.in |

**No**. **ELSKYN/WKS/2024/01 Pending Bill Date: 03.07.2024**

**Sr. DFM/BB**

**(Kind attention: Shri Akshay Sharma, DFM-II/BB)**

Sub: Regarding pending bill under PU 32 of Demand No.5 C, Sub Head- 550 pertaining to ELS/KYN for want of funds.

Present status of pending bill under PU 32 of Demand No.5 C, Sub Head- 550 pertaining to ELS/KYN is as under :-

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **SN** | **Description** | **Firm** | **Firm Invoice** | **Amount** | **Demand No** |
| 1 | Overhauling of CCB | M/S KBIL | Bill No.CRBBY-Elec-24-005-B1 & Date 04.05.2024 | ₹ 14,16,064.05 | 5 |
| 2 | Cleaning of bogie frame and its components of Electric locomotives | M/S Utsav Care Refrigeration & Electrical | UCR/020/23-24/03 dated 18.05.2024 | ₹ 5,16,600.12 | 5 |
| 3 | AMC CAB AC for 03 year | M/S Utsav Care Refrigeration & Electrical | UCRE/07 dtd.17.05.2024 | ₹ 8,16,895.86 | 5 |
| 4 | Repair, Rehabilitation, Reconditioning, Testing and Supply. | M/S High Volt Electricals Pvt Ltd | CR/BBY/Elect./2023/0079/B2. (Firm Invoice 313 dated 04.03.2024 & 03 dated 04.04.2024) | ₹ 1,02,38,053.49 | 5 |
| 5 | Modification in under slung Compressor Mounting Legs of 3 phase locomotives | M/S Tara Engineering Works-.Kolkata | Invoice No.TEW04UCKYN Dtd 06/05/2024 | ₹ 8,44,927.20 | 5 |
| 6 | Renewal of Annual Maintenance Contract (AMC) of HIRECT | M/S Hind Rectifiers Limited- Mumbai | HRL/ ELS/KYN/AMC-SIV/ 11 dated 08.05.2024 (Firm's Invoice No.231040255 dated 20.12.2023) | ₹ 1,61,997.76 | 5 |
| 7 | Safety Bracket after cooler | M/S Akshay Enterprises | AE /01 dated 15.04.2024 (Against Firm Invoice No. 50 dated 01.03.2024) | ₹ 4,97,859.70 | 5 |
| 8 | PU Painting of earlier PU Painted Conventional Locomotives, 93 Locos | M/S Rangshree Arts- Jalgaon | CR/BBY/Elect./2022/0060/B4 | ₹ 4,66,513.32 | 5 |

The above-mentioned bills are pending due to non-availability of funds. The firms are chasing their bill with this office. The letter of the same received is enclosed along with this letter.

Therefore, it is requested to process this bill on priority basis as the same has been pending since last 3-4 months.

This is for your information and necessary action

**(Niraj Kumar Garg)**

**Sr.DEE/TRS/KYN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No: ELSKYNWKS22-10-Electrifi-A** **Date: 03.07.2024**

Regional Inspection Office Head,

RITES Limited, Western Region,

5th Floor, Regent Chamber,

Nariman Point,

Mumbai - 400 021

**Sub:** LOA no. ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023 for the work of “Electrification work for newly shifted Auxiliary Section and Body Section at Electric Loco Shed, Kalyan”

**Ref :** (i.) LOA no.ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023

(ii.) Firm’s letter ref no. TE/56/24-25 Dtd. 26.06.2024

--\*\*--

A work contract for the subject work was awarded to M/s Tanya Electricals-Thane, C303, Gulmoher Complex Phase 3, Viva College Road, Virar, Palghar, Thane- 401303 Maharashtra, India vide LOA under ref (i).

In connection to above firm vide letter under ref (ii) has requested for the RITES inspection of some schedule items in term of tender condition mentioned under chapter IV Inspection clause which states that “RITES inspection Test Certificate of Flood light and Street light to be submitted by firm at the time of supply.”

The details of item for inspection which are ready at manufactures premises are mentioned below

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SN** | **LOA’s Schedule item no.** | **Description** | **Qty** | **Address of Manufacture Premise for inspection** |
| 1 | Schedule – 14(1) | 4 CORE 185 SQ. MM Aluminium Armoured cable | 800 Mtrs | M/s. Vardhaman cables & conductors.  **Works:** 129, Shinoli (B.K),Tal. Chandgad, Dist. Kolhapur, Maharashtra.  Mob: i). 9920472760 ii). 9403346846  Email : i) [ajaymsaboo@gmail.com](mailto:ajaymsaboo@gmail.com).  ii)sales@bharatcab.in |
| 2 | Schedule – 14(2) | 4 CORE 25 SQ. MM Aluminium Armoured cable | 500 Mtrs |
| 3 | Schedule – 14(3) | 4 CORE 10 SQ.MM Copper Armoured cable | 500 Mtrs |
| 4 | Schedule – 14(4) | 2 CORE 4 SQ. MM Copper Armoured cable | 1188 Mtrs |

Copy of ELS Kalyan specification of the above mentioned schedule items and LOA along with manufacture data sheet and test report is enclosed.

This is for your information and necessary action

**(Shri. Bhupesh Yadav)**

**ADEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

C/- M/s Tanya Electrical - Thane

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  व.रि.मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय, विद्युतलोकोशेड, कल्याण–४२१३०१  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301. Email: srdeetrskyncrly@bb.railnet.gov.in |

**No**. **ELSKYN/WKS/2023/30/AMC-SWL Date: 28.06.2024**

**Sr. DFM/BB**

**(Kind attention: Shri Akshay Sharma, DFM-II/BB)**

**Sub:** CAMC of Surface Wheel Lathe Model no. YSL-012 at Electric Loco Shed,

Kalyan.

**Ref:** COFMOW/IR/S/OP-608850 dated: 25.05.2021

The subject work was awarded to M/s. HYT Engineering Company Pvt. Ltd. Vide COFMOW AT under ref. This work includes supply of Surface Wheel Lathe machine as well as AMC for period of 05 years post of warranty period.

Accordingly, the Proposal to execute the AMC part of work was initiated on 24.02.2024, and same was vetted by finance on 18.04.2024. Further LOA for the same was prepared and sent to account for verification. During verification it was learnt that firm should submitted the BG for AMC 90 days prior to expiry of warranty, if not submitted suitable penalty as per clause 0702 section-II, Bid Document part – I to be charged to the firm.

However, clause 17.3.8 of COFMOW AT under ref does not mention any penalty clause for delay in submission of PG. Hence it is requested to waive off LD for delay in submission of BG in the subject work. PG would be collected from firm within 30 days from the issue of LOA.

Henceforth, as advised by Divisional account, in future all the case of AMC related to COFMOW will be dealt as per clause 17.3.8 of COFMOW AT under ref. and penalty would be collected in term of COFMOW clause 0702 section-II, Bid Document part – I.

Hence it is requested to waive off LD for delay in submission of BG in the subject work.

**Sr.DEE/TRS/KYN.**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड,कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 |  | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

ELSKYN/WKS/2024/Con. Fund Date: 19.06.2024

**Sr. DEN (GSU)**

**CSMT**

Sub.: Requirement of contingency fund from ongoing work under PH 42

Ref: Umbrella work CR Pink Book no. 709b/2020-21

--\*\*--

This office has urgent requirement of fund of Rs. 10 Lakhs for executing the work related to procurement of ICT equipment’s, Furniture’s and other necessary items for various activities.

The sanctioned Umbrella work under PH-42 i.e. “Augumentation of Electric Loco shed, Kalyan by creation of facilities for homing of 200 Locos” is under execution. The cost of work is Rs. 31.68 Cr, which include the contingency of Rs. 16.95 Lakhs (Civil Portion).

It is therefore requested to allocate contingency fund of Rs. 10 Lakhs only from the above-mentioned umbrella work for procurement of ICT equipment’s, Furniture’s and other necessary items for various activities.

**Sr.DEE (TRS) KYN**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELSKYN/WKS/2019/16/HIRECT SIV Date: 12.06.2024

**Sr.DEE (TRS) BSL**

Sub:- Extension of CA No.CR/BSL/Elect./2021/0011 dated 20-07-2021 for “Renewal of Annual Maintenance Contract (AMC) of HIRECT make SIV for the period of three years at Electric Loco Shed, Bhusawal / Kalyan.”

Ref: (i) Your office LOA No.BHUSAWAL DIVISION- ELECTRICAL/ BSL-TRS-TENDER-2021-01/ 01029820032724 dtd. 27-02-2021

(ii) Your office letter no.BHUSA/TRS/TENDER/2021/01 dated 27.02.2024

--\*\*--

A contract for the subject work was awarded to M/s Hind Rectifiers Limited- Mumbai, Lake Road, Bhandup West, Mumbai - 400 078 at a total cost of Rs.19,49,319 /- LOA No.BHUSAWAL DIVISION- ELECTRICAL/ BSL-TRS-TENDER-2021-01/ 01029820032724 dtd. 27-02-2021 with a completion period of three years i.e. up to 27.02.2024 and extended upto 17.06.2024 vide your office letter mentioned under Ref.2.

This office tender for subject work is under finalization, also 2 locos fitted with Hirect make SIV was received by this office; hence you are requested to extend the subject work for minimum one month so that the healthiness of SIV can be ensured without interruption.

**(Shikhar Srivastava)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/2022/10/BTIL TC Date. 08.06.2024

**Post Commander**

**RPF Kalyan Loco**

Sub: Work Permission at Electric Loco Shed Kalyan for carrying out “Comprehensive Annual Maintenance Contract (CAMC) of BTIL make IGBT based Traction Converters fitted in 3phase locomotives of ELS/KYN for a period of 03 Years through OEM M/s BTIL.”

Ref : (i) LOA No. ELS-KYN-ELECTRICAL /ELSKYNWKS-2022-20-BTIL-TC /

00623660096189 dtd. 25.01.2024

--\*\*--

Following employee deputed by M/s ALSTOM TRANSPORT INDIA LIMITED-BENGALURU 65/2, Block C, Level 03, Bagmane Embassy Building Bagmane Tech Park, CV Raman Nagar Bengaluru 560093 is permitted to work at ELS Kalyan for carrying out Annual Maintenance Contract against the above referred LOAs and other warranty related works at Electric Loco Shed, Kalyan round the clock all working days including Sundays and holidays up to 24.01.2027:

|  |  |  |  |
| --- | --- | --- | --- |
| Sr. No. | Name | Employee Code | AADHAR No |
| 1. | Mr. Makarand Gawade | 9440-5490-2612 | 9440-5490-2612 |

Above employee have provided copies of their Police Verification and Adhar card same are attached herewith for your reference.

**DEE/TRS/KYN**

**For Sr. DEE (TRS) Kalyan**

Copy to: M/s ALSTOM TRANSPORT INDIA LIMITED-BENGALURU

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/IR\_WCMS User Date. 28.05.2024

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Replacing IR-WCMS user details and Mapping with HRMS

--\*\*\*--

Below old IR-WCMS user SSE(AUX) Nemi Chand has been transferred from ELS/Kalyan. Hence you are requested to replace the old IR-WCMS user with the new user details. Also map the user with HRMS

|  |  |  |
| --- | --- | --- |
| Particulars | Old user details | New user details |
| Name (in full) | NEMI CHAND | Chandrakant J Bendre |
| Designation | SSE (Aux) ELS KYN | SSE (Aux) ELS KYN |
| IR-WCMS Id | sseauxelskyn |  |
| IR-WCMS Password | Sseauxelskyn@123 |  |
| HRMS Id |  | TXTYRZ |
| HRMS Password |  | Bendre@123 |
| IREPS user ID | sseaux.elskyn@gmail.com | sseaux.elskyn@gmail.com |

You are requested to replace the details with new one and map the ID with HRMS.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2020/21/ MEDHA/AMC-SIV Date: 29.05.2024

**Sr.DEE (TRS) AQ**

Sub:- Contract Agreement No. ELSKYN/WKS/2020/21/MEDHA/AMC-SIV dated 05.08.2021 for the work of “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) for a period of three years as per RDSO’s SMI No.RDSO/2016/EL/SMI/0291 (Rev.0) at Electric Loco Shed Kalyan, Bhusawal and Ajni, Qty- 70 Nos.”

Ref:- 1. LOA No. ELS-KYN-ELECTRICAL/ ELSKYN-WKS-2020-21-AMC-

SIV/00987030036441 dated 04.06.2021

2. CR HQ’s Letter No.L.253.AC.118.Vol-VI dated 24.01.2023

3. CR HQ’s Letter No.L.253.AC.118.Vol-VI dated 20.06.2023

--\*\*--

With reference to CR HQ’s letter mentioned under Ref.2 & 3 some of ELS/AQ’s locos having Medha SIV were transferred to ELS/AQ.

These locos were under AMC through subject contract at your end before transferring to ELS/AQ. You are requested to provide the details of SIV Serial no. covered under AMC, Loco Days executed at your end, balance loco days. Also please provide how many no. of locos days can be utilized by ELS/Kalyan from the balance loco days at your end.

For variation in quantity and extension of work above data is required urgently, therefore you are requested to provide required data at the earliest please.

(**Shikhar Srivastava**)

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2017/24/DBR Repair Date. 14.05.2024

**Sr.DEE(TRS) AQ**

Sub: C .A. No. ELS/AQ/DRG/WCQ/18-19/01 dated 03-01-2019 for “Repairs

of Complete Dynamic Braking Resistance (DBR) of A C Locomotives

of ELS/Ajni, BSL, KYN & ELW/BSL.

Ref: Your letter No.ELS/AQ/DRG/WCQ/18-19/01 dated 22-03-2024

--\*\*\*--

With reference to your letter under ref – 1, it is hereby conveyed that there is no warranty obligation pending regarding the subject work. Maintenance certificate is attached herewith for your reference.

This is for your information and necessary action.

(**Shikhar Srivastava**)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/MIsc. Date: 08.05.2024

CWM/ELW/BSL

Sub:- Warranty obligation for “Conversion & Up gradation (1500 AMP capacity) of BA Panels of Electric Locomotives, Qty. 9 Locomotives.’’

Ref: (i) LOA No. ELW/BSL/Tender/2017-18/14 dated 27/09/2017

(ii) This office letter no. ELS/KYN.ACE.FR.ELWBSL dtd. 04.12.2018

(iii) Your office letter no. BSL/ELW/Tender/2017-18/14 dated 03.04.2023

(iv) This office letter no.ELSKYN/WKS/Misc dated 06.04.2023

(iv) Your office letter no. BSL/ELW/Tender/2017-18/14 dated 03.04.2023 received on date 04.05.2024

--\*\*--

The reply to your office letter mentioned under Ref.(iii) was already given by this office vide letter of even no. dated 06.04.2023 and also email was sent on email id [waoelwbsl@yahoo.com](mailto:waoelwbsl@yahoo.com), [cwmelwcrly@gmail.com](mailto:cwmelwcrly@gmail.com) . However, the same letter under Ref.(iii) has been received again by this office on date 04.05.2024, therefore letter under reference (iii) is being sent herewith for your information and further action.

(ASHISH GUPTA)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELSKYN/WKS/20/17/AMC SIV Siemens Date: 04.05.2024

**Sr.DEE (TRS) BSL**

Sub:- Extension of work against, LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021 for “Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan”

Ref: Your office LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

--\*\*--

The contract for the subject work was awarded to M/s Siemens Ltd. Navi Mumbai, vide LOA under reference with a completion period of three years i.e. up to 07.06.2024.

This office has initiated a new proposal for subject work, which is currently under administrative approval stage. The same will take considerable amount of time for finalization, hence it is requested to extend the subject work up to 31.07.2024 for 24 locos of ELS/Kalyan so that the healthiness of SIV can be ensured without interruption.

**(Shri. Shikhar Srivastava)**

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No: ELSKYNWKS22-10-Electrifi-A** **Date: 31.05.2024**

Regional Inspection Office Head,

RITES Limited, Western Region,

5th Floor, Regent Chamber,

Nariman Point,

Mumbai - 400 021

**Sub:** LOA no. ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023 for the work of “Electrification work for newly shifted Auxiliary Section and Body Section at Electric Loco Shed, Kalyan”

**Ref :** (i.) LOA no. ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023

(ii.) Firm’s letter ref no. TE/507/23-24 Dtd. 02.05.2024

--\*\*--

A work contract for the subject work was awarded to M/s Tanya Electricals-Thane, C303, Gulmoher Complex Phase 3, Viva College Road, Virar, Palghar, Thane- 401303 Maharashtra, India vide LOA under ref (i).

In connection to above firm vide letter under ref (ii) has requested for the RITES inspection of some schedule items in term of tender condition mentioned under chapter IV Inspection clause which states that “RITES inspection Test Certificate of Flood light and Street light to be submitted by firm at the time of supply.”

The details of item for inspection which are ready at manufactures premises are mentioned below

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SN** | **LOA’s Schedule item no.** | **Description** | **Qty** | **Address of Manufacture Premise for inspection** |
| 1 | Schedule - 2 | 45 Watt LED Street Light Fittings | 20 Nos | M/s. Mika Engineers.  **Works:** Shed No. 2, At post –Aghai, Tal. Shahapur, Dist-Thane-421601.  Mob: 9975085712  Email : mika@mtnl.net.in |
| 2 | Schedule – 6 | 150 Watt LED flood Light luminaries | 140 Nos |

Copy of ELS Kalyan specification of the above mentioned schedule items and LOA along with manufacture data sheet and test report is enclosed.

This is for your information and necessary action

**(Shri. Bhupesh Yadav)**

**ADEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

C/- M/s Tanya Electrical - Thane

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.coxm](mailto:srdeetrskyncrly@gmail.coxm)  : srdeetrskyncrly |

No: ELSKYN/WKS/2020/29/MPCS Date: 30.04.2023

**Sr.DEE (TRS) BSL**

Sub:- Annual Maintenance contract (AMC) of M/s. Medha make MPCS (FDCS) at Electric loco shed, Bhusawal, Kalyan.

Ref:- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER- 2020-06 / 00987030024273 dated 20.08.2020

2. Your office letter no.BSL/TRS/Tender/2016/08 dated 15.06.2021.

3. Your office letter No.BSL/TRS/Tender/2020/06 dated 24.07.2023

4. Your office letter No. BSL/TRS/Tender/2020/06 /00987030024273 dtd 17.08.2023

5. Your office letter No. CR/BSL/Elect./2020/0025/CD-0002

6. Your office letter No. CR/BSL/Elect./2020/0025/CD-0003

--\*\*--

With reference to your office letter at Ref.2 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 09.09.2020. Vide Joint Note No.ELS/KYN/I&E/Medha/MPCS dated 16.06.2021 date of handover of 06 locos was revised and 06 locos are handed over to M/s Medha for subject mentioned work. Vide Joint No.ELS/KYN/I&E/MEDHA/FDCS/02/10 dated 29.10.2021 one more loco added in the subject AMC from dated 29.10.2021.

Payment for AMC work of Medha make FDCS for 11 Qtrs. i.e. from 09.09.2020 to 08.06.2023 has been already passed

Further, AMC work carried out by firm during the period 09.06.2023 to 12.03.2024 i.e. 3 Qtrs. is as under:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Qtr. No. | AMC Period | No. of Locos | Date of Joint Note | No. Loco Days. | Downtime in Hrs. |
| 1. | 09.06.2023 to 08.09.2023 i.e. 92 Days | 07 | 14.10.2023 | 644 | 00 Hrs. |
| 2. | 09.09.2023 to 08.12.2023 i.e. 91 Days | 07 | 02.01.2024 | 637 | 00 Hrs. |
| 3. | 09.12.2023 to 12.03.2024, i.e. 95 days | 07 | 14.03.2024 | 665 | 00 Hrs. |
|  |  | **Total No. of Loco days** | | **1,946** |  |

AMC work of Medha make FDCS for 3 Qtrs. i.e. from 09.06.2023 to 12.03.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

As stated in your office letter mentioned at Ref.3, Joint note and downtime calculation sheet of each quarter (3 Qtrs.) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

(ASHISH GUPTA)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**ELSKYN/WKS/2020/17/AMC SIV Siemens DATE:- 03.04.2024**

**Sr. DEE/TRS**

**BHUSAWAL**

**Subject:** Annual Maintenance Contract of Siemens make SIV for the period of three

year at Electric Loco Shed, Bhusawal/Ajni/Kalyan

**Ref:** 1.LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

2. Your office letter no.BSL/TRS/Tender/2021/02 dated 11.07.2023

--\*\*--

The AMC of 14 Nos. Siemens make SIV at Electric Loco Shed, Kalyan for a period of 3 years has been started from 08.06.2021 vide Joint Note No.ELSKYN/PEX/JN/SIEMENS/SIV/CAMC/21-22/1 dated 08.06.2021. Further vide Joint No.ELSKYN/PEX/JN/SIEMENS/SIV/HO/AMC/22-23/1 dated 30.01.2021, 04 locos are handed over to firm for AMC (03 Nos. w.e.f 13.01.2023 and 01 No. w.e.f 24.01.2023).

As stated in your office letter mentioned at Ref.2, Joint note and Penalty statement of each quarter from the period 08.06.2023 to 07.12.2023 (i.e 9th & 10th Qtrs) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

|  |
| --- |
| (SHIKHAR SRIVASTAVA) DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 05.04.2024

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no.ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to above referred contract a Joint note and penalty statement of five quarters i.e from 22.04.2022 to 21.07.2023 duly signed by concerned officer in-charge was sent to your office for passing payment as stated in your office letter mentioned at Ref.2.

Now CAMC work of AAL make SIV for 6th & 7th Qtr i.e from 22.07.2023 to 21.01.2024 has been carried out by firm as per LOA and scope of work satisfactorily.

The certificate for measurement of quarter 6th & 7Th Quarter of above-mentioned contract is as under: -

1. It is certified that, 20% work is check done by me.
2. It is certified that; this work is under process.

Joint notes and penalty statements of these quarters (6th & 7th Qtr) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end.

(SHIKHAR SRIVASTAVA)

DEE/TRS/KALYAN

For Sr. DEE/TRS/KALYAN

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELS KYN/WKS/2023/10/FDCS-Medha Date: 12.03.2024

**Sr.DEE (TRS) BSL**

Sub:- Inclusion of Ver.3 Fault Diagnostic System (MPCS) into the work of “Comprehensive Annual Maintenance Contract (AMC) of M/s Medha Make (MPCS) (FDCS) at Electric Loco Shed, Bhusawal, Kalyan”

Ref: 1. Your office LOA No.BSL/TRS/Tender/2023/13/00987030096072 dtd 24.01.2024

3. This office note no.ELS/KYN/FDCS/MedhaV3/02 dated 27.02.2024

2. This office letter of even no. dated 16.10.2023

--\*\*--

Vide your office LOA mentioned under ref.1, ELS/Kalyan’s 07 Nos. Medha make Ver.2 MPCS are covered under CAMC. There is no coverage of AMC of Medha make Ver.3 MPCS. Therefore, a list of Medha make Ver.3 MPCS whose warranty is expiring in next one year i.e upto March 2025 is prepared and requested to include this quantity for one year in the LOA issued by you.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr. No. | LOCO NO | FDCS Sr. No | MPCS-DOC | Warranty Expiring date |
| 1 | 27118 | 2070 | 03-05-2016 | 02-05-2021 |
| 2 | 27356 | 2219 | 31-10-2018 | 30-10-2023 |
| 3 | 28557 | 2197 | 23-01-2019 | 22-01-2024 |
| 4 | 27109 | 2203 | 20-03-2019 | 19-03-2024 |
| 5 | 27260 | 2289 | 26-09-2019 | 25-09-2024 |
| 6 | 27374 | 2553 | 25-11-2019 | 24-11-2024 |
| 7 | 27367 | 2348 | 31-12-2019 | 30-12-2024 |
| 8 | 27375 | 2552 | 22-02-2020 | 21-02-2025 |
| 9 | 27112 | 2174 | 02-03-2020 | 01-03-2025 |
| 10 | 27102 | 2315 | 03-03-2020 | 02-03-2025 |

It is requested to include ELS/KYN’s above mentioned quantity of Ver.3 MPCS for one year in the LOA issued by your office under ref.1.

**(Ashish Gupta)**

**DEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/IR\_WCMS User Date. 05.03.2024

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

Please create IR-WCMS IDs for the following SSEs of ELS Kalyan. Required particulars are as under:

|  |  |  |
| --- | --- | --- |
| Name (in full) | UDAY KUMAR | NIRAJ KUMAR SAXENA |
| Designation | SSE (Works) ELS KYN | SSE (TM) ELS KYN |
| Date of Birth | 10.02.1990 | 10.05.1966 |
| Mobile No./ CUG No. | 8355830763 | 9004411311 |
| E-mail ID | ssewk.elskyn@gmail.com | nksaxena1966@gmail.com |
| Department | Electrical | Electrical |
| IPAS ID | CR02EXE2558 | -- |
| IRPSM ID | -- | -- |
| IREPS DETAILS |  |  |
| 1. IREPS Login ID | ssewk.elskyn@gmail.com | nksaxena1966@gmail.com |
| 1. User Name | UDAY KUMAR | NIRAJ KUMAR SAXENA |
| 1. Designation | SSE(Works) ELS KYN | SSE(TM) ELS KYN |
| 1. Department | Electrical | Electrical |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed, Kalyan - 421 301 | Office of Sr. DEE (TRS), Electric Loco Shed, Kalyan - 421 301 |
| Office Phone No. | 0251 6763120 | 0251 6763123 |
| Employee Id | 00229803555 | 00201775583 |

Also, a list of IR-WCMS users of this shed is sent herewith along with their HRMS Id for mapping.

You are requested to create above users and map their IDs with HRMS.

**ADEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No: ELSKYNWKS22-10-Electrifi-A** **Date: 28.02.2024**

Regional Inspection Office Head,

RITES Limited, Western Region,

5th Floor, Regent Chamber,

Nariman Point,

Mumbai - 400 021

**Sub:** LOA no. ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023 for the work of “Electrification work for newly shifted Auxiliary Section and Body Section at Electric Loco Shed, Kalyan”

**Ref :** (i) LOA no. ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023

(ii) Firm’s letter ref no. TE/505/23-24 Dtd. 24.02.2024

--\*\*--

A work contract for the subject work was awarded to M/s Tanya Electricals-Thane, C303, Gulmoher Complex Phase 3, Viva College Road, Virar, Palghar, Thane- 401303 Maharashtra, India vide LOA under ref (i).

In connection to above firm vide letter under ref (ii) and (iii) has requested for the RITES inspection of some schedule items in term of tender condition mentioned under chapter IV Inspection clause which states that “RITES inspection Test Certificate of cable and LED luminaries to be submitted by firm at the time of supply.”

The details of item for inspection which are ready at manufactures premises are mentioned below

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SN** | **LOA’s Schedule item no.** | **Description** | **Qty** | **Address of Manufacture Premise for inspection** |
| 1 | Schedule - 19 | Supply + erection, testing and commissioning of 10-12W LED pit lighting confirming to IP 67 watertight with complete sealed suitable to work on 110V AC supply. The work also includes fixing of light fittings with wire mesh | 350 Nos | Mika Engineers. Post Aghal, Shed no. 2, Tal- Shahpur, District- Thane- 421601  Mob: 9820019739 (Asgar B. Karimi)  9975085712 (Puransingh) |

Copy of ELS Kalyan specification of the above mentioned schedule items and LOA along with manufacture data sheet and test report is enclosed.

This is for your information and necessary action

**(Shri. Bhupesh Yadav)**

**ADEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

C/- M/s Tanya Electrical - Thane

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No: ELSKYNWKS22-10-Electrifi-A** **Date: 28.02.2024**

Inspection Office, Chennai

CTS Building, 2nd Floor, BSNL Complex,

No-16, Greams Road,

Chennai-600006

**Sub:** LOA no. ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023 for the work of “Electrification work for newly shifted Auxiliary Section and Body Section at Electric Loco Shed, Kalyan”

**Ref :** (i) LOA no. ELSKYNWKS22-10Electrifi-A /01374300076008 Dtd. 28.04.2023

(ii) Firm’s letter ref no. TE/507/23-24 Dtd. 15.02.2024

--\*\*--

A work contract for the subject work was awarded to M/s Tanya Electricals-Thane, C303, Gulmoher Complex Phase 3, Viva College Road, Virar, Palghar, Thane- 401303 Maharashtra, India vide LOA under ref (i).

In connection to above firm vide letter under ref (ii) and (iii) has requested for the RITES inspection of some schedule items in term of tender condition mentioned under chapter IV Inspection clause which states that “RITES inspection Test Certificate of cable and LED luminaries to be submitted by firm at the time of supply.”

The details of item for inspection which are ready at manufactures premises are mentioned below

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SN** | **LOA’s Schedule item no.** | **Description** | **Qty** | **Address of Manufacture Premise for inspection** |
| 1 | Schedule – 2 | 45 Watt LED Fitting Street Light | 20 Nos | LUKER ELECTRIC TECHNOLOGIES PVT LTD  54, KRISHNARAYAPURAM THOTTA SALAI OLD COCHIN BYPASS ROAD  CHETTI PALAYAM, COIMBATORE – 641201  Mob: 9092552394 (Venkat Luker)  9987987223(Ajeet Karn)  9975085712 (Puransingh) |
| 2 | Schedule - 6 | 150 Watt LED Fitting Flood Light | 140 Nos |

Copy of ELS Kalyan specification of the above mentioned schedule items and LOA along with manufacture data sheet and test report is enclosed.

This is for your information and necessary action

**(Shri. Bhupesh Yadav)**

**ADEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

C/- M/s Tanya Electrical - Thane

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2016/25/AMC-SIV Date: 24.02.2024

**Sr.DEE (TRS) BSL**

Sub: C.A. No. ELSKYN.WKS.2016.25.AMC-SIV dated 05-10-2018 for “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) fitted in conventional locomotives as per RDSO's SMI No.RDSO/2016/EL/SMI/0291 (Rev 0) for a period of 3 years at Electric Loco Shed, Kalyan, Ajni and Bhusaval”

Ref : (i) LOA no. ELSKYN/WKS/2016/25/ AMC-SIV dated 21.03.2018

(ii) This office letter of even no. dated 12.11.2022 & 17.08.2023

--\*\*--

Please connect this office letters cited at Ref. No. (ii) vide which it was requested to confirm the total payment amount released and the security deposit deducted from the on account bills along with any other balance recovery against this contract.

As the above contract was awarded by this shed, final payment is to be released by this office. The firm’s payment pertaining to ELS/KYN for one quarter is yet to be released. This shed will be able to release the same after getting the above information from your end. Firm is pressurizing hard for early clearance of their long pending payment.

In view of the above, you are once again requested to give confirmation of the final payment made from your end so that the final bill may be released, and the contract may be closed.

**(Shri. Shikhar Srivastava)**

**DEE (TRS) KALYAN**

**For Sr. DEE/TRS/KYN**

**Electric Loco Shed/KYN/CR**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELSKYN/WKS/2019/16/HIRECT SIV Date: 22.02.2024

**Sr.DEE (TRS) BSL**

Sub:- Extension of CA No.CR/BSL/Elect./2021/0011 dated 20-07-2021 for “Renewal of Annual Maintenance Contract (AMC) of HIRECT make SIV for the period of three years at Electric Loco Shed, Bhusawal / Kalyan.”

Ref: Your office LOA No.BHUSAWAL DIVISION- ELECTRICAL/ BSL-TRS-TENDER-2021-01/ 01029820032724 dtd. 27-02-2021

--\*\*--

A contract for the subject work was awarded to M/s Hind Rectifiers Limited- Mumbai, Lake Road, Bhandup West, Mumbai - 400 078 at a total cost of Rs.19,49,319 /- LOA No.BHUSAWAL DIVISION- ELECTRICAL/ BSL-TRS-TENDER-2021-01/ 01029820032724 dtd. 27-02-2021 with a completion period of three years i.e. up to 27.02.2024.

This office has initiated a new proposal for subject work which is currently with accounts for concurrence and vetting. The sanctioning of renewal proposal and its tendering process will take considerable time; hence it is requested to extend the subject work for minimum one quarter so that the healthiness of SIV can be ensured without interruption.

नीरज कुमार गर्ग

वरि०मंडल विद्युत् इंजिनियर

(क.च.स्टॉक)कल्याण

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/E-Tender Date: 07.02.2024

WAO (ELW) BSL

Sub:- IPAS access to process contractual bills for RSP item

--\*\*--

This office has to process bills of WAO (BSL), for this you are requested to create a IPAS user for officers whose details are as under:

1. Name : Shri ASHISH GUPTA
2. Designation : DEE-II TRS Kalyan
3. PF No. : 00729800383
4. Date of Birth : 15.05.1994
5. Mobile Number registered on IPAS : 8828119362
6. Email I/D : dee2trskyn@gmail.com

It is requested to allot ID and password in favour of above officer so that the bill can be processed to your office.

You are also requested to nominate following users as L-2 and L-3 for processing bills on IPAS

1. CR02EXE2031 Shri Udya Kumar SSE(W)TRS/KYN L-2
2. Shri Ashish Gupta DEE-II/TRS/KYN L-3

(Bhupesh Yadav)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/CCB Date: 02.02.2024

Sr.DME (D) Pune

Sub:- SMC Contract for CCB II Air Brake System valves, Make- KBIL

Ref:- Your office letter no.PA/MD/SMC/CCB II dated 19.01.2024

--\*\*--

In reference to your letter mentioned above, locomotives no. 39055, 39056, 39050 & 39047 transferred from ELS KYN are not covered in a SMC contract. However contract for repair/ overhauling of CCB-II Air brake system is in progress at this shed and quantity covered under this contract is required for locomotives getting due for IOH during year 2024-25.

This is for your kind information please.

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/MIsc. Date: 23.12.2022

ADRM/Admin

CSMT

CR

Sub:- Complaint received against M/s A1 facility & Services Pvt. Ltd.

Ref: Your office letter no.BB.ADRM(Admin)A.Admin/Misc/23 dated 02.11.2023

--\*\*--

In reference to your letter mentioned above, it is stated that there is no work awarded by ELS Kalyan on M/s A1 facility & Services Pvt. Ltd.

This is for your kind information please.

नीरज कुमार गर्ग

वरि०मंडल विद्युत् इंजिनियर

(क.च.स्टॉक)कल्याण

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/IR\_WCMS User Date. 27.11.2023

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

Please create IR-WCMS IDs for the DEE(TRS)Kalyan. Required particulars are as under:

|  |  |
| --- | --- |
| Name (in full) | ASHISH GUPTA |
| Designation | DEE-II (TRS) Kalyan |
| Date of Birth | 15.05.1994 |
| Mobile No./ CUG No. | 8828119362 |
| E-mail ID | dee2trskyn@gmail.com |
| Department | Electrical |
| IPAS ID | -- |
| IRPSM ID | -- |
| IREPS DETAILS |  |
| 1. IREPS Login ID | dee2trskyn@gmail.com |
| 1. User Name | ASHISH GUPTA |
| 1. Designation | DEE-II(TRS)KYN |
| 1. Department | Electrical |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed, Kalyan - 421 301 |
| Office Phone No. | 0251 6763120 |
| Employee Id | 00729800383 |

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/E-Tender Date: 23.12.2023

WAO (ELW) BSL

Sub:- IPAS access to process contractual bills for RSP item

--\*\*--

Shri G K Sharma, SSE (Works) retired on Oct- 2023 having IPAS I/D CR02EXE2031 for processing bills of WAO (BSL).

You are therefore requested to provide IPAS access of USER ID CR02EXE2031 to Shri Uday Kumar SSE (Works). The particulars of staff are as under:

1. Name : Shri Uday Kumar
2. Designation : SSE (W)/TRS/KYN
3. PF No. : 00229803555
4. Date of Birth : 10-02-1990
5. Mobile Number registered on IPAS : 08355830763
6. Email I/D : ssewk.elskyn@gmail.com

It is requested to allot ID and password in favour of above staff so that the bill can be processed to your office

(BHUPESH YADAV)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2022/IPAS Date. 22.11.2023

**AEDPM (T)**

**CSMT**

Sub: Creation of IPAS user ID

--\*\*\*--

Kindly create IPAS user for following officers of ELS Kalyan, the details are as under:

|  |  |  |  |
| --- | --- | --- | --- |
| Sr. No. | Particulars | DEE-I | DEE-II |
| 1 | Name | SHIKHAR SRIVASTAVA | ASHISH GUPTA |
| 2 | Designation | DEE-I(TRS)KALYAN | DEE-II(TRS)KALYAN |
| 3 | Mobile No. | 8828119321 | 8828119362 |
| 4 | Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| 5 | PF No. | 00729800412 | 00729800383 |

(BHUPESH YADAV)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/MIsc. Date: 22.11.2022

ADST/Kalyan

Sub:- Provision of Internet connection to SSE/Works section

--\*\*--

In works section of ELS/Kalyan a new system has been installed for that internet connection is required. This section works on various online portal IREPS, IR-WCMS, IPAS, GeM, E-office therefore internet access is utmost for day to day working. Also you are requested to make the IPs of all internet connection suitable for connecting systems in LAN. This is necessary for sharing data easily and avoiding multiple files creation.

You are requested to provide 01 Internet connection and make the IPs of all system suitable for LAN.

(BHUPESH YADAV)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

As per Para 1316 of Chapter III of Engineering code Assistant Engineer/ Div. Assistant Engineer are to be carried out Test Check of 20%. However in IRWCMS there is no provision of test check less than 100%. Please see the matter and do the necessary implementation. (Engineering code copy attached for reference)

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 26.10.2023

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no.ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to above referred contract a Joint note and penalty statement of four quarters i.e from 22.04.2022 to 21.04.2023 duly signed by ADEE/TRS/Klayan was sent to your office for passing payment as stated in your office letter mentioned at Ref.2.

Now CAMC work of AAL make SIV for 5th Qtr i.e from 22.04.2023 to 21.07.2023 has been carried out by firm as per LOA and scope of work satisfactorily.

Joint note and penalty statement of this quarter (5th Qtr) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end.

(SHUBHAM RADKE)

DEE/TRS/KALYAN

For Sr. DEE/TRS/KALYAN

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No. ELS KYN/WKS/2023/10/FDCS-Medha Date: 16.10.2023

**Sr.DEE (TRS) BSL**

Sub:- Submission of sanctioned estimate for “Annual Maintenance Contract of M/s Medha Make Microprocessor Based Control & Fault Diagnostic System (MPCS) Ver 2 of AC Conventional Locomotives as per RDSO’s SMI No.RDSO/2016/EL/SMI/0288 (Rev) for a period of 3 years at Electric Loco Shed, Kalyan, Qty- 07 Nos.”

Ref: Your office LOA No.BSL/TRS/Tender/2020/06/00987030024273 dated 20.08.2020

--\*\*--

Vide your office LOA mentioned under reference 06 Nos. of M/s Medha make MPCS of ELS Kalyan are covered under AMC. During quarter 5th, 7th loco was included in the existing contract. Therefore a fresh proposal for subject work for 07 Nos. MPCS at total cost of Rs.8,57,437.56 inclusive of 18% GST through Single Tender from OEM, has been sanctioned by ADRM/BB e-office note no.#16 dated 11.10.2023. Detailed estimate No.ELSKYN/WKS/2023/10 dated 18.07.2023 got sanctioned by Sr.DEE(TRS)KYN vide this office letter of even no. dated 12.10.2023.

It is requested to include ELS/KYN’s quantity in your tender. The details of locos to be covered are as under:

|  |  |  |
| --- | --- | --- |
| Sr. No. | Loco No. | MPCS No. |
| 1 | 27221 | 1978 |
| 2 | 27287 | 2193 |
| 3 | 27254 | 1959 |
| 4 | 27265 | 1960 |
| 5 | 28559 | 1628 |
| 6 | 27277 | 1956 |
| 7 | 27257 | 2036 |

Following documents are sent herewith for further action:

1. Copy of Sr.DFM/CSMT’s concurrence letter No.BB/AC/FX-I/10104095 dtd.29.09.2023 (E-office concurrence)

2. Copy of ADRM/BB’s sanction for AMC on single tender basis with OEM vide this office note of even no. dated 06.10.2023. (Through E-office)

3. Sanctioned Detailed Estimate No.ELSKYN/WKS/2023/10 dated 18.07.2023 vide office note of even no. dated 12.10.2023.

You are requested to include above MPCS of ELS/ Kalyan in new AMC for the subject work.

(SHUBHAM RADKE)

DEE/TRS/KALYAN

For Sr. DEE/TRS/KALYAN

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**No. ELSKYN/WKS/2022/29/TM Stator DATE:- 16.10.2023**

**SMM**

**Office of PCMM**

**PLW, Patiala**

**Punjab**

**Subject:** Confirmation of documents submitted by firm in this office Tender

No.ELSKYNWKS22-29-TMStator-A opened on 23.08.2023

**Ref:** 1.PO No.02192652100275 dated 31.01.2020

--\*\*--

This office has invited a tender no.ELSKYNWKS22-29 for the work “Mechanical repair / rehabilitation of Hitachi traction motor stators (type HS-15250A) of Electric locomotives, Qty: 50 Nos.” and opened on 23.08.2023. Against this tender M/s Saini Electrical and Engineering- Navi Mumbai has uploaded PO copy mentioned under reference along with receipt notes in support to minimum technical eligibility criteria.

Following information is necessary for evaluation of said tender’s technical eligibility.

1. Is M/s Saini Electricals and Engineering- Navi Mumbai manufacturer of the TM type HS 15250 supplied by them against PO No. 02192652100275 dated 31.02.2020.?

2. Whether M/s Saini Electricals and Engineering- Navi Mumbai has completed the PO quantity or is under progress. If under progress please provide percentage of PO executed. Please provide any completion certificate issued against this PO.

3. Total payment made against this PO.

Information sought above will be helpful to evaluate technical credential of M/s Saini Electrical and Engineering- Navi Mumbai. It is therefore requested to please reply to this letter and sent on email [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) at the earliest.

|  |
| --- |
| (SHUBHAM RADKE)  DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |
|  |

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/2020/21/Medha/SIV/HLC Date. 04.10.2023

**Post Commander**

**RPF Kalyan Loco**

Sub: Work Permission at Electric Loco Shed Kalyan for carrying out Annual Maintenance Contracts and for attending warranty failures of different equipment of Electric Locomotives.

Ref : (i) LOA No. ELSKYNWKS-2020-21-AMC-SIV/00987030036441 dated 04.06.2021

valid up to 03.06.2024

(ii) LOA No. ELSKYNWKS-2021-31-MEDHA HLC/00987030060213 dated 18.08.2022

valid up to 17.08.2025

(iii) LOA No. BSL/TRS/TENDER/2020/06/00987030024273 dated 20.08.2020

Valid up to 08.12.2023

--\*\*--

Following employees deputed by M/s Medha Servo Drives Pvt. LTD, Hyderabad are permitted to work at ELS Kalyan for carrying out Annual Maintenance Contract against the above referred LOAs and other warranty related works at Electric Loco Shed, Kalyan round the clock all working days including Sundays and holidays up to 17.08.2025:

|  |  |  |  |
| --- | --- | --- | --- |
| Sr. No. | Name | Employee Code | AADHAR No |
| 1. | Mr. Sarang Bhagwat | 904363 | 7609 5744 3766 |
| 2. | Mr. Shubham Magdum | 906389 | 4459 9495 1083 |
| 3. | Mr. Aniket Kajale | 906391 | 7015 1054 2778 |
| 4. | Mr. Anil Yadav | 907283 | 5455 6415 2994 |

Above employees have provided copies of their Police Verification and Medical Certificate (Mr. Shubham Magdum Police verification application form) same are attached herewith for your reference.

**ADEE/TRS/KYN**

**For Sr. DEE (TRS) Kalyan**

Copy to: M/s Medha Servo Drives Pvt. LTD, Hyderabad

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**ELSKYN/PEX/SIEMENS/AMC/22/02 DATE:- 02.09.2023**

**Sr. DEE/TRS**

**BHUSAWAL**

**SUBJECT: Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan**

**REFERENCE:**

1. LOA No. BSL/TRS/Tender/2017/06 dated 07.06.2017 and Amendment 1 dated 08.09.17 and extension of completion period letter dated 19.11.2020 and Second Quantity variation and extension of completion period dated 10.02.21 and Third variation letter dated 06.05.21
2. This office letter no. of even no. dated 23.01.2023
3. ELS/BSL Letter No. BSL/TRS/Tender/2017/06 dated 03.03.2023

--\*\*--

In reference to your office letter mentioned at Ref.3, it is already stated in this office letter of even no. dated 23.01.2023 that the no. of executed loco days in 13th quarter is 1060 loco days. During this quarter 03 locos (27207, 27264 & 27266) has been received from ELS/AQ vide letter no.L.253.AC.118 dated 08.01.2021. These locos are handed over to firm from the date 08.01.2021. However in the Joint note for 13th quarter dated 05.03.2021 only the details of locos whose schedule inspection carried out during this period are mentioned instead of all loco covered under AMC i.e 13 Nos.

Information as sought in your office letter mentioned at Ref.3 is attached as Annexure-I. Total utilized loco days during 13th Qtr- 1060 Loco Days, 14Th Qtr- 1157 Loco Days & during Last month- 403 Loco Days are same as stated earlier in this office letter of even no. dated 23.01.2023.

This is for your information and necessary action please.

|  |
| --- |
| (SHUBHAM RADKE) DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

**Annexure-A**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **SIEMENS SIV AMC DETAILS FROM 01.11.2020 TO 07.06.2021** | | | | | | | |
| **Sr. No.** | **Qtr No.** | **Period** | | **Loco No.** | **Handover date** | **Executed Loco days in Shed** | **Remarks** |
| **From** | **To** |
| 1 | QTR 13 | 11/1/2020 | 2/7/2021 | 27101 | 10/8/2019 | 99 |  |
| 2 | 11/1/2020 | 2/7/2021 | 27207 | 1/8/2021 | 31 | Loco transferred from ELS/EQ on date 08.01.2021, hence handed over for AMC from date 08.01.2021 |
| 3 | 11/1/2020 | 2/7/2021 | 27264 | 1/8/2021 | 31 |
| 4 | 11/1/2020 | 2/7/2021 | 27266 | 1/8/2021 | 31 |
| 5 | 11/1/2020 | 2/7/2021 | 27218 | 4/2/2018 | 99 |  |
| 6 | 11/1/2020 | 2/7/2021 | 27239 | 9/4/2019 | 99 |  |
| 7 | 11/1/2020 | 2/7/2021 | 27304 | 2/25/2019 | 99 |  |
| 8 | 11/1/2020 | 2/7/2021 | 27352 | 9/4/2018 | 99 |  |
| 9 | 11/1/2020 | 2/7/2021 | 27367 | 12/4/2019 | 99 |  |
| 10 | 11/1/2020 | 2/7/2021 | 27374 | 10/17/2019 | 99 |  |
| 11 | 11/1/2020 | 2/7/2021 | 27407 | 9/4/2019 | 99 |  |
| 12 | 11/1/2020 | 2/7/2021 | 27408 | 11/13/2018 | 99 |  |
| 13 | 11/1/2020 | 2/7/2021 | 27418 | 11/24/2020 | 76 |  |
| **Loco days for Qtr 13** | | | | | | **1060** |  |
| 1 | QTR 14 | 2/8/2021 | 5/7/2021 | 27101 | 10/8/2019 | 89 |  |
| 2 | 2/8/2021 | 5/7/2021 | 27207 | 1/8/2021 | 89 |  |
| 3 | 2/8/2021 | 5/7/2021 | 27218 | 4/2/2018 | 89 |  |
| 4 | 2/8/2021 | 5/7/2021 | 27239 | 9/4/2019 | 89 |  |
| 5 | 2/8/2021 | 5/7/2021 | 27264 | 1/8/2021 | 89 |  |
| 6 | 2/8/2021 | 5/7/2021 | 27266 | 1/8/2021 | 89 |  |
| 7 | 2/8/2021 | 5/7/2021 | 27304 | 2/25/2019 | 89 |  |
| 8 | 2/8/2021 | 5/7/2021 | 27352 | 9/4/2018 | 89 |  |
| 9 | 2/8/2021 | 5/7/2021 | 27367 | 12/4/2019 | 89 |  |
| 10 | 2/8/2021 | 5/7/2021 | 27374 | 10/17/2019 | 89 |  |
| 11 | 2/8/2021 | 5/7/2021 | 27407 | 9/4/2019 | 89 |  |
| 12 | 2/8/2021 | 5/7/2021 | 27408 | 11/13/2018 | 89 |  |
| 13 | 2/8/2021 | 5/7/2021 | 27418 | 11/24/2020 | 89 |  |
| **Loco days for Qtr 14** | | | | | | **1157** |  |
| 1 | Last Month | 5/8/2021 | 6/7/2021 | 27101 | 10/8/2019 | 31 |  |
| 2 | 5/8/2021 | 6/7/2021 | 27207 | 1/8/2021 | 31 |  |
| 3 | 5/8/2021 | 6/7/2021 | 27218 | 4/2/2018 | 31 |  |
| 4 | 5/8/2021 | 6/7/2021 | 27239 | 9/4/2019 | 31 |  |
| 5 | 5/8/2021 | 6/7/2021 | 27264 | 1/8/2021 | 31 |  |
| 6 | 5/8/2021 | 6/7/2021 | 27266 | 1/8/2021 | 31 |  |
| 7 | 5/8/2021 | 6/7/2021 | 27304 | 2/25/2019 | 31 |  |
| 8 | 5/8/2021 | 6/7/2021 | 27352 | 9/4/2018 | 31 |  |
| 9 | 5/8/2021 | 6/7/2021 | 27367 | 12/4/2019 | 31 |  |
| 10 | 5/8/2021 | 6/7/2021 | 27374 | 10/17/2019 | 31 |  |
| 11 | 5/8/2021 | 6/7/2021 | 27407 | 9/4/2019 | 31 |  |
| 12 | 5/8/2021 | 6/7/2021 | 27408 | 11/13/2018 | 31 |  |
| 13 | 5/8/2021 | 6/7/2021 | 27418 | 11/24/2020 | 31 |  |
| **Loco days for Qtr 15** | | | | | | **403** |  |

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**ELSKYN/WKS/2020/17/AMC SIV Siemens DATE:- 02.09.2023**

**Sr. DEE/TRS**

**BHUSAWAL**

**Subject:** Annual Maintenance Contract of Siemens make SIV for the period of three

year at Electric Loco Shed, Bhusawal/Ajni/Kalyan

**Ref:** 1.LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL – TRS – TENDER – 2021 -02 / 00857060036611 dated 08.06.2021

2. Your office letter no.BSL/TRS/Tender/2021/02 dated 11.07.2023

--\*\*--

The AMC of 14 Nos. Siemens make SIV at Electric Loco Shed, Kalyan for a period of 3 years has been started from 08.06.2021 vide Joint Note No.ELSKYN/PEX/JN/SIEMENS/SIV/CAMC/21-22/1 dated 08.06.2021. Further vide Joint No.ELSKYN/PEX/JN/SIEMENS/SIV/HO/AMC/22-23/1 dated 30.01.2021, 04 locos are handed over to firm for AMC (03 Nos. w.e.f 13.01.2023 and 01 No. w.e.f 24.01.2023).

As stated in your office letter mentioned at Ref.2, Joint note and Penalty statement of each quarter from the period 08.06.2021 to 07.06.2023 (i.e 8 Qtrs) duly signed by DEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

|  |
| --- |
| (SHUBHAM RADKE) DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2020/29/MPCS Date: 01.08.2023

**Sr.DEE (TRS) BSL**

Sub:- Annual Maintenance contract (AMC) of M/s. Medha make MPCS (FDCS) at Electric

loco shed, Bhusawal, Kalyan.

Ref:- 1. LOA No. BHUSAWAL DIVISION-ELECTRICAL / BSL-TRS-TENDER-2020-

06 / 00987030024273 dated 20.08.2020

2. Your office letter no.BSL/TRS/Tender/2016/08 dated 15.06.2021.

3. Your office letter No.BSL/TRS/Tender/2020/06 dated 24.07.2023

--\*\*--

With reference to your office letter at Ref.2 an AMC of Medha make MPCS (FDCS) at Electric Loco Shed, Kalyan for a period of 3 years has been started from 09.09.2020. Vide Joint Note No.ELS/KYN/I&E/Medha/MPCS dated 16.06.2021 date of handover of 06 locos was revised and 06 locos are handed over to M/s Medha for subject mentioned work. Vide Joint No.ELS/KYN/I&E/MEDHA/FDCS/02/10 dated 29.10.2021 one more loco added in the subject AMC from dated 29.10.2021.

Summary of AMC work carried out by firm during the period 09.09.2020 to 08.06.2023 i.e 11 Qtrs is as under:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Qtr No. | AMC Period | No. of Locos | Date of Joint Note | No. Loco Days. | Downtime in Hrs. |
| 1 | 09.09.2020 to 08.12.2020 i.e 91 Days | 06 | 09.07.2021 | 546 | 00 Hrs. |
| 2 | 09.12.2020 to 08.03.2021 i.e 90 Days | 06 | 09.07.2021 | 540 | 00 Hrs. |
| 3 | 09.03.2021 to 08.06.2021 i.e 92 Days | 06 | 09.07.2021 | 552 | 00 Hrs. |
| 4 | 09.06.2021 to 08.09.2021 i.e 92 Days | 06 | 21.10.2021 | 552 | 00 Hrs. |
| 5 | 09.09.2021 to 08.12.2021 i.e 91 Days (7th Loco- from 29.10.21 | 07 | 23.12.2021 | 587 | 00 Hrs. |
| 6 | 09.12.2021 to 08.03.2022 i.e 90 Days | 07 | 23.03.2022 | 630 | 00 Hrs. |
| 7 | 09.03.2022 to 08.06.2022 i.e 92 Days | 07 | 23.06.2022 | 644 | 00 Hrs. |
| 8 | 09.06.2022 to 08.09.2022 i.e 92 Days | 07 | 20.09.2022 | 644 | 00 Hrs. |
| 9 | 09.09.2022 to 08.12.2022 i.e 91 Days | 07 | 11.01.2023 | 637 | 27 Hrs. |
| 10 | 09.12.2022 to 08.03.2023 i.e 90 Days | 07 | 27.03.2023 | 630 | 00 Hrs. |
| 11 | 09.03.2023 to 08.06.2023 i.e 92 Days | 07 | 25.07.2023 | 644 | 00 Hrs. |
|  |  | **Total No. of Loco days** | | **6,606** |  |

AMC work of Medha make FDCS for 11 Qtrs i.e from 09.09.2020 to 08.06.2023 has been carried out by firm as per LOA and scope of work satisfactorily.

As stated in your office letter mentioned at Ref.3, Joint note and downtime calculation sheet of each quarter (11 Qtrs) duly signed by ADEE/TRS/Klayan are sent herewith for further necessary action at your end. Necessary debit will be accepted against the passing of bills.

(ASHISH GUPTA)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/IR\_WCMS User Date. 14.07.2023

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

Please create IR-WCMS IDs for the DEE(TRS)Kalyan. Required particulars are as under:

|  |  |
| --- | --- |
| Name (in full) | SHUBHAM SUHAS RADKE |
| Designation | DEE (TRS) Kalyan |
| Date of Birth | 12.10.1994 |
| Mobile No./ CUG No. | 8828119321 |
| E-mail ID | deetrs.elskyn@gmail.com |
| Department | Electrical |
| IPAS ID | -- |
| IRPSM ID | -- |
| IREPS DETAILS |  |
| 1. IREPS Login ID | deetrs.elskyn@gmail.com |
| 1. User Name |  |
| 1. Designation | DEE(TRS)KYN |
| 1. Department | Electrical |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed, Kalyan - 421 301 |
| Office Phone No. | 0251 6763112 |
| Employee Id | 00729800326 |

**DEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/17/AMC SIV Siemens Date: 11.07.2023

**Sr.DEE (TRS) BSL**

Sub:- Annual Maintenance contract of Siemens make SIV for the period of three years at Electric loco shed, Bhusawal/ Ajni / Kalyan.

Ref: 1. LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL-TRS-TENDER-2021-02

/00857060036611 dated 08.06.2021

2. Your office letter No.L.No.BSL/TRS/Tender/2021/02 dated 11.07.2023

--\*\*--

With reference to above, a work contract for the subject work awarded to M/s Siemens Ltd., Navi Mumbai by your office. In this contract 11 Nos. Siemens make SIVs of ELS Kalyan are covered (Ref 1). Meanwhile 03 Nos. SIVs of Siemens make are transferred from ELS/AQ to ELS/KYN (Ref.2). These SIVs are also covered in subject contract hence total 14 Nos. Siemens make SIVs of ELS Kalyan are covered in subject contract.

Now, 02 Nos. SIVs are out of warranty and 01 No. SIV warranty will be due in Dec-2022 as detailed below:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Sr. No. | Loco No. | SIV Sr. No. | SIV DOC. | Warranty Expiry date | Warranty Status |
| 1 | 27117 | STB8M1035 | 30-12-2020 | 29-12-2022 | Under Warranty |
| 2 | 27121 | STB2H0961 | 02-03-2021 | 05-08-2018 | Out of warranty  (Old SIV which was kept on shop floor, fitted on loco during MTR at Dahod on 02.03.2021) |
| 3 | 27126 | STB1H0953 | 17-06-2020 | 16-06-2022 | Out of warranty |

Hence you are requested to include 03 Nos. Siemens make SIVs in the existing contract, and inform this office since when these SIVs can be handed over to firm.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/GeM User Date. 12.07.2023

**DyCMM (S)**

**HQ/CR**

Sub: Creation of Buyer Account on Government E-Market Place (GeM)

--\*\*\*--

With reference to above, following officer is already a user on GeM portal is now nominated for registration on Government E-market place (GeM) as a buyer, his particulars are as under:

|  |  |
| --- | --- |
| Name (in full) | Shri Shubham Radke |
| Designation | DEE (TRS) Kalyan |
| E-mail (only “gov.in” domain | [deetrskyn@bb.railnet.gov.in](mailto:deetrskyn@bb.railnet.gov.in) |
| Mobile No./ CUG No. | 8828119321 |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan – 421 301 |
| Office Phone No. | 0251 6763110 |
| Employee Id | 00729800326 |
| GeM Id | deetrskyn.cr |
| Role | Buyer |

नीरज कुमार गर्ग

वरि०मंडल विद्युत् इंजिनियर

(क.च.स्टॉक)कल्याण

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/Parliament-2023 Date. 26.06.2023

**Sr.DPO/BB**

**Mumbai CSMT**

Sub: Study Visit of Department- related Parliamentary Standing Committee on Labour, Textile & Skill Development to Bhubaneswar and Pune from 01.07.2023 to 04.07.2023 reg..

Ref: GM’s Office Letter No.G.197/02/2023/Committees dated 23.06.2023

--\*\*\*--

In reference to above letter, required information is furnished as under:

1. What are the Activities that are outsourced in the department. The details of contract to be provided in format in Annex- A.

Ans: There is no labour based contractual work running in ELS Kalyan. However outsourced contract on Outcome & Activity basis is as under.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Activity / Nature of work outsourced | Whether Labour / Activity based | No. of labours engaged | Whether details entered in Shramik Kalyan Portal (Yes/No) | Whether Contractor Registered/ Unregistered | Biometric attendance compulsory or otherwise | Employed directly or through contractor |
| 1. | Maintenance and Up-keeping of ELS/ KYN, SMM office and Trip Sheds for a period of 2 years | Activity Based | 17 to 25 Variable based on quantum of work | Yes | Registered on Shramik Kalyan Portal. | Otherwise | Through Contractor |

|  |  |  |
| --- | --- | --- |
| **Qtn. No.** | **Questions** | **Answer** |
| 1 | What are the Activities that are outsourced in the department. The details of contract to be provided in format in Annex- A. | Above table |
| 2 | List of records like Muster Roll, wage register, deduction Register, Over Time register etc. which are being maintained to ensure the same in field units, division offices. | List of required records are available with consignee section. |
| 3 | What is the system enforced for ensuring timely payment of minimum wages, bonus, deduction of EPF/ESIC/Pension etc. by Contractor? | Monitored through the Shramik Kalyan Only. |
| 4 | What is the mechanism of payment of EPF and ESIC by the department? Whether payment is made by reimbursement after submission of actual payment document by contractor or it is all inclusive rates? | Contract is awarded with all inclusive rate. |
| 5 | What are the Documents insisted upon by the department from the contractor like bank account details of the contractual labourers, monthly EPF/ ESI deposit made, labour licenses etc. before processing the payment of bills to the contractors? | Wage report generated through Shramik Kalyan Portal. |
| 6 | What System is adopted in the department for addressal of payment related complaints/issues? | No complaints received till now. |
| 7 | Number of vigilance checks conducted to ensure compliance of provision of various labour laws and the action taken report (ATR) thereof? Amount of payment made and system improvement suggested after vigilance Check and its implementation status. | No. |
| 8 | Are cash payments allowed to be made to labour. If so, what is the system of witness by Railways officials? | No. |
| 9 | Has any contractor been black listed in last three years on account of irregularities in Payment practices? | No contractor has been black listed in last three years on account of irregularities in Payment practices. |
| 10 | What is the penalty levied on Biometric related payment? Is there any Clause for the provision of spare Biometric instrument in contracts? | Biometric System is not mandatory. |
| 11 | How many Inspections/Visits were conducted by Labour Enforcement Officers (RLC/ ALC) in last one year? Number of cases made and its resolution thereof. | No Inspection/ Visits were conducted by Labour Enforcement Officers in last one year./ As per their schedule. |
| 12 | What basic facilities viz. Uniform, canteen, restroom, drinking water and sanitation, medical, retirement benefits etc. are being provided to contract workers by Contractors as well as Railways? And system to ensure the provision of these facilities. | Basic facilities viz. canteen, restroom, drinking water and sanitation are provided by railway during their working hours. Other facilities are provided by the contractor. |
| 13 | What safety related provisions like personal protective gears, safety equipment etc. have been made in the contract and penalties thereof in case of non-compliance? | Necessary protective gear are provided by contractor. Penalty clause exist in contract agreement in case of non-compliance. |
| 14 | What innovative steps have taken for betterment of condition of workers? | Regular meetings are being taken with contractor for betterment of condition of workers. |
| 15 | a) Clauses in General Conditions of Contract (GCC) of service contract for the compliance of statutory labour laws and various other provisions to be highlighted by each Department. | Contracts are governed by GCC and all relevant clauses being adhered. |
|  | b) How is it being ensured that all the prescribed amenities under the Labour laws are given by the contractors to the labourers engaged by them? | It is being ensured by regular counselling of staff. There is a provision of complaint box for labours. |
| 16 | Has any contract been terminated due to non-compliance of extant labour laws in the last 3 years (Details to be supported from Statistics of Shramik Kalyan Portal/GeM). | Nil |
| 17 | Suggestions for improvement in implementation of labour laws, if any. | Nil |
| 18 | Specify existing Flow diagram in place in field units for checking /ensuring payment of minimum wages, ESIC payment, EPF and ensuring provision of safety related protective equipment/ gears etc. | LOA-Consignee Section- Timely execution of work- Payment to Labour (Monitored through Shramik Kalyan Portal)- Bill raised by contractor- Verification by Sr.SO WKS/CSMT- Payment to contractor |
| 19 | Photographs of labours in field with protective equipment/ gears and safety measures being adopted should be provided. | Ok |
| 20 | What are the facilities provided for staff working in running trains? | Not applicable |
| 21 | Any Special facilities provided for female staff? | Not applicable as no female staff is employed by contractor. |
| 22 | What are the social security schemes available for contract labours and how many labours are benefited by such schemes? What is the mechanism available for dealing with cases of deviation? | Not applicable |
| 23 | Provide Details of ‘As on date claims and their settlement under Workmen’s Compensation Act for on-going contracts’. | Nil |

This is for your information and necessary action.

नीरज कुमार गर्ग

वरि०मंडल विद्युत् इंजिनियर

(क.च.स्टॉक)कल्याण

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/Parliament-2023 Date. 24.06.2023

**CELE**

**CR/ CSMT**

**(Kind Attention: Shri G. C. Solanki, Dy CEE (EM)**

Sub: Study Visit of Department- related Parliamentary Standing Committee on Labour, Textile & Skill Development to Bhubaneswar and Pune from 01.07.2023 to 04.07.2023 reg..

Ref: GM’s Office Letter No.G.197/02/2023/Committees dated 23.06.2023

--\*\*\*--

In reference to above letter, required information is furnished as under:

1. What are the Activities that are outsourced in the department. The details of contract to be provided in format in Annex- A.

Ans: There is no labour based contractual work running in ELS Kalyan. However outsourced contract on Outcome & Activity basis is as under.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Activity / Nature of work outsourced | Whether Labour / Activity based | No. of labours engaged | Whether details entered in Shramik Kalyan Portal (Yes/No) | Whether Contractor Registered/ Unregistered | Biometric attendance compulsory or otherwise | Employed directly or through contractor |
| 1. | Maintenance and Up-keeping of ELS/ KYN, SMM office and Trip Sheds for a period of 2 years | Activity Based | 17 to 25 Variable based on quantum of work | Yes | Registered on Shramik Kalyan Portal. | Otherwise | Through Contractor |

1. List of records like Muster Roll, wage register, deduction Register, Over Time register etc. which are being maintained to ensure the same in field units, division offices.

Ans: List of required records are available with consignee section.

1. What is the system enforced for ensuring timely payment of minimum wages, bonus, deduction of EPF/ESIC/Pension etc. by Contractor?

Ans: Monitored through the Shramik Kalyan Only.

1. What is the mechanism of payment of EPF and ESIC by the department? Whether payment is made by reimbursement after submission of actual payment document by contractor or it is all inclusive rates?

Ans: Contract is awarded with all inclusive rate.

1. What are the Documents insisted upon by the department from the contractor like bank account details of the contractual labourers, monthly EPF/ ESI deposit made, labour licenses etc. before processing the payment of bills to the contractors?

Ans: Wage report generated through Shramik Kalyan Portal.

1. What System is adopted in the department for addressal of payment related complaints/issues?

Ans: No complaints received till now.

1. Number of vigilance checks conducted to ensure compliance of provision of various labour laws and the action taken report (ATR) thereof? Amount of payment made and system improvement suggested after vigilance Check and its implementation status.

Ans: No.

1. Are cash payments allowed to be made to labour. If so, what is the system of witness by Railways officials?

Ans: No.

1. Has any contractor been black listed in last three years on account of irregularities in Payment practices?

Ans: No contractor been black listed in last three years on account of irregularities in Payment practices.

1. What is the penalty levied on Biometric related payment? Is there any Clause for the provision of spare Biometric instrument in contracts?

Ans: Biometric System is not mandatory.

1. How many Inspections/Visits were conducted by Labour Enforcement Officers (RLC/ ALC) in last one year? Number of cases made and its resolution thereof.

Ans: No Inspection/ Visits were conducted by Labour Enforcement Officers in last one year./ As per their schedule.

1. What basic facilities viz. Uniform, canteen, restroom, drinking water and sanitation, medical, retirement benefits etc. are being provided to contract workers by Contractors as well as Railways? And system to ensure the provision of these facilities.

Ans: Basic facilities viz. canteen, restroom, drinking water and sanitation are provided by railway during their working hours. Other facilities are provided by the contractor.

1. What safety related provisions like personal protective gears, safety equipments etc. have been made in the contract and penalties thereof in case of non-compliance?

Ans: Necessary protective gear are provided by contractor. Penalty clause exist in contract agreement in case of non-compliance.

1. What innovative steps have taken for betterment of condition of workers?

Ans: Regular meetings are being taken with contractor for betterment of condition of workers.

1. a) Clauses in General Conditions of Contract (GCC) of service contract for the compliance of statutory labour laws and various other provisions to be highlighted by each Department.

Ans: Contracts are governed by GCC and all relevant clauses being adhered.

15. b) How is it being ensured that all the prescribed amenities under the Labour laws are given by the contractors to the labourers engaged by them?

Ans: It is being ensured by regular counseling of staff. There is a provision of complaint box for labours.

1. Has any contract been terminated due to non-compliance of extant labour laws in the last 3 years (Details to be supported from Statistics of Shramik Kalyan Portal/GeM).

Ans: Nil.

1. Suggestions for improvement in implementation of labour laws, if any.

Ans: Nil.

1. Specify existing Flow diagram in place in field units for checking /ensuring payment of minimum wages, ESIC payment, EPF and ensuring provision of safety related protective equipment/ gears etc.

Ans: LOA-Consignee Section- Timely execution of work- Payment to Labour (Monitored through Shramik Kalyan Portal)- Bill raised by contractor- Verification by Sr.SO WKS/CSMT- Payment to contractor

1. Photographs of labours in field with protective equipment/ gears and safety measures being adopted should be provided.

Ans: Ok

1. What are the facilities provided for staff working in running trains?

Ans: Not applicable

1. Any Special facilities provided for female staff?

Ans: Not applicable as no female staff is employed by contractor.

1. What are the social security schemes available for contract labours and how many labours are benefited by such schemes? What is the mechanism available for dealing with cases of deviation?

Ans: Not applicable

1. Provide Details of ‘As on date claims and their settlement under Workmen’s Compensation Act for ongoing contracts’.

Ans: Nil.

This is for your information and necessary action.

नीरज कुमार गर्ग

वरि०मंडल विद्युत् इंजिनियर

(क.च.स्टॉक)कल्याण

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2023/IR\_WCMS User Date. 12.06.2023

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

Please create IR-WCMS IDs for the ADEE(TRS)Kalyan-III. Required particulars are as under:

|  |  |
| --- | --- |
| Name (in full) | ASHISH GUPTA |
| Designation | ADEE (TRS) Kalyan |
| Date of Birth | 15.05.1994 |
| Mobile No./ CUG No. | 8828119362 |
| E-mail ID | adee3trs.elskyn@gmail.com |
| Department | Electrical |
| IPAS ID | -- |
| IRPSM ID | -- |
| IREPS DETAILS |  |
| 1. IREPS Login ID | adee3trs.elskyn@gmail.com |
| 1. User Name |  |
| 1. Designation | ADEE(TRS)KYN |
| 1. Department | Electrical |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed, Kalyan - 421 301 |
| Office Phone No. | 0251 6763116 |
| Employee Id | 00729800383 |

**ADEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

List of records like Muster Roll, wage register, deduction Register, Over Time register etc. which are being maintained to ensure the same in field units, division offices.

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 19.05.2023

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref:- 1. LOA No.ELS–AJNI-ELECTRICAL/ELS–AQ–DRG-WCQ–21–22-10/

00015970051944 dated 30.03.2022.

2. Your office letter no.ELS/AQ/DRG/WCQ/21-22/10 dated 02.03.2023

--\*\*--

With reference to above referred contract a CAMC of AAL make 180 KVA Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years has been started at ELS Kalyan from 22.04.2022. Vide Joint Note No. ELSKYN/PEX/JN/AAL/119/22-23 dated 22.04.2022, 09 locos are handed over to M/s AAL for subject mentioned work.

CAMC work of AAL make SIV for 04 Qtrs i.e from 22.04.2022 to 21.04.2023 has been carried out by firm as per LOA and scope of work satisfactorily.

As stated in your office letter mentioned at Ref.2, Joint note and penalty statement of each quarter (4 Qtrs) duly signed by ADEE/TRS/Klayan are sent herewith for further necessary action at your end.

(Nitish Kumar Shukla)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/MIsc. Date: 06.04.2023

CWM/ELW/BSL

Sub:- Warranty obligation for “Conversion & Up gradation (1500 AMP capacity) of BA Panels of Electric Locomotives, Qty. 9 Locomotives.’’

Ref: (i) LOA No. ELW/BSL/Tender/2017-18/14 dated 27/09/2017

(ii) This office letter no. ELS/KYN.ACE.FR.ELWBSL dtd. 04.12.2018

(iii) Your office letter no. BSL/ELW/Tender/2017-18/14 dated 03.04.2023

--\*\*--

Vide this office letter referred at Sr.No. (ii) , the warranty failure of reverser provided on loco No. 21869 was reported to your office. However joint inspection note for the same was not prepared as neither any representative of M/s Elco Enterprises nor from your office visited ELS/KYN for preparation of Joint Inspection Note.

Further the cost of warranty failure attended, as asked vide your letter referred at Sr.No.(iii), works out to be Rs 6,063/- as detailed in Note No.ELSKYN.ACE.FR.ELWBSL/08 dated 06.04.2023 (Copy enclosed). However other losses on account of said failure may please be confirmed from other respective department.

This is for your information and further action at your end.

(Nitish Kumar Shukla)

ADEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/Labour Contract/Rajya Sabha Date: 04-02-2023

Sr.DPO/ CSMT

Sub: Rajya Sabha Starred/ Unstarred Question No. U443 to be answered on 03.02.2023 regarding contract worker in Indian Indian Railways

Ref : (i) APO (Ruling & Court) /CSMT’s letter No.P/HQ/R/745/PQ Dy.No.443

dated 03.02.2023

(ii) Rly. Boards L. No. 2023/E (LL)/AT/CNR/01 dated 02.02.2023

--\*\*--

With reference to above correspondence, the required information pertaining to Electric Loco Shed, Kalyan is as below:

Department: Electrical

1. **Contract labourers engaged by railway contractors:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 |
| Nos. | 28 | 28 | 30 | 30 | 30 | 17 |

1. **Contract workers (other than labourers) engaged by railway contractors:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 |
| Nos. | 16 | 19 | 26 | 28 | 20 | 31 |

1. **Workers engaged on contract by Zonal Railways directly:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 |
| Nos. | --NIL-- | | | | | |

|  |
| --- |
| (**नीरज कुमार गर्ग)**  **वरि०मंडल** **विद्युत् इंजिनियर**  **(क.च.स्टॉक) कल्याण** |

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/Labour Contract/Rajya Sabha Date: 30-01-2023

CELE/ CSMT

Sub: Rajya Sabha Starred/ Unstarred Question Dy No. U443 regarding Vacant and Sanctioned Post in Indian Railways

Ref : (i) Your e-mail dated 30.01.2023

(ii) PCSC/RPF/ Mumbai CSMT’s letter No. CRX/CB/HQ-24/PQ-04/

RS/U443/2023 dated 27.01.2023

(iii) Rly. Boards L. No.2022/Sec (SPL)/120/09 Supp dtd 27.01.2023

--\*\*--

With reference to above correspondence, the required information pertaining to Electric Loco Shed, Kalyan is as below:

(b) Details of the number of contract workers hired by Indian Railways in the last

8 years, year wise:

**Details are as mentioned below:**

|  |  |  |  |
| --- | --- | --- | --- |
| Period | Zone | Number of contract workers hired | Remarks if any |
| A | B | C | D |
| 2014-15 | CR | 29 | There is no direct hiring of workers. These are the minimum workers mentioned in contract for “Up-keeping and maintenance of Electric Loco Shed, Kalyan” which is not loco maintenance activity and to be carried out from outside agency |
| 2015-16 | 28 |
| 2016-17 | 28 |
| 2017-18 | 28 |
| 2018-19 | 28 |
| 2019-20 | 30 |
| 2020-21 | 30 |
| 2021-22 | 30 |

(c) Has the number of contractor workers in Indian Railways increased in the last

few years :

**No. Presently no “Manpower based Contract” is in progress at Electric**

**Loco Shed, Kalyan and required services are carried out through**

**“Activity based contract”.**

|  |
| --- |
| (**नीरज कुमार गर्ग)**  **वरि०मंडल** **विद्युत् इंजिनियर**  **(क.च.स्टॉक) कल्याण** |

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com)  **GSTIN : 27AAAGM0289C2ZI** |

No: ELSKYN/WKS/2020/20/Up Keeping Date: 27.01.2023

**SSE (TRS/O)**

**Electric Loco Trip Shed,**

**Vidyavihar (C.Rly.)**

**Sub:** Maintenance & Up-Keeping of Electric Loco Shed Kalyan including SMM/ELS/KYN and Trip Sheds at CSMT, VVH, LNL & IGP for a period of two years.

Ref. (i) Your letter dated 14.01.2023

(ii) PCME’s letter No. L.531.P.15A dated 12.08.2021.

--\*\*--

With reference to your letter dated 14.01.2023, it is stated that in the previous service contract executed by M/s Panchal Majoor Kamgar Sahakari Sanstha Ltd. Kulgaon, Badlapur (W), three house keeping staff were specifically mentioned for VVH Trip Shed.

But new GeM Service Contract placed on M/s D.N.Virkar Engineers & Contractors, Kalyan for subject mentioned work is an **“Activity based contract”**  not a **“Manpower based contract”**. This contract is awarded as per GM’s obsevations circulated by Dy CEE(EMU) CSTM vide letter under reference at Sr.No.(ii).

However the contractor has been advised to put extra efforts to improve the cleanliness level at Vidyavihar Trip Shed.

**(Bhupesh Yadav)**

**ADEE(TRS) Kalyan**

**For Sr.DEE(TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No: ELSKYN/WKS/2016/25/AMC-SIV Date: 12.11.2022

**Sr.DEE (TRS) BSL**

Sub:- Contract Agreement No.ELSKYN/WKS/2020/21/Medha/AMC-SIV dated 05.08.2021 for the work of “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) for a period of three years as per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed, Kalyan, Bhusawal & Ajni

Ref: 1. LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-21-AMC-SIV/00987030036441

dated 04-06-2021

2. Your office letter no.BSL/TRS/Tender/Medha make SIV ELS KYN dated 11.11.2022

--\*\*--

In reference to your office letter mentioned at Ref.2, it is stated that the contract agreement for the subject work has already been processed through offline mode. For the billing purpose contract agreement again prepared online on IR-WCMS portal. But as stated by CRIS through email from crisadmin dated 27.12.2022 “If consignees are of different division, then LOA cannot be processed in online mode”

Therefore the details of this contract are not visible to Bhusawal division.

This is for your information and necessary action.

|  |
| --- |
| (**नीरज कुमार गर्ग)**  वरि०मंडल विद्युत् इंजिनियर (क.च.स्टॉक) कल्याण |

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**ELSKYN/PEX/SIEMENS/AMC/22/02 DATE:- 23.01.2023**

**Sr. DEE/TRS**

**BHUSAWAL**

**SUBJECT: Annual Maintenance Contract of Siemens make SIV for the period of three year at Electric Loco Shed, Bhusawal/Ajni/Kalyan**

**REFERENCE:**

1. LOA No. BSL/TRS/Tender/2017/06 dated 07.06.2017 and Amendment 1 dated 08.09.17 and extension of completion period letter dated 19.11.2020 and Second Quantity variation and extension of completion period dated 10.02.21 and Third variation letter dated 06.05.21
2. ELS/BSL Letter No. BSL/TRS/Tender/2017/06 dated 16.09.2022

--\*\*--

In reference to your office letter mentioned at Ref.2 the number of actual loco days executed against the subject AMC at ELS Kalyan in respective quarters during the period from 01.11.2020 to 07.06.2021 is as under:

1. Till the end of 13th Quarter- 1060 Loco days
2. Till the end of 14th Quarter- 1157 Loco days
3. Till the end of last month- 403 Loco days

This is for your information and necessary action please.

|  |
| --- |
| (NITISH KUMAR SHUKLA) ADEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | Description: New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2021/IR\_WCMS User Date. 04.01.2023

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

Please create IR-WCMS IDs for the following officers. Required particulars are as under:

|  |  |  |
| --- | --- | --- |
| Name (in full) | NITISH KUMAR SHUKLA | BHUPESH YADAV |
| Designation | ADEE (TRS) Kalyan | ADEE (TRS) Kalyan |
| Date of Birth | 12.01.1994 | 05.07.1971 |
| Mobile No./ CUG No. | 8828119342 | 8828119343 |
| E-mail ID | adee1trs.elskyn@gmail.com | adee2trs.elskyn@gmail.com |
| Department | Electrical | Electrical |
| IPAS ID | -- | -- |
| IRPSM ID | -- | -- |
| IREPS DETAILS |  |  |
| 1. IREPS Login ID | adee1trs.elskyn@gmail.com | adee2trs.elskyn@gmail.com |
| 1. User Name |  |  |
| 1. Designation | ADEE(TRS)KYN | ADEE(TRS)KYN |
| 1. Department | Electrical | Electrical |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| Office Phone No. | 0251 6763116 | 0251 6763118 |
| Employee Id | 00729800318 | 00201934405 |

**ADEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2022/27/EOT AMT Date. 16.12.2022

**CME/PCM**

**COFMOW**

**Railway Office Complex**

**New Delhi – 110 002**

**E- Mail :- cmepcm@gmail.com**

Sub: Encashment of WBG/ Recovery of cost for repair work of machines.

Ref: Your office’s Note No. COFMOW/IR/M/Enc dated 31.05.2021

--\*\*\*--

Vide above mentioned note (copy enclosed), it is understood that encashment/ recovery of WBG for following consignee has been initiated.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.  No. | AT No. | Consi-  gnee | Machine | Supplier | Commiss-ioning | Advice | Ref |
| 12-13 | OP-2324 | KYN | EOT Cranes  (2 Nos.) | M/s AMT International | 29.08.2017 | Recovery  Rs 28,00,000/- | 9 |

Please furnish the details of above encashment/ recovery amount transferred to Central Railway to this office.

Further in above referred note, following suggestion was given to various consignees:

“As the COFMOW’s contract is closed now with the above recovery/ encashment of WB, you may continue to get this machine repaired at your end”.

Accordingly, this administration is going to repair/ recondition above 50/15 Ton EOT Cranes supplied by M/s AMT International, Mandi Gobindgarh from outside agencies through Revenue Expenditure.

(BHUPESH YADAV)

ADEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

Copy to :- CMM-I/CMM-II- COFMOW

:- Dy.CME (Plg) CSMT

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/Parliament-2022 Date. 10.12.2022

**Sr.DPO**

**CSMT**

Sub: Outsourcing employees

Ref: PCPO’s Office Letter No.P/HQ/R/745/PQ Dy.No.4197 dated 07.12.2022

--\*\*\*--

In reference to above letter it is stated that, not any employee outsourcing is being done at ELS/ Kalyan of Mumbai division.

(BHUPESH YADAV)

ADEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2021/IR\_WCMS User Date. 01.12.2022

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

It has is understood that now Revenue Bills are to be processed through IR-WCMS only. A list of Sr. Section Engineers deals with works contract along with necessary data is attached herewith.

You are requested to create their IR- WCMS IDs so that the works contract can be processed smoothly.

**(BHUPESH YADAV)**

**ADEE (TRS) Kalyan**

**For Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2021/IR\_WCMS User Date. 08.11.2022

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

It has is understood that now Revenue Bills are to be processed through IR-WCMS only. Please create ID to the undersigned giving **Co-Admin Login rights** on IR-WCMS. Required particulars are as under:

|  |  |
| --- | --- |
| Name (in full) | Shri NIRAJ KUMAR GARG |
| Designation | Sr.DEE (TRS) Kalyan |
| Date of Birth | 13.02.1985 |
| Mobile No./ CUG No. | 8828119305 |
| E-mail ID | [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |
| Department | Electrical |
| IPAS ID | DRNCJY |
| IRPSM ID |  |
| IREPS DETAILS |  |
| 1. IREPS Login ID | nirajgarg.186@gov.in |
| 1. User Name |  |
| 1. Designation | Sr.DEE(TRS)KYN |
| 1. Department | Electrical |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| Office Phone No. | 0251 6763110 |
| Employee Id |  |

**(Niraj Kumar Garg)**

**Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2016/25/AMC-SIV Date: 12.11.2022

**Sr.DEE (TRS) BSL**

Sub: C.A. No. ELSKYN.WKS.2016.25.AMC-SIV dated 05-10-2018 for “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) fitted in conventional locomotives as per RDSO's SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) for a period of 3 years at Electric Loco Shed, Kalyan, Ajni and Bhusaval”

Ref : LOA no. ELSKYN/WKS/2016/25/ AMC-SIV dated 21.03.2018

--\*\*--

A contract for the subject work covering quantity of 25 Nos. SIV (ELS/ KYN- 08 Locos, ELS/Bhusawal- 11 locos & ELS/AQ- 06 Locos) was expired on 16.06.2021 at ELS/AQ and was expired on 09.04.2021 at ELS/KYN and ELS/BSL.

Completion period for ELS/KYN and ELS/BSL was extended for one month each i.e up to 09.05.2021 in lieu of non execution of AMC work for 2 months at ELS/KYN in the month of May & June 2020 due to Covid- 19 Lockdown. Payment for the same will be processed by this office.

Since the fresh tender for subject work was under finalization, a variation in quantity for 19 loco months (ELS/KYN 08 loco months and ELS/BSL 11 loco months) has been done under variation clause. Payment for these 11 loco months is to be processed at your end as per variation statement and for 08 loco months of ELS/KYN will be processed by this office.

Now the subject contract has been completed and a fresh contract has also been awarded, a final bill is to be processed by this office.

It is therefore requested to kindly confirm whether final payment of your quantity has been passed from your end and also give the figures of final payment amount released & security deposit deducted from the bills against subject mentioned contract.

(SANJESH)

DEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2016/25/AMC-SIV Date: 12.11.2022

**Sr.DEE (TRS) AQ**

Sub: C.A. No. ELSKYN.WKS.2016.25.AMC-SIV dated 05-10-2018 for “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) fitted in conventional locomotives as per RDSO's SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) for a period of 3 years at Electric Loco Shed, Kalyan, Ajni and Bhusaval”

Ref : LOA no. ELSKYN/WKS/2016/25/ AMC-SIV dated 21.03.2018

--\*\*--

A contract for the subject work covering quantity of 25 Nos. SIV (ELS/ KYN- 08 Locos, ELS/Bhusawal- 11 locos & ELS/AQ- 06 Locos) was expired on 16.06.2021 at ELS/AQ and was expired on 09.04.2021 at ELS/KYN and ELS/BSL.

Now the subject contract has been completed and a fresh contract has also been awarded, a final bill is to be processed by this office, being LOA issuing authority.

It is therefore requested to kindly confirm whether final payment of your quantity has been passed from your end and also give the figures of final payment amount released & security deposit deducted from the bills against subject mentioned contract.

(SANJESH)

DEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2021/IR\_WCMS User Date. 08.11.2022

**Sr.DEE (G) CSMT**

**Admin (IR-WCMS (Elect.)**

Sub: Creation of Account on IR-WCMS

--\*\*\*--

It has is understood that now Revenue Bills are to be processed through IR-WCMS only. Please create ID to the undersigned giving Co-Admin Login rights on IR-WCMS. Required particulars are as under:

|  |  |
| --- | --- |
| Name (in full) | Shri NIRAJ KUMAR GARG |
| Designation | Sr.DEE (TRS) Kalyan |
| Date of Birth | 13.02.1985 |
| Mobile No./ CUG No. | 8828119305 |
| E-mail ID | [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |
| Department | Electrical |
| IPAS ID | DRNCJY |
| IRPSM ID |  |
| IREPS DETAILS |  |
| 1. IREPS Login ID | nirajgarg.186@gov.in |
| 1. User Name |  |
| 1. Designation | Sr.DEE(TRS)KYN |
| 1. Department |  |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| Office Phone No. | 0251 6763110 |
| Employee Id |  |

**(Niraj Kumar Garg)**

**Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/Misc Date. 12.10.2022

**ADRM/Admin**

**CSMT**

Sub: Information regarding dealing/ interface with Oracle Corporation

Ref: 1. Directorate Vigilance (Police) D.O. No.2022/DVP/Oracle dated 10.10.2022

2. SDGM & CVO Letter No.G.130/SDGM/Genl./2022/ dated 11.10.2022

.--\*\*\*--

With reference to your above mentioned letters, the position pertaining to Electric Loco Shed Kalyan may be treated as “Nil”.

(NIRAJ KUMAR GARG)

Sr.DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/2015/02 Date. 16.09.2022

**Sr.DEE(TRS) AQ**

Sub: Repairs, Reconditioning, Rehabilitation & Testing of 5400 KVA Aluminium

Foil type Transformers of WAG-7 loco of ELS/AQ & ELS KYN

* **Repairing of 03 Nos. 5400 KVA transformer of ELW/BSL.**

Ref: Your letter No. ELS/AQ/DRG/WCQ/18-19/14 dated 01.09.2022

--\*\*\*--

With reference to your above mentioned letter, it is confirmed that repairing as no foil type transformer is lying defective on shop floor at ELS/KYN, Qty of one No. transformer may be operated for ELW/BSL.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2017/10/ AMC/SIV AAL Date: 16.09.2022

**Sr.DEE (TRS) BSL**

Sub: C.A. No. L.253 A C/AMC/AAL-SIV dated 22.03.2019 (HQ) dated 22.03.2019

for “Comprehensive Annual Maintenance Contract (AMC) of AAL make 180

KVA Static Inverter (SIV) fitted in conventional locomotives of various electric

loco sheds of Central Railway (i.e ELS KYN, BSL & AJNI) for three years.”

Ref : Your letter No.BSL/TRS/Tender/AMC/AAL/SIV dated 03.08.2022

--\*\*--

Vide your above referred letter, it is stated that total bill amount of Rs 2,29,20,556/- was passed upto 12th quarter in 8th on A/c bill, but it is not cleared whether this is final payment or not.

ELS/KYN’s bills for last quarter of 9 SIVs from 22-01-2022 to 21-04-2022 is under passing at A/cs. Total amount for said AMC works out to be Rs 37,72,944/- at ELS/KYN.

As total bill amount to contractor has been exceeded to sanctioned amount for ELS KYN, A/cs is asking total bill passed at ELS/AQ and ELS/BSL to ensure that total bill amount is not exceeding to total contract value after variation.

It is therefore requested to kindly give the figures of final payment amount released from your end against subject mentioned contract.

(SANJESH)

DEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2022/16/CNC ATL Date: 30.08.2022

CWM/TMW/ NKRD

Sub:-Diversion of M&P Item i.e. CNC Axle Turning Lathe (Model SBCSN/40/3000,

on turnkey basis) including Concomitant Accessories -01 No.

* Shifting of machine from ELS/KYN to TMW/NKRD

Ref: (i) Your letter No.NK/TWM/DRG/534/PWP/2018-19 dated 29.04.2022

(ii) This office letter No. ELSKYN/TM/05 dated 21.06.2022

--\*\*--

Vide letter referred at Sr. No. (i), you have stated this office to make necessary arrangement for loading of lathe parts, transportation will be carried out by TMW/NKRD.

Accordingly arrangement for loading of machine was initiated by this shed and vide this office letter mentioned at Sr. No. (ii), it was intimated to your office that loading of machine will be arranged whenever transportation arrangement is made by TMW/NKRD.

It is once again stated that LOA for loading of machine at ELS/KYN has already been placed and loading arrangement will be provided immediately whenever you want to transport the machine to TMW/NKRD.

CME (PL)/ CSMT vide letter No. CR-HQ0MECH (MnP)/41/2021-O/o Dy CME (PLG)/MECH/HQ/CR dated 10.08.2022 requested to CELE/ CSMT to intervene in this matter so that machine is shifted from KYN TRS to TMW NK, installed and commissioned at the earliest. (Copy enclosed)

You are requested to shift the machine from ELS/KYN to TMW/NK RD at the earliest.

(Niraj Kumar Garg)

Sr. DEE (TRS) Kalyan

Copy : CELE/ CR/ CSMT } For kind information please.

: Dy.CME (PL) CSMT

}

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिoमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301. Email:srdeetrskyncrly@bb.railnet.gov.in |

No: ELSKYN/WKS/2017/10/ AMC/SIV AAL Date: 25.08.2022

**CELE/ Mumbai CST**

**Central Railway**

**(Kind Attention: Shri M.L.Vishnoi, Dy.CEE/EM/HQ)**

Sub :- LOA No.L.253.AC/AMC/AAL-SIV dtd 07.08.2018 for “Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA static inverter (SIV) fitted in conventional locomotives of various electric loco sheds of Central Railway (i.e. ELS/KYN, BSL & Ajni)

Ref:- Your office letter No.L.253.AC.AMC.AAL/SIV dated 13.07.2022.

--\*\*--

With reference to above cited letter, it is confirmed that CAMC of AAL make 180 KVA static inverter (SIV) has been successfully completed by M/s Autometer Alliance Ltd, Noida as per contract agreement. However, their bill for last two quarters is under verification and passing.

It is also confirmed that Railway have no claim balance from the contractor.

(SANJESH)

DEE/TRS/KYN

For Sr.DEE(TRS)KYN

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2017/10/ AMC/SIV AAL Date: 24.08.2022

**Sr.DFM/CSMT**

Sub: C.A. No. L.253 A C/AMC/AAL-SIV dated 22.03.2019 (HQ) dated 22.03.2019

for “Comprehensive Annual Maintenance Contract (AMC) of AAL make 180

KVA Static Inverter (SIV) fitted in conventional locomotives of various electric

loco sheds of Central Railway (i.e ELS KYN, BSL & AJNI) for three years.”

Ref: 1. ELS AQ Letter No.ELS/AQ/DRG/AMC-SIV-AAL(HQ-129) dated 30.7.2022

2. ELS BSL Letter No.BSL/TRS/Tender/AMC/AAL/SIV dated 03.08.2022

--\*\*--

Contract for subject mentioned work awarded to M/s Autometer Alliance Ltd, Noida as per HQ’s C.A.No. L.253.AC/AMC/AAL-SIV dated 22-03-2019 has been completed at ELS/KYN.

The quantity of this contract was finally increased from 36 months to 42 months for 74 Nos. SIV vide HQ’s letter No.L.253.AC/AMC/AAL-SIV dated 19.10.2021. As per this letter total cost of contract has become Rs 4,81,65,712/- ( Rs 4,08,18,400/- + Rs 73,47,312/- (GST).

Against this contract following payment are passed as confirmed by ELS AQ and ELS/BSL vide letters mentioned under reference.

1. By ELS/AQ - Rs.1,48,21,521.83 (Including 18% GST)
2. By ELS/BSL - Rs.2,29,20,556.00 (Including 18% GST)
3. By ELS/KYN Rs.44,52,073.92 (Including 18% GST)

Up to IXth Bill - Rs.30,63,744 /-

Xth Bill - Rs. 3,54,600 /-

XIth Bill - Rs. 3,54,600 /-

Total Final Amount- Rs.37,72,944 /-

Total Amount with IGST 18%- Rs.44,52,073.92

1. Grand Total - Rs.4,21,94,151.75 (Including 18% GST)

Revised contract value of subject contract is Rs.4,81,65,712 /- against which Rs.4,21,94,151.75 payment has been passed. Thus payment passed against subject contract is not exceeding revised contract value after variation.

It is therefore requested to kindly process the Xth and XIth bills of M/s AAL which are already sent to your office for verification and budget.

ADEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2022/16/CNC ATL Date: 05.08.2022

CWM/TMW/ NKRD

Sub:-Diversion of M&P Item i.e. CNC Axle Turning Lathe (Model SBCSN/40/3000,

on turnkey basis) including Concomitant Accessories -01 No.

* Shifting of machine from ELS/KYN to TMW/NKRD

Ref: (i) Your letter No.NK/TWM/DRG/534/PWP/2018-19 dated 29.04.2022

(ii)This office letter No. ELSKYN/TM/05 dated 21.06.2022

--\*\*--

Please connect this office letter cited at Sr.No. (ii) vide which it was stated that loading arrangement of machine at ELS/KYN is in advance stage of finalization,

In this regard, it is stated that LOA for loading arrangement of machine at ELS/KYN will be issued upto 15.08.2022.

It is requested to arrange necessary transportation of machine from ELS/KYN to TMW/NKRD and intimate this office one day prior to lifting so that loading of machine can be arranged.

concurrence and sanction

With reference to your above cited letter at Sr.No.(i), the expenditure occurred in attending the defect of Tap Changer Sr.No. TCP-19050011-03 of loco No.21932 on 07-10-2019 by this shed’s staff works out to Rs 436.50 say Rs 437.00.

This is for your information and further action at your end.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com)  **GSTIN : 27AAAGM0289C2ZI** |

No: ELSKYN/WKS/2022/Misc/HQ Date: 05.08.2022

**ADRM (Sub) BB**

Sub: Action plan for reduction in AMC Contracts/ Expenditure during the current year.

Ref. Your letter No.BB/ADRM (Sub)/Notes dated 04.08.2022

--\*\*--

As desired vide above mentioned letter, complete list of existing AMCs pertaning to Electric Loco Shed, Kalyan is enclosed as Annexure A. Action plan for achieving 30% reduction in the same during the FY 2022-23 is as given below:

**Action Taken/ Action Plan for achieving reduction in AMCs/ Expenditure during FY 2022-23**

1. OT has been reduced as detailed below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| OT Exp. during 2019-20 | OT Exp. during 2021-22 | Reduction in OT Exp | % reduction in OT | Remarks |
| Rs 73,75,980/- | Rs 8,71,457/- | **Rs.65,45,023/-** | **88.18%** | OT booked in 2021-22 is only for ART Staff. Further efforts are being taken to maintain zero OT in shed. |

1. **Contract for Maintenance and Up-keeping of Electric Loco shed Kalyan is awarded in May-2022 on activity basis, resulting saving in expenditure of Rs 29 Lakh per year (reduced from 1.24 Cr to 0.95 Cr per year) which is 23.39%**
2. Maintenance of Alstom make 85 Nos. SI Unit is being carried out **in-house** resulting saving of approx. **Rs 4.25 Cr per year towards AMC** (@ Rs 5 Lakh per SIV per year)
3. Two WAP/7 locos have been made HOG compliant. Due to this there is a saving of Rs 2.6 Crore per year (i.e. Rs 1.3 Cr. per loco per year) per year. Further in year 2022-23, four locomotives are planned to convert to Non- HOG to HOG compliant, that in-turn result into savings of **Rs.5.20 cr. approx**.**per year.**
4. **Cab AC being new item provided in recently received locos, no technical experts are available in shed. Hence AMC has been awarded. However possibility will be explored for making departmental staff conversant with maintenance of CAB AC to avoid AMC resulting saving of Rs 39.70 Lakh per year will be achieved.**

**(Bhupesh Yadav)**

**ADEE(TRS)Kalyan**

**For Sr.DEE(TRS) Kalyan**

**Central Railway, Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/17/AMC SIV Siemens Date: 04.08.2022

**Sr.DEE (TRS) BSL**

Sub:- Inclusion of additional SIVs in existing works contract vide LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL-TRS-TENDER-2021-02 /00857060036611 dated 08.06.2021 for the work of “Annual Maintenance contract of Siemens make SIV for the period of three years at Electric loco shed, Bhusawal/Ajni/Kalyan.

Quantity = 37 Nos.

Ref: 1. This office letter of even no. dated 12.12.2020

2. HQ’s letter No.L.253.AC.118 dated 08.01.2021

--\*\*--

With reference to above, a work contract for the subject work awarded to M/s Siemens Ltd., Navi Mumbai by your office. In this contract 11 Nos. Siemens make SIVs of ELS Kalyan are covered (Ref 1). Meanwhile 03 Nos. SIVs of Siemens make are transferred from ELS/AQ to ELS/KYN (Ref.2). These SIVs are also covered in subject contract hence total 14 Nos. Siemens make SIVs of ELS Kalyan are covered in subject contract.

Now, 02 Nos. SIVs are out of warranty and 01 No. SIV warranty will be due in Dec-2022 as detailed below:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Sr. No. | Loco No. | SIV Sr. No. | SIV DOC. | Warranty Expiry date | Warranty Status |
| 1 | 27117 | STB8M1035 | 30-12-2020 | 29-12-2022 | Under Warranty |
| 2 | 27121 | STB2H0961 | 02-03-2021 | 05-08-2018 | Out of warranty  (Old SIV which was kept on shop floor, fitted on loco during MTR at Dahod on 02.03.2021) |
| 3 | 27126 | STB1H0953 | 17-06-2020 | 16-06-2022 | Out of warranty |

Hence you are requested to include 03 Nos. Siemens make SIVs in the existing contract, and inform this office since when these SIVs can be handed over to firm.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2017/10/ AMC/SIV AAL Date: 29.07.2022

**Sr.DEE (TRS) AQ/ BSL**

Sub: C.A. No. L.253 A C/AMC/AAL-SIV dated 22.03.2019 (HQ) dated 22.03.2019

for “Comprehensive Annual Maintenance Contract (AMC) of AAL make 180

KVA Static Inverter (SIV) fitted in conventional locomotives of various electric

loco sheds of Central Railway (i.e ELS KYN, BSL & AJNI) for three years.”

--\*\*--

Contract for subject mentioned work awarded to M/s Autometer Alliance Ltd, Noida as per HQ’s C.A.No. L.253.AC/AMC/AAL-SIV dated 22-03-2019 has been completed at ELS/KYN.

The quantity of this contract was finally increased from 36 months to 42 months for 74 Nos. SIV vide HQ’s letter No.L.253.AC/AMC/AAL-SIV dated 19.10.2021. As per this letter total cost of contract has become Rs 4,81,65,712/- ( Rs 4,08,18,400/- + Rs 73,47,312/- (GST).

The sanctioned estimate for ELS Kalyan is for 4 Nos. SIVs at a total cost of Rs 25,80,000/-.

Now bills for last quarter of 9 SIVs from 22-01-2022 to 21-04-2022 was forwarded to A/cs for verification. Total amount for said AMC works out to be Rs 37,72,944/- at ELS/KYN.

As total bill amount to contractor has been exceeded to sanctioned amount for ELS KYN, A/cs is asking total bill passed at ELS/AQ and ELS/BSL to ensure that total bill amount is not exceeding to total contract value after variation.

It is therefore requested to kindly give the figures of total amount passed to M/s AAL Noida against subject mentioned contract from your end.

(SANJESH)

DEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELS KYN/WKS/HQ/Misc Date: 29.07.2022

**DRM (C) CSMT**

Sub:-Details of total number of Electrical Locomotives available in Mumbai Division.

Ref :-Your office letter No.BB.C.465.CP.TDR.TM.2022 dated 25.07.2022

--\*\*\*--

With reference to your above referred letter, it is stated that proposal for allotment of electric locomotive for branding purpose, has been sent to HQ of this office (PCEE’s Office) for necessary guidelines/ approval.

As soon as response is received from HQ, the same will be communicated to your office.

(SANJESH)

DEE (TRS) Kalyan

For Sr.DEE(TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELS KYN/WKS/HQ/Misc Date: 27.07.2022

**Dy.Chief Law Officer**

**CSMT**

Sub:-Legal vetting of draft charge sheet for banning of business with the firm

viz M/s N.M. Industries Kalyan.

Ref :-Dy.CVO/EL’s letter No.G.130/2020/09/00287/V6/V.Con dated 24.06.2022

--\*\*\*--

A works contract for “Supply, Erection of Safety Bracket on BP/FP Isolating Cock of WAG/9 locomotives was awarded to M/s N.M. Industries, 401, E-3, Kalptaru Co-op Hsg.Socity, Lok Udyan, Kalyan (W) at a total cost of Rs 4,73,121/- inclusive of all, vide this office letter of acceptance No. ELSKYN/WKS/2018/40/Safety Bracket dated 31.10.2018. (Pg 9-11)

As per para-No. 3.6 of scope of work, the contractor should have to submit Govt. approved lab test certificate of supplied material for necessary IS. The cost of laboratory testing should be borne by contractor.

The firm had submitted the material test certificates issued by “Reliable Testing Services, Andheri, Certificate No.18121023-A, 18121023-B, 18121023-C, 18121023-D dated 14.12.2018, on the basis of which supplied material was accepted by ELS/KYN. (Pg 5-8)

Later on the genuineness of these certificates was verified by vigilance office/CSMT from test certificate issuing agency i.e. Reliable Testing Services, Andheri and they found that all these certificates are forged. (Pg 1-4)

Dy CVO/EL CSMT vide letter No. G.130/2020/09/00287/V6/V.Con dated 24.06.2022 has submitted draft charge sheet and draft statement of article of charges framed against the above firm and stated to submit the same to Vigilance Office after approval of PHOD and duly vetted by Law Officer. (Pg 13-15)

In view of the above, it is requested to kindly accord legal vetting to the draft charge sheet so that approval of PHOD can be taken and case may be processed further.

Annexure 10.1 duly filled with available information is also enclosed herewith (Pg-16)

(Niraj Kumar Garg)

Sr.DEE(TRS) Kalyan

ANNEXURE – 10.1

Para 1023 (b)

SUSPENSION OF BUSINESS/ BANNING OF BUSINESS APPLICABLE TO RAILWAY MINISTRY, BANNING OF BUSINESS APPLICABLE TO ALL MINISTRIES

|  |  |
| --- | --- |
| Name of the firm & Address | M/s N.M. Industries,  401, E-3, Kalptaru Co-op Hsg.Socity,  Lok Udyan, Kalyan (W) |
| Constitution of the firm (Public Ltd./ Private Ltd./ Partner | Private Limited |
| Names of the Directors/ Partners/ Proprietors | Kusum Adyashankar Pandey (Proprietor) |
| Date of Registration on the Railways; and/ | Not available with this office |
| Whether registered with other Railways/ NSIC etc. | Not available with this office |
| Period for which action is proposed | 03 Years |
| Whether the proposed action will create difficulties in procurement of items such as spare parts for machinery for which the firm may be the sole supplier on proprietary basis. Also if the proposed action would dry up already limited sources of supply of any vital materials | No |
| Whether the firm has been removed from the list of approved suppliers | Not an approved supplier |
| Name (s) of the allied firms or sister concerns | Not available with this office |
| This has the personal approval of General Manager/ Head of Department |  |
| Head of Department | PCEE |

**Sr.DEE(TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/21/Medha/AMC-SIV Date: 14.07.2022

**Sr.DEE (TRS) BSL**

Sub:- Inclusion of additional SIVs in existing works contract vide LOA No. BHUSAWAL DIVISIONELECTRICAL/ BSL-TRS-TENDER-2021-02 /00857060036611 dated 08.06.2021 for the work of “Annual Maintenance contract of Siemens make SIV for the period of three years at Electric loco shed, Bhusawal/Ajni/Kalyan. Quantity-37 Nos.

--\*\*--

With reference to above, a work contract for the subject work awarded to M/s Siemens Ltd., Navi Mumbai by your office. In this contract 11 Nos. Siemens make SIVs of ELS Kalyan are covered.

Presently ELS/KYN shed is having 39 Nos. of SIV of various make. Out of these 39 SIVs, 17 Nos. SIVs are of Siemens make are now out of warranty are covered under subject AMC contract ofyour office has issued a LOA

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  रेल फ़ोन :- 010/63110  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Railway Phone :- 010/63110  Email :- [srdeetrs.elskyn@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

**ELSKYN/PEX/SIEMENS/AMC/22/02 DATE:- 15.07.2022**

**Sr. DEE/TRS**

**BHUSAWAL**

**SUBJECT: Discrepancies noticed in TV of Siemens make SIV CAMC work**

**REFERENCE:**

1. LOA No. BSL/TRS/Tender/2017/06 dated 07.06.2017 and Amendment 1 dated 08.09.17 and extension of completion period letter dated 19.11.2020 and Second Quantity variation and extension of completion period dated 10.02.21 and Third variation letter dated 06.05.21
2. ELS/BSL Letter No. BSL/TRS/CR/OTV dated 25.01.2021
3. Joint Note No. ELSKYN/PEX/JN/SIEMENS/AMC/22/01 DATE:-13.07.2022.
4. ELS/BSL Letter No. BSL/TRS/Tender/2017/06 dated 13.07.2022

--\*\*--

In reference to your letter referred at Ref. No.4, following clarifications are made.

|  |  |  |  |
| --- | --- | --- | --- |
| Sr.  No. | Quarters | ELS/BSL’s Queries/ Remarks | ELS/KYN’s Clarifications |
| 1. | QTR 10  (01.02.2020 to 30.04.2020) | As per Joint Note dated 01.09.2020, it is not cleared that from which date, the work was stopped due to lockdown | The work was stopped from 22.03.2020 to 30.04.2020 due to lockdown during this quarter.  Fresh Joint Note dated 13.07.2022 for not carrying out activities from 22.03.2020 to 30.07.2020 is enclosed. |
| 2. | QTR 11  (01.05.2020 to 31.07.2020) | As per Joint Note dated 01.09.2020, it is not cleared that from which date, the work was stopped due to lockdown | The work was stopped from 01.05.2020 to 30.07.2020 due to lockdown during this quarter.  Fresh Joint Note dated 13.07.2022 for not carrying out activities from 22.03.2020 to 30.07.2020 is enclosed.  Work was started from 31.07.2020 after lockdown |

This is for your information and necessary action please.

|  |
| --- |
| (SANJESH) DEE/TRS/KALYAN  For Sr. DEE/TRS/KALYAN |

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/21/Medha/AMC-SIV Date: 14.07.2022

**Sr.DEE (TRS) BSL**

Sub:- Variation in contract agreement no.ELSKYN/WKS/2020/21/Medha/AMC-SIV dated 05.08.2021 for the work of “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) for a period of three years as per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed, Kalyan, Bhusawal & Ajni

Ref: LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-21-AMC-

SIV/00987030036441 dated 04-06-2021

--\*\*--

This office intends to increase the quantity of SIV covered under subject contract as per the requirement of ELS/AQ and this shed. You are requested to convey your requirement so that the increase in quantity if any can be included in same variation. If no quantity is to be included from your side please also confirm the same.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com)  **GSTIN : 27AAAGM0289C2ZI** |

No: ELSKYN/WKS/2022/Misc Date: 02.07.2022

**ADRM (O) BB**

Sub: CAMC Proposals

Ref. Your letter No.BB/ADRM (O)/Notes dated 01.07.2022

--\*\*--

As desired vide above mentioned letter, details of CAMC contracts which are under going, on tender stage and proposed in prescribed format are as detailed below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| S.  No. | Name of Work | Cost/Approx cost | Status  Process/ Tender Stage/ Proposed | Whether HQ’s approval is obtained before entering into CAMC. Reference letter to be annexed. |
| 1 | CAMC of Medha make  Static Inverter (SIV) for a period of three years- 34 Nos. | 1,98,59,629/- 42,48,011/- (for ELS KYN) | Undergoing | ELS/KYN is nominated shed for Medha make SIV of all three sheds of KYN,BSL AQ vide HQ’s letter No.L.253. AC.AMC dated 23.07.2016 |
| 2 | CAMC of M/s AAL SIV, 36 Months | 5,06,56,817/-51,48,782/- (for ELS KYN) | Undergoing | ELS/AQ is nominated shed for AAL make SIV of all three sheds of KYN,BSL AQ vide HQ’s letter No. L.253. AC.AMC dtd 23.07.2016 |
| 3 | AMC of Siemens make SIV for the period of three years at ELS, BSL/AQ & KYN - 59 Nos. | 4,08,06,680/-  71,35,687/- (for ELS KYN) | Undergoing | ELS/BSL is nominated shed for Siemens make SIV of all three sheds of KYN,BSL AQ vide HQ’s letter No.L.253. AC.AMC dated 23.07.2016 |
| 4 | AMC of HIRECT make SIV for the period of three year at ELS Bhusawal/Kalyan- 12 Nos. | 77,97,255/-  17,40,769/- (for ELS KYN) | Undergoing | ELS/BSL is nominated shed for HIRECT make SIV of all three sheds of KYN,BSL AQ vide HQ’s letter No.L.253. AC.AMC dated 23.07.2016 |
| 5 | AMC of Medha make MPCS, Qty- 83 Locos, 3 years | 1,01,66,781/-  6,35,713/-  (for ELS KYN) | Undergoing | ELS/BSL is nominated shed for Medha make MPCS of all three sheds of KYN,BSL AQ vide HQ’s letter No.L.253. AC.AMC dated 23.07.2016 |
| 6 | CAMC of Medha make 2 X 500 KVA Hotel Load Conveter of WAP-7 loco for 3 years | 83,60,064/- | Tender Stage,  TOD – 07.07.2022 | Obtained vide e-office note No.#23 dated 14.03.2022 |
| 7 | CAMC of Siemens make 2 X 500 KVA Hotel Load Convetres in WAP-7 Locos for 3 years | 51,61,448/- | -do- | Obtained vide e-office note No.#33 dated 07.03.2022 |
| 8 | AMC of Cummins make 2 Nos. Diesel Engines of HS-SPART for 3 years | 32,22,330/- | -do- | Obtained vide Note No. L.253.AC.Outsourcing/sheds dated 27.12.2021. |
| 9 | CAMC of BHEL make IGBT Traction Converter & Auxiliary Converter of 3 phase loco for 3 years | 3,01,78,571/- | Tender Stage | Obtained vide e-office note No.#23 dated 14.03.2022 |
| 10 | CAMC of BHEL make Hotel Load Converter in WAP-7 loco for 3 years | 1,04,54,455/- | Proposal Stage | Under HQ’s approval |
| 11 | CAMC of BTIL make Traction Converters for 3 years | 1,13,19,150/- | Proposal Stage | Under HQ’s approval |

Copies of HQ’s approval as mentioned above are enclosed herewith.

**(Niraj Kumar Garg)**

**Sr.Divisional Electrical Engineer**

**(Traction Rolling Stock)**

**Central Railway, Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com)  **GSTIN : 27AAAGM0289C2ZI** |

No: ELSKYN/WKS/2020/20/Up Keeping Date: 09.05.2022

**SMM ELS Kalyan**

**Trip Sheds ELS Kalyan**

**CSMT, VVH, LNL and IGP**

**Sub:** Maintenance & Up-Keeping of Electric Loco Shed Kalyan including SMM/ELS/KYN and Trip Sheds at CSMT, VVH, LNL & IGP for a period of two years.

Ref. i. This office Gem Contract No. GEM-511687782760106 dated 06.05.2022

ii. Amendment No.1 to Gem Contract No. GEM-511687782760106 dated 06.05.2022

--\*\*--

A work contract for the subject work has been awarded to M/s D N Virkar Engineers and Contractor, 204, Usha Garden Society, Rambaug No.4 Kalyan 421301 at Rs.1,89,78,028.64 (Rupees One Crore Eighty- Nine Lakh Seventy- Eight Thousand Twenty Eight and Sixty- Eight Paisa only) as per Annexure-A inclusive of all taxes, duties, GST, transportation, labour charges (based on minimum wages rate as per Minimum Wages Act, 1948), consumable materials, machinery/ tool & tackles, statutory charges etc. for subject service from 08.05.2022 to 07.05.2024 against the GeM Contract at Ref i. and Amendment No.1 at Ref. ii.

A copy of contract and amendment to contract along with scope of work and all terms & condition is attached herewith for your reference and necessary action. SSE General section will co-ordinate the work at ELS/ Kalyan & SMM ELS Kalyan. Trip sheds work will be coordinated by the respective SSE In-charge.

**(Niraj Kumar Garg)**

**Sr.Divisional Electrical Engineer**

**(Traction Rolling Stock)**

**Central Railway, Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2022/IPAS Date. 05.05.2022

**AEDPM (T)**

**CSMT**

Sub: Creation of IPAS user ID

--\*\*\*--

Shri Uday Kumar SSE/ Drawing working under Works section of ELS/ Kalyan, deals with the online payment, Security Deposit, EMD passing activities.

You are requested to create the IPAS user for Shri Uday Kumar, the details as under:

1. Name - Shri Uday Kumar
2. Designation - SSE Drawing (TRS) Kalyan
3. Mobile No. - 08355830763
4. Office Address - Office of Sr. DEE (TRS), Electric Loco Shed,

Kalyan - 421 301

1. PF No. - 00229803555

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No. ELSKYN/WKS/2015/02 Date. 30.03.2022

**Sr.DEE(TRS) AQ**

Sub: Repairs, Reconditioning, Rehabilitation & Testing of 5400 KVA Aluminium

Foil type Transformers of WAG-7 loco of ELS/AQ & ELS KYN

* **Repairing of 03 Nos. 5400 KVA transformer of ELW/BSL.** ,

Ref: Your letter No.ELS/AQ/DRG/WCQ/18-19/14 dated 30.03.2021

--\*\*\*--

With reference to your above mentioned letter, it is confirmed that as no foil type transformer is lying defective on shop floor at ELS/KYN, Qty of one No. transformer may be operated for ELW/BSL.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2022/IPAS Date. 07.03.2022

**AEDPM (T)**

**CSMT**

Sub: Resetting of IPAS user ID

--\*\*\*--

The contact details of user id CR02EXE1051 has been changed. You are requested to update the details as under:

1. Name - Shri Sanjesh
2. Designation - DEE (TRS) Kalyan
3. Mobile No. - 09996688854
4. Office Address - Office of Sr. DEE (TRS), Electric Loco Shed,

Kalyan - 421 301

1. PF No. - 00729800243

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/MIsc. Date: 25.02.2022

CWM/ELW/BSL

Sub:- Extension of completion period for the work of “Provision of Conventional

Brake Rigging arrangement in 25 KV AC 3-phase Electric Locomotive

type WAG9 for high speed operations.

Ref: (i) Your letter No.BSL/ELWTender/2018-19/84 dated 07-02-2022

(ii) LOA No.ELW/BSL/Tender/2018-19/84 dated 07-08-2019

(iii) ELS/KYN’s letter No.ELS/KYN/BGE/17 dated 21-11-2021

--\*\*--

With reference to your above referred letter status of work executed by firm till date at ELS/KYN is as under:

* Four Nos. of spare bogies have been lifted by firm from ELS/KYN on 13-11-2021.
* Above bogies are under stage inspection at firm’s premises through ELS/LGD. Letter has already written by this shed to ELS/LGD for carrying out stage inspection.
* Expected time of completion of above quantity is upto 10-03-2022.

Please connect this office letter referred at Sr.No. (iii) vide which it was stated that only 07 Nos. of WAG-9 locos are left for conversion and overall 18 bogies (4 + 14) was supposed to be executed for ELS KYN through said contract.

Further above 07 Nos. WAG-9 locos have also been transferred to DLS/TKD. Now only 2 Nos. WAG-9 HC locomotives left with ELS/KYN in which conventional brake system already exists. As such 04 Nos. of bogies lifted from ELS/KYN and presently under stage inspection at firm’s premises are no more required to ELS/KYN.

It is understood that ELS/BSL has TBU/PBU type of WAG-9 locomotives in their holding. It is therefore proposed to transfer these 04 Nos.of conventional bogies frames to ELS/BSL. The firm has no objection to deliver said bogies to ELS/BSL in place of ELS/KYN.

As there is no loco balance for carrying out said work at ELS/KYN, completion period extension and loss to railway due to extension may please be viewed at your end. However as 4 spare bogies were given to firm for conversion, no loco is held up for want of these bogies, hence no loss is incurred.

(Sanjesh)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/MIsc. Date: 25.02.2022

ADST/Kalyan

Sub:- Provision of Internet and Telephone connection to SSE/Works section

--\*\*--

This office “Works section” is to be relocated at other location (Old ADEEs Chambers). In existing Works Section there are 03 internet connection and 01 telephone connection present.

You are requested to shift or provide 03 Internet and 01 Telephone connection in the new location bearing the telephone extension number 63355.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/MIsc. Date: 15.02.2022

CWM/ELW/BSL

Sub:- Expenditure occurred in attending the defect of Tap Changer

Sr.No. TCP-19050011-03 of loco No.21932

Ref: (i) Your letter No.BSL/ELWTender/2017-18/65 dated 18-01-2022

(ii) LOA No.ELW/BSL/Tender/2017-18/65 dated 04-06-2019

(iii) ELS/KYN’s Joint No.ELS/KYN/ACE/JN/REPL/168-A dated

14-12-2019.

--\*\*--

With reference to your above referred letter at Sr.No.(i), the expenditure occurred in attending the defect of Tap Changer Sr.No. TCP-19050011-03 of loco No.21932 on 07-10-2019 by this shed’s staff works out to Rs 436.50 say Rs 437.00.

This is for your information and further action at your end.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/E-Tender Date: 15.02.2022

WAO (ELW) BSL

Sub:- IPAS access to process contractual bills for RSP item

--\*\*--

Shri G.K.Sharma, SSE (Works) is having IPAS I/D of Mumbai Division (Sr.DFM/CSMT) for dealing contractual bills.

Now some contractual bills pertaining to RSP items, for which you are associated finance, are to be dealt by this office.

You are therefore requested to provide IPAS access to the above concerned staff of this unit. The particulars of staff are as under:

1. Name : Shri G.K.Sharma
2. Designation : SSE (W)/TRS/KYN
3. PF No. : 00201772739
4. Date of Birth : 27-10-1963
5. Mobile Number registered on IPAS : 9004411315
6. Email I/D : ssewk.elskyn@gmail.com

It is requested to allot ID and password in favour of above staff so that the bill can be processed to your office

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2017/26/Tap Changer Date: 08.02.2022

**Dy. CVO (EL) / CSMT**

Sub : Information related to LOA No. ELS/KYN/WKS/2017/26/Tap Changer

dated 12-9-2018 for “Repair, Rehabilitation, Reconditioning, Testing and

Supply of Tap Changer at Electric Loco Shed, Kalyan, Qty – 10 Nos.

Ref Your letter No. BSD/2021.10.01608 dated 07-02-2022.

--\*\*--

Para wise information sought vide above referred letter for subject mentioned tender is as follows:

1. Cost of new Tap Changer is Rs 41,76,610/- (inclusive of 18% GST) vide P O No. 52205146100073 dated 18-08-2021 of SMM/ NR/Saharanpur. (Copy enclosed)
2. Revamping cost of Tap Changer shall be within 60% of cost of new tap changer as per Railway Board’s letter No.2000/Elec (TRS)/132/1 dated 17-09-2001. (Copy enclosed)
3. Performance of repaired and overhauled tap changers after fitment on locomotives is found to be satisfactory till date completing 2 to 3 years’ service successfully.
4. Codal life of Tap Changers is 35 years as per Railway Board’s letter No. 2015/AIMS&AR/ED/FAR/ED’s Committee dated 18-03-2016.
5. (a) Codal life of Electric Locomotives is 35 years as per Railway Board’s letter No. 2015/AIMS&AR/ED/FAR/ED’s Committee dated 18-03-2016. Residual life of locomotives on which repaired and rehabilitated tap changers are fitted is as below:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr.  No. | Loco No. | DOC of Loco | Residual life of Locos | Sr.  No. | Loco No. | DOC of Loco | Residual life of Locos |
| 1 | 21866 | 11-12-1995 | 08 Years | 6 | 21952 | 25-04-1998 | 11 Years |
| 2 | 21945 | 11-03-1998 | 11 Years | 7 | 27259 | 14-10-1997 | 10 Years |
| 3 | 27138 | 27-10-1996 | 09 Years | 8 | 21955 | 05-05-1998 | 11 Years |
| 4 | 27277 | 30-12-1997 | 10 Years | 9 | 21949 | 28-03-1998 | 11 Years |
| 5 | 21868 | 18-09-1995 | 08 Years | 10 | 21893 | 22-05-1997 | 10 Years |

1. (b) Codal life of tap changer is 35 years. Date of manufacturing of tap changers which are repaired and rehabilitated along with their residual life is as under:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr.No. | Original Tap Changer No. | Sr.No. of Tap Changer after repair | Year of Tap Changer Manufacturing | Residual life of Tap Changers |
| 1 | 40B96973 | TCR-1811112-01 | 1996 | 09 years |
| 2 | 40D971216 | TCR-1811112-02 | 1997 | 10 Years |
| 3 | 40A96959 | TCR-1811112-03 | 1996 | 09 years |
| 4 | 40B971149 | TCR-1902127-01 | 1997 | 10 Years |
| 5 | 40D95930 | TCR-1902127-02 | 1995 | 08 Years |
| 6 | 40C971170 | TCR-1907156-01 | 1997 | 10 Years |
| 7 | 40D961047 | TCR-1907156-02 | 1996 | 09 years |
| 8 | 40A95808 | TCR-2001186-02 | 1995 | 08 Years |
| 9 | 40B991474 | TCR-2001186-01 | 1999 | 12 Years |
| 10 | S22376 | TCR-2003196-01 | 1997 | 10 Years |

Residual life of repaired/ rehabilitated tap changer is 8 to 12 years and residual life of locomotives on which these tap changers are provided is also within 8 to 11 years. Normally locomotive is not condemned after exact codal life of 35 years. It may be seen that residual codal life of tap changer and locomotives are almost same. However if life of any tap changer found balance, the same will be utilized in another locos as present holding of locomotives provided with tap changers is 147 locomotives.

(Hemant Jindal)

Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| मध्य रेल  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | Central Railway  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/CVO Date: 02.02.2022

CVO (S&T)/ CSMT

Sub:- Contracts awarded at abnormally low price

Ref:- Your office letter no.2022/G.130/Misc/V.Con dated 21.01.2022

--\*\*--

In reference to your letter mentioned above, there is no contract awarded at abnormally low price pertaining to Electric Loco Shed, Kalyan during the years 2019, 2020, 2021 and 2022 (till date)

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

Central Railway Office of the

Sr.DEE(TRS)KYN

Date : 01-02-2022

**Note**

As per discussion with CVI (El) CSMT, following information are furnished in connection with “Repair, Rehabilitation, Reconditioning, Testing and Supply of Tap Changer at ELS/KYN by M/s River Engineering Pvt. Ltd, Greater Noida, UP.

1. Final Joint Inspection reports of all 10 tap changers are enclosed.
2. HQ’s letter No.L.253.AC/AMC Policy dated 08-08-2016 for works tenders including “Repair/ reconditioning/ rehabilitation of all electric loco items” costing less than Rs 20 Cr are to be dealt at division/ workshop level as per provision of SOPGEN is enclosed.
3. RDSO’s approved list is enclosed herewith.
4. Codal life of Electric Locomotive is 35 years as per Railway Board’s letter No.2002/AC-II/1/10 dated 24-05-2006. Date of commissioning of locos on which rehabilitated tap changers are installed is given in Annexure I.
5. No loco was condemned from Sept 2018 to Dec 2021.
6. There is no pending PO for procurement of Tap Changers from Sept 2018 to Dec 2021.

SSE (ACE) KYN

DEE (TRS) KYN

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2021/GeM User Date. 11.01.2022

**Sr.DMM / (CSMT)**

Sub: Creation of Account on Government E-Market Place (GeM)

--\*\*\*--

With reference to above, following officer is nominated for registration on Government E-market place (GeM), his particulars are as under:

|  |  |
| --- | --- |
| Name (in full) | Shri Hemant Jindal |
| Designation | Sr.DEE (TRS) Kalyan |
| E-mail (only “gov.in” domain | [srdeetrskyn@bb.railnet.gov.in](mailto:srdeetrskyn@bb.railnet.gov.in) |
| Mobile No./ CUG No. | 8828119305 |
| Office Address | Office of Sr. DEE (TRS), Electric Loco Shed,  Kalyan - 421 301 |
| Office Phone No. | 0251 6763110 |
| Employee Id | 00208765133 |

**(Hemant Jindal)**

**Sr. DEE (TRS) Kalyan**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2015/01/ Date: 07.01.2022

**Sr.DEE (TRS) Ajni**

Sub:-Sr.DEE(TRS) AQ’s LOA No.ELS/AQ/DRG/WCQ/17-18/05 (TFP Coil type)

For “Repairing of Transformer type HETT 5400 (Copper Coil type) for

WAG-7 type conventional locomotives

**Releasing of Security Deposit**

Ref : Your letter No. ELS/AQ/DRG/WCQ/17-18/05 (TFP Coil type) dated 22-12-2021

--\*\*--

With reference to above referred letter following remarks are offered:

1. Proposal sent to Sr.DFM/CSMT for obtaining clearance/ NOC to release the bank guarantee towards PG.
2. Performance Report of repaired transformer is as given below:

Transformer type HETT 5400 KVA bearing Sr.No. 2011297 (coil type) repaired/ rehabilitated by M/s Vishwas Power Engg. Services Pvt. Ltd., Nagpur, was received on 15-12-2018 at ELS KYN and commissioned on loco no. 27138 on 05-01-2019.

Above transformer was lifted by firm on 19-12-2020 for under warranty defect attention (abnormal DGA). After attending defects, same transformer was received back at ELS/KYN on 20-02-2021 vide challan No.VPES/20-21-GST/K-5/71 dated 17-02-2021. This transformer was fitted on loco No. 27101 on 15-07-2021 and the same is working satisfactorily till date.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No. ELS KYN/WKS/2021/29/Transportation Date: 18-12-2021**

**Sr.DMM/Stores**

**CSMT**

Sub: 1. Transportation of Railway Material through road transport between Electric Loco Shed Kalyan and anywhere in India including cost of fuel, toll and other consumables, salary of driver & cleaner, road/ toll tax, repair & maintenance including insurance charges for a period of two years for loading capacity 09 Tonne for 95,000 KMs and for 15 Tonne for 20,000 KMs and

2. Hiring of 01 Number of Truck having capacity of 06 MT for attending breakdown & material assistance for Mumbai Division depots including cost of fuel, toll and other consumables, salary of driver & cleaner, road/ toll tax, repair & maintenance including insurance charges for a period of 24 months

Total Cost- Rs.63,52,706 /-

---\*\*\*---

Sr.DFM/CSMT’s concurrence for subject mentioned work was accorded vide letter No.BB/AC/FX-I/Prop/36633 dated 15.11.2021, Note No.#24 dated 23.11.2021 of e-office File No.CR-MUM0ETRS(ETTC)/56/2021-O/o SR DEE/ELS/KYN/MUM/CR.

Vide Note No. # 29 dated 03.12.2021, ADRM(OP)/MUM/CR has accorded sanction to the subject work in terms of item No.41 Part-A of Model SOP-2018.

Vide office note of even No. dated 06.12.2021, Sr.DEE(TRS)KYN has sanctioned the Detailed Estimate No. ELSKYN/WKS/2021/19 dated 26.08.2021 for the subject work in terms of item No. 2 (C) Part A of Model SOP-2018.

Now this proposal is to be processed though services on Gem as hiring of vehicles is one of the services mentioned in Railway Board’s letter No.2020/RS (G)/779/3 dated 17-06-2020.

Scope of Work/ Technical Specification, Special Conditions of Contract, Payment Terms and Penalty Clause etc duly approved by competent authority are sent herewith for inviting this service through Gem.

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/16/Tap Changer Date: 27.12.2021

**Sr.DEE (TRS) BSL**

Sub:-This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/

00967350038710 dated 21-07-2021 for Repair, Rehabilitation, Reconditioning,

Testing and Supply of Tap Changer of Electric Locomotives based at Electric

Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.

Ref : (i) This office letter of even No. dated 11-08-2021

(ii) This office letter of even No. dated 24-09-2021

--\*\*--

LOA including Specification and Scope of work was sent to you vide this office letter referred at Sr. No. (i) above. Further PBG, Indemnity Bonds were sent vide this office letter referred at Sr. (ii)

Now agreement No.ELSKYN/WKS/2020/16/TC dated 04-10-2020 has been signed. This agreement contains Power of Attorney and its legal vetting from LAW Section, 3 Indemnity Bonds and their legal vetting from LAW Section, Bank Guarantee Bond towards PG along with its confirmation from Bank and legal vetting from LAW Section.

One copy of agreement duly verified by WAO(ELW) Bhusawal vide letter No. AC/W/BSL/FX/AGREEMENT/33 dated 06-12-2021 is sent herewith for your reference and records. One original agreement copy is available at WAO (ELW) Bhusawal office.

Further original Indemnity Bond dated 31-07-2021 for Rs 1,90,00,000/- pertaining to your office is sent herewith for your records and reference.

As stated earlier Law vetting charges of Rs 200/- each for documents verified by LAW Section shall be deducted from this end.

Please acknowledge the receipt.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/16/Tap Changer Date: 27.12.2021

**Sr.DEE (TRS) Ajni**

Sub:-This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/

00967350038710 dated 21-07-2021 for Repair, Rehabilitation, Reconditioning,

Testing and Supply of Tap Changer of Electric Locomotives based at Electric

Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.

Ref : (i) This office letter of even No. dated 11-08-2021

(ii) This office letter of even No. dated 24-09-2021

--\*\*--

LOA including Specification and Scope of work was sent to you vide this office letter referred at Sr. No. (i) above. Further PBG, Indemnity Bonds were sent vide this office letter referred at Sr. (ii)

Now agreement No.ELSKYN/WKS/2020/16/TC dated 04-10-2020 has been signed. This agreement contains Power of Attorney and its legal vetting from LAW Section, 3 Indemnity Bonds and their legal vetting from LAW Section, Bank Guarantee Bond towards PG along with its confirmation from Bank and legal vetting from LAW Section.

One copy of agreement duly verified by WAO(ELW) Bhusawal vide letter No. AC/W/BSL/FX/AGREEMENT/33 dated 06-12-2021 is sent herewith for your reference and records. One original agreement copy is available at WAO (ELW) Bhusawal office.

Further original Indemnity Bond dated 31-07-2021 for Rs 1,00,00,000/- pertaining to your office is sent herewith for your records and reference.

As stated earlier Law vetting charges of Rs 200/- each for documents verified by LAW Section shall be deducted from this end.

Please acknowledge the receipt.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No: ELSKYN/WKS/2020/21/Medha/AMC-SIV Date: 27.12.2021

**Sr.DEE (TRS) BSL/ AQ**

Sub:-This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-21-AMC-

SIV/00987030036441 dated 04-06-2021 for “Comprehensive Annual Maintenance Contract (AMC) of Medha make Static Inverter (SIV) for a period of three years as per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed, Kalyan, Bhusawal & Ajni

--\*\*--

Agreement No.ELSKYN/WKS/2020/21/Medha/AMC-SIV dated 05-08-2021 against subject mentioned LOA has been signed. This agreement contains Bank Guarantee Bond towards PG along with its confirmation from Bank and legal vetting from LAW Section, Specific Power of Attorney and its legal vetting from LAW Section.

One copy of agreement duly verified by Sr.DFM/CSMT vide letter No. AC/W/BSL/FX/AGREEMENT/33 dated 06-12-2021 is sent herewith for your reference and records.

Law vetting charges of Rs 200/- each for documents verified by LAW Section shall be deducted from this end.

Please acknowledge the receipt.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@bb.railnet.gov.in |

No. ELSKYN/WKS/2021/31A/Imprest Date.17.12.2021

Sr. DFM. CSTM

Sub: Submission of Cash Memo against the Special Imprest Cash of Rs 50,000/-

to meet the expenditure for GM’s visit to Electric Loco Shed, Kalyan

Ref : (i) This office letter of even No. dated 08-09-2021

(ii) Sr.DFM/CSMT’s concurrence letter No.BB/AC/FX-I/Imprest/

36227 dated 03-09-2021.

--\*\*\*--

Vide this office letter referred at Sr. No.(i), Pay Order No. 118089 dtd 07-09-2021 for Rs 50,000/- duly budgeted and allocated was sent to you for arranging payment. Bill No. 01022110398 dated 09-09-2021 for Rs 50,000/- against this Pay Order was forwarded on AIMS.

Cash Memo No.SR2122/06 dated 17-09-2021 for Rs 50,625/- by SR Innovations, Airoli, Navi Mumbai- 400 708 for expenditure incurred against above Special Imprest is sent herewith for your accountal.

(Mohan Choudhary)

DEE/TRS)/ I/ Kalyan.

DA:- Cash Memo SR2122/06 dated 17-09-2021 in original

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

**No. ELSKYN/WKS/2016/38/Pit Lighting Date: 17-12-2021**

**Sr.DFM/ CSMT**

Sub: Contract Agreement No. ELSKYN/WKS/2016/38/Pit Lighting dated 16-08-2018

in connection with “Major repairs of Pit Lighting in ELS/Kalyan”

---\*\*\*---

Above mentioned contract was placed to M/s E-Mac Opto Electronics Pvt. Ltd., Mumbai -02 this office LOA No. ELSKYN/WKS/2016/38/Pit Lighting dated 26-03-2018 at a total cost of Rs 8,35,167 /- (Including GST). The original completion period of said contract was 6 months i.e. upto 25-09-2018 with original completion period upto 25-09-2018, extended up to 31-01-2019 and further extended up to 31-07-2019 with token penalty of Rs 5,000/-.

The firm has submitted requisite Performance Guarantee Rs 41,760/- in the form of FDR No.KM 188258 (A/c No.0107401005473/7) dated 11-05-2018, maturing on 11-05-2019 and extended upto 04-05-2020. This is in safe custody at your end. The firm have not extended the FDR validity period.

The firm has carried out work partially and payment for the same has been released through Ist on account bill. Thereafter the firm have not executed any work. Repeated reminders and phone calls have been made to complete the balance work and to rectify the defects but the firm has not responded and completed the contract.

As firm has failed to complete the work, subject mentioned contract has been rescinded in terms of Clause 62 of Standard General Conditions of Contract duly approved by competent authority vide this office note of even No. dated 07-12-2021 and EMD/ PG/ SD and amount deducted from bill against 15% BG is being forfeited.

You are therefore requested to forfeit following amount submitted by M/s E-Mac Opto Electronics Pvt. Ltd., Mumbai -400 002

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr.  No. | Description | Mode of Payment | Amount | Forwarding letter to A/cs |
| 1. | EMD | IREPS Ref ID No.PE1869551 / Bank Trans No. IGACYJUJG6 dated 20-02-2018 | 15,500/- | Letter No. ELSKYN/WKS/2016/38/Pit Light dated 08-05-2018. |
| 2. | Performance Guarantee | FDR No.KM 188258 (A/c No. 0107401005473/7 dated 11-05-2018 | 41,760/- | Letter No. ELSKYN/WKS/2016/38/ Pit Light dated 19-09-2020 for passing f 20% balance payment. (80% was released in lockdown period as per JPO) |
| 3 | Security Deposit | Deducted from Bill | 26,260/- | Deducted from Ist on A/c Bill No.E-Mac/ 18-19/264-265 dated 12-07-2019, AIMS bill No. 01022001110.  (Passed during lock down period) |
| 4 | 15% BG as per Terms of Payment | Deducted from Bill as firm has not submitted requisite BG of 15% | 85,625/- | --do-- |
|  |  | Total | 1,69,145/- |  |

Please forfeit above mentioned amount and deposit in appropriate head of A/c.

(Mohan Choudhary)

DEE(TRS)Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com) |

No. ELSKYN/WKS/2021/GeM User Date. 14.12.2021

**Sr.DMM / (CSMT)**

Sub: Creation of Account/user on GeM portal

--\*\*\*--

This office is required to create new ID on GeM Portal. The details are as under:

1. Name - Shri Hemant Jindal
2. Designation - Sr.DEE (TRS) Kalyan
3. Active Rail net email - [srdeetrskyn@bb.railnet.gov.in](mailto:srdeetrskyn@bb.railnet.gov.in)
4. Mobile No. - 8828119305
5. Office Address - Office of Sr. DEE (TRS), Electric Loco Shed,

Kalyan - 421 301

1. Role - Buyer/Consignee
2. PF No. - 08765133

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No. ELSKYN/WKS/2017/24/DBR Repair Date. 10.12.2021

**Sr.DEE(TRS) AQ**

Sub: C .A. No. ELS/AQ/DRG/WCQ/18-19/01 dated 03-01-2019 for “Repairs

of Complete Dynamic Braking Resistance (DBR) of A C Locomotives

of ELS/Ajni, BSL, KYN & ELW/BSL.

**Unutilized qty of ELS/KYN**

Ref: (i) Your letter No.ELS/AQ/DRG/WCQ/18-19/01 dated 03-12-2021

(ii) This office letter of even No. dated 15-11-2021

--\*\*\*--

With reference to your letter under ref – 1, it is confirmed that repairing work of balance 6 Nos. DBR for ELS/KYN against above mentioned contract is not required now.

Utilization of KYN’s balance 6 Nos. qty for ELS/BSL is not agreed due to paucity of funds under Revenue. This may be operated on ELS/BSL’s account by utilizing their funds/ revising estimate for additional quantity.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No. ELSKYN/WKS/2017/24/DBR Repair Date. 15.11.2021

**Sr.DEE(TRS) AQ**

Sub: C.A. No. ELS/AQ/DRG/WCQ/18-19/01 dated 03-01-2019 for “Repairs

of Complete Dynamic Braking Resistance (DBR) of A C Locomotives

of ELS/Ajni, BSL, KYN & ELW/BSL.

--\*\*\*--

A works contract for the above mentioned work was awarded to M/s Daulat Ram Engineering Services Private Ltd., KH no 10/2, NH-12, Village Simrai, Raisen – 464 993 (MP) vide Sr.DEE(TRS) AQ’s LOA No. ELS/AQ/DRG/WCQ/18-19/01 (DBR) dated 27-08-2018.

In above contract, ELS/KYN’s quantity was 30 Nos. Out of which the firm have completed the work of 24 Nos. Dynamic Barking Resistance (DBR) as per Railway`s scope of work and specifications and 100% payment for the same has been released.

Total 12 Nos. complete Dynamic Braking Resistance with AC MVRF have been sanctioned in RSP vide item No. 2046/2020-21. Out of which 10 Nos. have been received from M/s Stesalit Telema Electricals Pvt. Ltd, and 2 Nos. are yet to be received from Daulat Ram Engineering Services, Bhopal.

As sufficient quantity of DBR is now available, it is not necessary to carry out the repairing work of balance 6 Nos. DBR for ELS/KYN against above mentioned contract

You are therefore requested to short close the ELS/KYN’s quantity of 6 Nos.DBR in above mentioned contract as repairing of these DBR is not required now.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2020/16/Tap Changer Date: 11.11.2021

**WAO (ELW) BSL**

Sub:- Contract Agreements No. ELSKYN/WKS/2020/16/TC dated 04.10.2021 for the work of “Repair, Rehabilitation, Reconditioning, Testing and Supply of Tap Changer of Electric Locomotives based at Electric Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.

Ref : LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/00967350038710 dated 21.07.2021

--\*\*--

Subject work is to be carried out against three itemized and Bulk RSP items for Repair and Rehabilitation of Tap Changer on Electric Locos of ELS Kalyan, Bhusawal and Ajni. as per Itemised PB Item No.1956/2019-20 Estimate No. ELS/KYN/RS/RSP/2019/26 dtd 13.09.2019 for Qty- 10 Nos., Itemised PB Item No.2067/2020-21, ELS/KYN/RS/RSP/2020/27 dtd 13.07.2020 for Qty- 11 Nos. and Itemised PB Item No.1309/2020-21, ELS/KYN/RS/Bulk RSP/2020/33 dtd 13.07.2020 for Qty- 49 Nos.

Now, 03 Nos. Contract Agreements (Each for ELS Kalyan, Bhusawal & Ajni) has been prepared for the subject work awarded to M/s River Engineering Pvt Ltd, 54-55, Toy City, Ecotech-III, Greater Noida, Noida – 201206 vide LOA No.ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/00967350038710 dated 21-07-2021

These 03 Contract Agreements are sent herewith for verification/vetting and Budget. Kindly return the same after verification/vetting and Budget to this office.

SANJESH

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No. ELS KYN/WKS/2020/12/AMC-AAL SIV Date: 18.10.2021

**Sr.DEE(TRS) AQ**

Sub: Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA Static Inverter (SIV) fitted in conventional locomotives of Electric Loco Shed, Kalyan for a period of three years as per RDSO’s SMI No. RDSO/2016/EL/ SMI/0291 (Rev 0) Qty -09 Nos.

Ref : This office letter of even No. dated 16-08-2021

---\*\*\*---

Please connect this office letter referred above vide which ADRM/BB’s administrative approval for the subject work though Single Tender from OEM was sent to you and it was stated that sanctioned proposal and estimate will be submitted as soon as it received.

Now this proposal has been concurred by Sr.DFM/CSMT vide letter No.BB/AC/FX-I/Prop/36146 dated 25.08.2021/ e-office Note No.#18 dated 06-10-2021 for “Comprehensive AMC of 09 Nos. (9855 loco days) AAL make 180 KVA Static Inverters (SIV) in locomotives based on HQ’s LOA No.L.253.AC/AMC/AAL-SIV dated 07-08-2018 for Rs.50,21,126.44 (incl of 18% GST) (@ Rs 431.78 per loco day rate plus GST) for a period of 3 years.

As stated by Sr.DFM/ CSMT, ADRM’s sanction to the above proposal in terms of item No. 39 (e) Part-A of Model SOP-2018 has been obtained vide this office note of even no. dated 08.10.2021 (Pg-17-Reverse), e-office Note No.#23 dated 12-10-2021.

Sr.DEE(TRS) KYN has accorded sanction to detailed estimate No. ELSKYN/WKS.2021/14 dated 15.06.2021 in terms of item No.2 (C) Part-A (Works Matter) of Model SOP 2018 vide office note of even No. dated 18-10-2021.

All above documents i.e. Sr.DFM/CSMT’s concurrence letter, ADRM/BB’s sanction and Detailed estimate sanctioned by Sr.DEE (TRS) Kalyan are enclosed herewith for further necessary action.

(SANJESH)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

No: ELSKYN/WKS/2020/16/Tap Changer Date: 24.09.2021

**Sr.DEE (TRS) BSL/ AQ**

Sub:-This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/

00967350038710 dated 21-07-2021 for Repair, Rehabilitation, Reconditioning,

Testing and Supply of Tap Changer of Electric Locomotives based at Electric

Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.

Ref : This office letter of even No. dated 11-08-2021

--\*\*--

Please connect this office letter referred above vide which Copy of LOA No.ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/00967350038710 dated 21-07-2021 on M/s River Engineering Pvt Ltd, 54-55, Toy City, Ecotech-III, Greater Noida, Noida – 201206 for subject mentioned work including Specification and Scope of work were sent to you.

The firm has submitted requisite Bank Guarantee towards Performance Guarantee and Indemnity Bonds for lifting of material. The same have been verified by LAW Section of this administration.

Following documents are sent herewith for your record and further action.

|  |  |  |  |
| --- | --- | --- | --- |
| Sr.  No. | Description of Document | Amount | LAW Section’s letter |
| 1. | Performance Guarantee- BG No. 01791ILG009421 dated 07-08-2021 issued by Punjab National Bank, Cannaught Place, New Delhi | Rs 45,00,000/- | BB.W.LEG.Vetting-Elc dated 06-09-2021 |
| 2. | Indemnity Bond dated 31-07-2021 in favour of Sr.DEE/TRS/BSL for qty of 19 Nos. | Rs 1,90,00,000/- | BB.W.LEG.Vetting-Elc dated 06-09-2021 |
| 3. | Indemnity Bond dated 31-07-2021 in favour of Sr.DEE/TRS/AQ for qty of 10 Nos. | Rs 1,00,00,000/- | BB.W.LEG.Vetting-Elc dated 06-09-2021 |

Law vetting charges of Rs 200/- mentioned in each letter for above documents shall be deducted from this end.

Contract Agreement for subject work is under preparation. The same will be submitted to you after vetting from WAO/BSL.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – 421 301  फ़ोन / फैक्स :- 0251 - 2361293/2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS)  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No.KYN/RS/Misc Date: 18.10.2021

**ACM (Res)**

**CCM’s office CSMT**

Sub: **Release of One Berth by 01013 of dt 19-10-2021**

Kindly arrange to release One berth by 01013 dt. 19-10-2021. The particulars are given below:-

|  |  |  |
| --- | --- | --- |
| 1 | Name | Ms Delina Dennis Kurisinkal |
| 2 | PNR No | **8642975528** |
| 3 | Train No | **01013 (LTT- CBE SPL)** |
| 4 | Date of Journey | **19-10-2021** |
| 5 | Destination | SBC |
| 6 | Class | III AC |
| 7 | No. of berth | One |
| 8 | Reason | Proceeding for Joining Service (Job) |
| 9. | Mobile | 8652125767 |

**(Hemant Jindal)**

**Sr.DEE (TRS) KYN**

**Mob.No.8828119305**

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2020/16/Tap Changer Date: 24.09.2021

**Sr.DEE (TRS) BSL/ AQ**

Sub:-This office’s LOA No. ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/

00967350038710 dated 21-07-2021 for Repair, Rehabilitation, Reconditioning,

Testing and Supply of Tap Changer of Electric Locomotives based at Electric

Loco Shed, Kalyan, Bhusawal & Ajni, Qty – 70 Nos.

Ref : This office letter of even No. dated 11-08-2021

--\*\*--

Please connect this office letter referred above vide which Copy of LOA No.ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/00967350038710 dated 21-07-2021 on M/s River Engineering Pvt Ltd, 54-55, Toy City, Ecotech-III, Greater Noida, Noida – 201206 for subject mentioned work including Specification and Scope of work were sent to you.

The firm has submitted requisite Bank Guarantee towards Performance Guarantee and Indemnity Bonds for lifting of material. The same have been verified by LAW Section of this administration.

Following documents are sent herewith for your record and further action.

|  |  |  |  |
| --- | --- | --- | --- |
| Sr.  No. | Description of Document | Amount | LAW Section’s letter |
| 1. | Performance Guarantee- BG No. 01791ILG009421 dated 07-08-2021 issued by Punjab National Bank, Cannaught Place, New Delhi | Rs 45,00,000/- | BB.W.LEG.Vetting-Elc dated 06-09-2021 |
| 2. | Indemnity Bond dated 31-07-2021 in favour of Sr.DEE/TRS/BSL for qty of 19 Nos. | Rs 1,90,00,000/- | BB.W.LEG.Vetting-Elc dated 06-09-2021 |
| 3. | Indemnity Bond dated 31-07-2021 in favour of Sr.DEE/TRS/AQ for qty of 10 Nos. | Rs 1,00,00,000/- | BB.W.LEG.Vetting-Elc dated 06-09-2021 |

Law vetting charges of Rs 200/- mentioned in each letter for above documents shall be deducted from this end.

Contract Agreement for subject work is under preparation. The same will be submitted to you after vetting from WAO/BSL.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No.ELSKYN/WKS/2021/Imprest Date: 08-09-2021

**Sr.DFM/ CSMT**

Sub: Releasing of special imprest cash of Rs 50,000/- to meet the

expenditure for GM’s visit to Electric Loco Shed, Kalyan.

Ref: Sr.DFM/CSMT’s concurrence letter No.BB/AC/FX-I/Imprest/

36227 dated 03-09-2021

--\*\*\*--

Sr.DFM/CSTM has accorded concurrence for “Creation of one time special cash imprest amounting to Rs 50,000/- to meet the expenditure towards GM’s visit at to Electric Loco Shed, Kalyan” vide eoffice Note No.#9, letter No.BB/AC/FX-I/Imprest/36227 dated 03-09-2021.

Further ADRM’s approval and sanction for the same has been obtained vide eoffice Note No.#14 dated 07-09-2021.

Now Pay Order No.118089 dated 07-09-2021 duly budgeted and allocated is sent herewith for arranging payment in favour of Sr.DEE(TRS)Kalyan.

DEE(TRS)Kalyan

For Sr.DEE (TRS) Kalyan

DA : As above

Budget Supervisor : Please budget the enclosed Pay Order No,118089

Dated 07-09-2021

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- srdeetrskyncrly@gmail.com |

No.ELSKYN/WKS/2021/Imprest Date: 30-08-2021

**Sr.DFM/ CSMT**

Sub: Creation of special imprest to meet out the expenditure for GM’s visit

to Electric Loco Shed, Kalyan to be held on 08-09-2021.

--\*\*\*--

GM/ Central Railway’s visit to Electric Loco Shed, Kalyan is planned on 08-09-2021. Necessary up keeping and maintenance of shed is in progress.

For this purpose expenditure is to be incurred for following activities which cannot be done departmentally.

1. Inauguration of newly commissioned machine and renovated section is planned to be done. Some inauguration boards including associated items are to be prepared/ procured.
2. Loco position board in PPIO section is to be made.
3. GM Welcome Board and Loco Shed Layout board is to be made
4. Some new Flex Boards for safety slogan, safety instructions, maintenance practices, important parameters of loco equipment and Section Team Boards etc are to be made and some existing boards are to be repaired.
5. Procurement of material for decoration like rangoli materials, flowers and garland etc.
6. Any other emergent charges which cannot be foreseen.

Approx. expenditure of Rs 50,000/- is assessed to be incurred for this occasion.

It is therefore requested to accord finance concurrence for ‘One time special cash imprest to meet out the expenditure for GM’s visit to Electric Loco Shed, Kalyan” at a total cost of Rs 50,000/- in terms of item No. 1 (A) Part of C of Model SOP 2018.

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/WC Date: 30.08.2021

**Dy CVO (EL)/ CSMT**

Sub:- Mechanism to monitor closure of contracts.

Ref:- Your office letter no.G.139/2017/12/Misc/V4/V.con dated 20-08-2021

--\*\*--

In reference to your letter mentioned above, details of works contracts pertaining to Electric Loco Shed, Kalyan in requisite format sent herewith as Annexure.

(Hemant Jindal)

Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/LAR Date: 18.08.2021

**Sr.DEE (TRS) KLVA**

**Central Railway**

Sub:- Submission of LAR

Ref:- Your office letter no.KLVA/RS/WKS/219R dated 16.08.2021

--\*\*--

In reference to your letter mentioned above, it is informed that the work of “Repair of Under Floor Wheel Lathe by OEM M/s HYT” has not been carried out at ELS/Kalyan since the machine is under CAMC through COFMOW AT since commissioning.

Thus, LAR for the same is not available with this shed.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/Furniture-2021 Date: 18.08.2021

**Sr.DEE (TRD) CSMT**

Sub:- Provision of funds for procurement of furniture at Electric Loco Shed, Kalyan

--\*\*--

During visit of Electric Loco Shed, Kalyan on 10.07.2021, CELE/C. Rly has pointed out the condition of furniture is very poor and emphasized for replacement of the same.

Furniture available at PPIO, Investigation and I & T Sections of ELS/Kalyan are very old and condition of these furniture is very bad and shabby. These are the section where visitor and all sections supervisors visits frequently for daily position meeting. The chairs and tables conditions are very poor and requires replacement. Some of the tables are made departmentally now condition of these tables are bad due to use for such long time. These furniture are not economical to repair hence need replacement.

Approximate cost for replacement of these furniture worked out from furniture policy dated 10.11.2017 will be Rs.14,58,526 /-

You are therefore requested to provide funds to the tune of Rs.15 Lakhs (Lump sum) against contingencies of any sanctioned work at your end to enable this office to proceed the case further.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2017/10/ AMC/SIV AAL Date: 16.08.2021

**Sr.DEE (TRS) AQ**

Sub: On Account bill for C.A. No. L.253 A C/AMC/AAL-SIV dated 22.03.2019 (HQ)

dated 22.03.2019 for “Comprehensive Annual Maintenance Contract (AMC)

of AAL make 180 KVA Static Inverter (SIV) fitted in conventional locomotives

of various electric loco sheds of Central Railway (i.e ELS KYN, BSL & AJNI)

for three years.”

Ref : HQ’s letter No. L.253.AC/AMC/AAL-SIV dated 07-08-2018

--\*\*--

Contract for subject mentioned work awarded to M/s Autometer Alliance Ltd, Noida is completing on 21-10-2021 as per HQ’s C.A.No. L.253.AC/AMC/AAL-SIV dated 22-03-2019.

This contract was awarded for 70 Nos. SIV ( i.e. SIVs of (i) ELS.AJNI – 27 Nos., (ii) ELS/BSL – 39 Nos., (iii) ELS/KYN – 04 Nos.)

Sanctioned estimate No.ELSKYN/WKS/2017/07 dated 08-05-2017 for 4 Nos. of SIV at a total cost of Rs 25,80,000/- was submitted to your office vide this office letter of even No. dated 20-07-2017, being ELS/AQ as nodal shed for processing of AMC of AAL make SIV.

Thus sanctioned estimate and funds are available for 4 Nos. SIVs at ELS/Kalyan.

Bill for AMC of first loco No.27410 transferred from ELS/AQ, for the period from 11-10-2019 to 21-10-2019 amounting to Rs 4,728/- has been released from this end.

Thereafter AMC of SIV of two more locos No.27259 (SIV No.OB 180-0701 041) and 27290 (SIV No. OB 180-1102-059) transferred from ELS/AQ have also been undertaken at ELS/KYN from 08-11-2019.

Now bills for five quarters i.e. from 22-10-2019 to 21-01-2021 including above additional quantity of 3 locos was forwarded to A/cs for verification. Total amount for these 3 locos works out to be Rs 5,81,544/- in this bill.

The bill is not verified by A/cs stating that sanction is available for 4 loco SIVs in Mumbai Division. Against this, 7 locos SIVs payment cannot be verified without exercising variation as expenditure will exceed the sanctioned cost. HQ has stated there is no variation in contract due to transferring of locos already covered in AMC, from one shed to another shed.

Further vide your letter No. ELS/AQ/DRG/AMC-SIV-AAL (HQ-129) dated 21-01-2021 two loco No.27205 and 27258 are also taken for AMC of SIV from 08-01-2021 at ELS/KYN. Bills for these locos will be released in next on account bill.

As sanctioned estimate and fund provision for above five locos originally belonging to ELS/AQ is available at your end, it is requested to give your consent that debit for payment towards the AMC of these transferred locos will be accepted and regularized at your end.

(Hemant Jindal)

Sr.DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्यरेल**  वरिष्ठमंडलविद्युतअभियंता (कचस्टॉक) कार्यालय  विद्युतलोकोशेड, कल्याण–४२१३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox)m |

No: ELSKYN/WKS/2021/20/ AMC-AAL Date: 16.08.2021

**Sr.DEE (TRS) AQ**

Sub:-Comprehensive Annual Maintenance Contract (AMC) of AAL make 180 KVA

Static Inverter (SIV) of Electric Loco Shed, Kalyan for a period of 3 years as

per RDSO’s SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed

Kalyan, Bhusawal and Ajni, Qty – 09 Nos.

Ref : HQ’s letter No. L.253.AC/AMC dated 23-07-2016

--\*\*--

Contract for subject mentioned work awarded to M/s Autometer Alliance Ltd, Noida is completing on 21-10-2021 as per HQ’s contract agreement No. L.253.AC/AMC/AAL-SIV dated 22-03-2019.

As per HQ’s letter under reference, ELS/AQ is nominated shed for processing of AMC of AAL make Static Inverter.

This shed’s fresh proposal for comprehensive annual maintenance contract of 09 locos fitted with AAL make SIV for a period of 3 years at a total cost of Rs 50,21,126.64 inclusive of 18% GST through Single Tender from OEM, has been approved by ADRM/BB. This proposal and detailed estimate is under Sr.DFM’s vetting presently.

It is requested to include ELS/KYN’s quantity in your tender as detailed in Estimate No. ELSKYN/WKS/2021/14 dated 15-06-2021. (Copy enclosed)

To simplify the scheduled rate for inclusion of any other SIV of any transferred loco after awarding of AMC , under variation clause in existing contract, LAR which is Rs 1,57,600/- per unit per year is converted in rate for per loco day. Thus converted LAR works out to be Rs 431.78 per loco day (i.e. Rs 1,57,600/ 365 days) and quantity of 9 Nos. SIV for 3 years is converted into 9855 loco days (i.e. 9 Nos. x 365 days x 3 years).

Sanctioned proposal and estimate shall be submitted to you as soon as received. In the meantime, it is requested to consider ELS/KYN’s above quantity in your tender for subject work.

(Hemant Jindal)

Sr.DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2020/16/Tap Changer Date: 11.08.2021

**Sr.DEE (TRS) BSL/ AQ**

Sub:-Repair, Rehabilitation, Reconditioning, Testing and Supply of Tap

Changer of Electric Locomotives based at Electric Loco Shed, Kalyan,

Bhusawal & Ajni, Qty – 70 Nos.

Ref : HQ’s letter No.L.733.Loco.S.9 dated 31-07-2020

--\*\*--

As per HQ’s above referred letter, ELS/KYN was nominated as nodal agency for execution of rehabilitation of Tap Changer against PB Item No. 1309/20-21 through works contract at divisional level.

Accordingly this office has placed LOA No.ELS-KYN-ELECTRICAL/ ELS KYN WKS-2020-16-TC-A/00967350038710 dated 21-07-2021 on M/s River Engineering Pvt Ltd, 54-55, Toy City, Ecotech-III, Greater Noida, Noida – 201206 for subject mentioned work including your quantity against Bulk RSP Item No.1309/20-21 as under:

ELS /BSL- 19 Nos.

ELS / AQ – 10 Nos.

.

Copy of the above LOA alongwith Part IV i.e. Specification and Scope of Work is sent herewith.

Submission of Power of Attorney, Indemnity Bond and Performance Guarantee is in process at this end.

(Mohan Choudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No. ELSKYN/WKS/2020/16/Tap Changer Date: 11-06-2021

Sr.DFM/CSMT

Sub: Nomination of A/cs member for opening of Open E-Tender No. ELSKYN-WKS-2020-

16- TC-A for “Repair, Rehabilitation, Reconditioning, Testing and Supply of Tap

Changer of Electric Locomotives based at Electric Loco Shed, Kalyan, Bhusawal &

Ajni Qty: 70 Nos.

--\*\*--

Technical bid (Packet I) of above mentioned tender was opened on 06-05-2021. Now Packet II i.e. Financial bid is to be opened for the same.

Please nominate A/c’s member for opening of the above bid at ELS/KYN.

(Mohan Choudhary)

DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2021/Policy/IR-WCMS Date: 28.05.2021

**GM, CRIS**

**New Delhi**

Sub:- Regarding linking of IR-WCMS user with division

Ref: E-mail correspondence dated 26.05.2021

--\*\*--

This office is facing problems in processing bills on IR-WCMS portal. Regarding this, an e-mail query was raised to you ([irwcms@cris.org.in](mailto:irwcms@cris.org.in)) asking the solution.

As desired by you in the reference mail, the details of this department mentioned in IPAS and the division is as under.

User Department in IPAS- 06-ELECTRICAL

IPAS Accounting - 0102-MUMBAI DIVISION CENTRAL RAILWAY

Division - MUMBAI, CENTRAL RAILWAY

You are requested to link ELS/Kalyan Unit to Mumbai division so that we can process the bill. Kindly do the needful as soon as possible.

(Hemant Jindal)

Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2021/Policy/IR-WCMS Date: 29.04.2021

**Sr.DEN (Co)/ CSMT**

Sub:- Provision of ID & Password for e-MB and e-Billing through IR-WCMS portal

--\*\*--

All the work contract bills are to be forwarded to Accounts Dept. by means of e-billing through IR-WCMS portal.

Therefore, you are requested to kindly arrange to provide ID & Password for this unit at the earliest in order to process e-MB and e-Billing through IR-WCAMS portal, so that the contractors pending bills can be processed to Accounts Dept. for passing payment through e-billing in IR-WCMS.

Email ID- [srdeetrskyncrly@gmail.com](mailto:srdeetrskyncrly@gmail.com)

(Mohan Chaudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan

|  |  |  |
| --- | --- | --- |
| **मध्य रेल**  वरिष्ठ मंडल विद्युत अभियंता (कचस्टॉक) कार्यालय  विद्युत लोको शेड, कल्याण – ४२१ ३०१-  फोन / फैक्स:- 0251- 2361293 & 2363563 | New Bitmap Image.bmp | **Central Railway**  Office of Sr. DEE (TRS),  Electric Loco Shed, Kalyan - 421 301.  Email :- [srdeetrskyncrly@gmail.cox](mailto:srdeetrskyncrly@gmail.cox) m |

No: ELSKYN/WKS/2020/21/Medha/AMC-SIV Date: 04.06.2021

**Sr.DEE (TRS) BSL/ AQ**

Sub:- Comprehensive Annual Maintenance Contract (AMC) of Medha make

Static Inverter (SIV) for a period of 3 years as per RDSO’s

SMI No. RDSO/2016/EL/SMI/0291 (Rev 0) at Electric Loco Shed Kalyan,

Bhusawal and Ajni

--\*\*--

This office has placed LOA No.ELS-KYN-ELECTRICAL/ELSKYNWKS-2020-21-AMC-SIV dated 04-06-2021 on M/s Medha Servo Drives Pvt. Ltd. Hydrabad for subject mentioned work including your quantity of Medha make SIV..

.

Copy of the above LOA alongwith Part IV i.e. Specification and Scope of Work is sent herewith.

(Mohan Chaudhary)

DEE (TRS) Kalyan

For Sr. DEE (TRS) Kalyan